## Matrix
Minimum suppport for all
Damage |  |  | Emergency |  | Temporary |  |  | Transitional |  |  | Recovery
Building status | Definition | House status | Current Emergency Phase - Location | All | Temporary shelter options | Self recovery | Most vulnerable | Transitional shelter options | Self recovery | Most vulnerable | Recovery | Self recovery | Most vulnerable
|  |  |  | # | 0 to 9mths | # | # | 6 to 24mths | # | # |  | # | #
Collapsed | Collapsed | Not habitable | Displaced - evacuation ctr (public space) or community space | 9978 | Camps - tents, temporary shelter, NFI, wash. ESA - 10,000Php | 0 | 9978 | Move back to home location and upgrade temporary shelter to transitional. | ?? | ?? | Rebuild house
|  |  | Non displaced - home base |  | Tents, temporary shelter, NFI, wash. ESA - 10,000Php | 0 |  | Move back to home location and upgrade temporary shelter to transitional. | ?? | ??
Damaged | Damaged beyond safe repair Structural integraty comprimised and cannot be repaired | Not habitable assume | Displaced - evacuation ctr (public space) or community space | 34779 | Camps - tents, temporary shelter, NFI, wash. ESA - 10,000Php | 0 | 34779 | Move back to home location and upgrade temporary shelter to transitional. | ?? | ?? | Rebuild
|  |  | Non displaced - home base |  | Tents, temporary shelter, NFI, wash. ESA - 10,000Php | 0 |  | Move back to home location and upgrade temporary shelter to transitional. | ?? | ??
| Damaged but can be safely repaired Structural integraty not comprimised and can be repaired | Habitable assume | Displaced - evacuation ctr (public space) or community space |  | Displaced - evacuation ctr (public space) or community space | [5 empty] | Repair
|  |  | Non displaced - home base |  | Non displaced - home base | [5 empty] | Retrofit
| Superficial damage | Habitable | Displaced - evacuation ctr (public space) or community space |  | Not required
|  |  | Non displaced - home base |  | Not required |  | - |  |  |  | Repair
Not damaged | Not dmaged or superfical damage only | Habitable | Displaced - evacuation ctr (public space) or community space |  | Not required
|  |  | Non displaced - home base |  | Not required
Totals |  |  |  | 44757 |  |  | 44757
|  |  | Totally destroyed | Partly destroyed | Total
|  | 2013-10-20 | 9978 | 34779 | 44757

## Phases
Phase | Emergency shelter | Temporary shelter | Transitional shelters | Recovery
Design life | Few weeks | minimum 6 months | minimum 24 months
Completed by | 3 weeks after the EQ | 4 weeks after the EQ | 12 months after the EQ
Activities | Plastic sheeting and salavaged materials | 1. Tents - family tent | 1. Transitional shelters: | 1. Full house:
|  |  | Upgrade of temporary shetlters | House design appropriate for the conditions
|  | 2. Temporary shelters: | Buildig materials - timber/bamboo/nippa plam/CGI
|  | Tarpaulins - 2 by 6x4 international grade | Salavaged materals
|  | Building materials - timber/bamboo/nippa plam | Fixing materials
|  | Salavaged materials | Designs and guidance - IEC, trainings
Fixing materials - rope, wire, nails, roofing nails
Building tools - hammer, saw, plyers
Demolition tools - pick, sledge hammer, shovels, crow bars
Designs and guidance - IEC, trainings
Govt Emergency Shelter Assistance:
Partly damaged = 5,000PHP
Totally damaged = 10,0000PHP
Some families will need supprt for every phase
Some families will have capacity to miss the temporary phase
Families will move striaght to recovery