Typhoon Haiyan

Shelter Cluster Meeting Minutes

Tacloban

Friday 15th Nov

Hub: Tacloban - Overall focus of the meeting was on shelter in district 8.

Chaired: DSWD/Shelter Cluster

Attended:  UNDP UNDAC, Save the Children, Acted, IOM, Solidarities, CCCM Cluster

## Key actions

Action 1) cluster coordinator to ensure that someone takes an active lead in coordinating debris removal and coconut timber salvage: Required Activiites include:

- prioritisation of sites requiring debris removal

- coordination with humanitarian actors to tie n with government debris removal progrmmes

- ensurng consistency in labour rtes and common approach to rates for salvaged cocnut timber

- provide a forum to share best practices in debris removal.

Action 2: cluster coordinator to consult with government on danger zones – if coastal areas are fit for return / rebuilding.

Action 3: cluster coordinator tocoordinate with Wash relating to Non food item (shelter) and hygiene kits

Action 4::Cluster members to conduct an assessment to support prioritisation of distribution sites.

- Assessment planned for 16/13/11 to cars coordinated with wash. One car to head east and one car to head south from tacloban. Each car to contain:

  - 1 wash cluster representative

  - 1 member from REACH to ensure common methodology

  - Members of responding organisations

Action 5: Shelter cluster coordinator to actively request an individual to support DSWD  to coordinate

## Overview:

- Role of government – priority is distribution plan

- DSWD shelter assessment – ongoing

- Total affected Baneguays  in Tacloban - 138

- USAID tents already at airport, consigned to DSWD

- Total municipalities coordinated out of Tacloban hub - 27

- Total municipalities coordinated out of Ormuz hub - 15

## Emergency shelter Planned distribution status

| 1.Iom | 5000 | tacloban | bgy aniborg 68-69 |  |
| --- | --- | --- | --- | --- |
| 2.UNHCR | 2500 |  |  |  |
| 3.USAID | 12,500 | tacloban | 11/14 |  |
| 4. ACTED | 1000 | Cebu | 11/16 |  |
| 5. Shelter box | 852 | cebu | 11/12 |  |
| 6. Plan / sbox | 504 | cebu | 11/12 |  |

Using data from other hubs, the following agencies are also planning shelter interventions

7. Samaritans purse (2000 rolls of plastic sheeting to arrive in Cebu)

8. Ifrc

9. Crs

10. Habitat for humanity

11. World vision

12. Food for r the hungry

13. Mediar

14. Care / accord

15. Child fund

Key documents on strategy and NFI technical guidelines are available from www.sheltercluster.org.#to subscrive to the cluster mailing list contact Coord.Phil@sheltercluster.org