SHELTER CLUSTER MEETING

Tuesday 29th October 2013
JJ’s @  4.15pm

Minutes

Started:  - Ended:

| Chair: | DSWD AssSecGudmalin GraceSubong – DSWD shelter focal point | gqsubong@dswd.gov.ph | 09177120024 |
| --- | --- | --- | --- |
| Co-Chaired: | Patrick Elliott, IASC Shelter Cluster Coordinator | Patrick.elliott@ifrc.org | 09084011218 |
| Team | Neil Bauman - Information manager David O’Meara – Technical Coordinator Eve Leonard – Technical Support | neil.bauman@sheltercluster.org tech.phil@sheltercluster.org Eve.leonard@ifrc.org | 09198854004 09087026648 0908411217 |
| List of Partners in attendance: |  |  |  |
| Oxafm |  |  |  |
| ADRA – no |  |  |  |
| UN – OCHA |  |  |  |
| ICT – no |  |  |  |
| IOM |  |  |  |
| PRCS |  |  |  |
| DAI |  |  |  |
| SHELTER BOX |  |  |  |
| UNDP |  |  |  |
| Habitat for Humanity |  |  |  |
| IFRC-PRCS |  |  |  |
| World Vision |  |  |  |
| All Hands |  |  |  |
| CRS |  |  |  |
| Plan International – no |  |  |  |
| UNICEF – Wash |  |  |  |
| DSWD representatives |  |  |  |
| IDEA - International Deaf Education Association |  |  |  |

- Introductions

- Last meeting/minutesof 24th reviewed and approved

- Agency Updates

DSWD :

- DSWD provided gave a presentation on their current achievements.

- Field Staff and validators and engineersdeployed.

- Relief distributions are on going in 3 areas -  for tents installations -  Loon, Sagbayan, Tubigon – figures are available on the WWW.

- DSWD highlighted their 17 priority/hardest hit based on:

- High level poverty incidence (50%)

- High level of damaged houses (25%)

- High level of displaced families (25%)

OXFAM:

- Challenges in validating beneficiaries.

- Government are encouraging people to go back home.

- Planning to construct communal latrines or home based latrines.

- 3 areas Clarin, Capale and Sagbayan.

Shelter Box:

- Challenges in validation of homes.

- There is damage but often the families are elsewhere – not at home

- Confirmation on the numbers affected is required.

World Vision:

- Validation of damage is a challenge – distributed 154 preposition tents in Catigbian & Antequera; Plan to distribute 4,239 tents with NFI to Danao, Sagbayan & San Isidro.

- Identification of partly damaged/totally destroyed – in some cases houses described as totally destroyed should be changed to partly damaged and some case partly damaged should be changed to totally destroyed.

All Hands:

- Have set up an office in Antequera.

- They have observed that affected populations are building temporary shelters with salvage materials.

- They have not seen a lot of people deconstructing houses.

- People are moving away from the roads back into their homes.

CRS:

- Distributing tarps in Sagbayan for their A frame design.

- They have a targeting criteria with a community driven self-selection process – based on damage, most vulnerable.

- So far about 80 to 90% of the community are included.

- Challenges: identification of households and verification of damaged and destroyed houses.

- Already planning to move into early recovery.

Idea –International Deaf Education Association:

- They have developed a prefabricated model 12x12 ft. homes. They build the panels in Tagbilaran and move them to the community.

- Made with coco lumberand bamboo matting. The cost is about 25,000 not including contributions from the community.

- They have budget for 100 units but would be interested to hear from other agencies who would like to support this initiative

PRSC/IFRC:

- Ongoing distribution of 11,000 international standard tarpaulins. So far 2400 distributed.

- Validation is ongoing for other areas for distribution

- Summary of challenges and recommendations:

- The numbers of damaged and destroyed houses needs further clarification.

- Validation need to be carried out by agencies on the ground.

- Reliable numbers is the totally damaged houses.

- Agencies at Municipality level must coordinate with each other.

- There should be one agency per Barangay so they can validate the numbers and identify gaps.

- Relocations

- It’s probable there will be relocations based on the results if MGB hazard mapping:

  - Liquefaction areas

  - Sink holes

  - Land slides

  - Fault lines

- Discussion on technical issues

- IEC materials:

  - Emergency shelter – tarps and tents

  - Build back safer – timber houses

  - Awareness on safe and unsafe masonry houses

  - Demolition/clean up kits

- Discussion on structural assessments

- Discussion on risks of families moving back and repairing damaged houses which are not safe to be repaired – agreed there was a need to raise awareness on this.

- Day rates for carpenters are already going up – needs to be monitored.

- Agreed to call a TWG on technical standards/IEC materials for Wed 30th Oct

- Review of shelter strategy

- Strategy was emailed on 28th Oct to all cluster partners for review, comment, feedback.

- A strategic advisor group has been convened to meet on Thur 31 Oct to review the strategy.

- Agencies who have agreed to be represented on the SAG are: CRS, WVI, UNDP, IOM, IFRC-PRCS, JICA, Rep of local NGO’s/groups – to be identified.

- Inter-cluster:

- Early recovery - UNDP

  - Advocating for strategic approach to demolition, rubble removal, etc

  - Advocating for cash for work activities

  - Local municipal engineers will start to look at structural survey of private houses when they have finished public buildings/assets.

  - ILO-  advocating for hard hats and boots and protective gear

- WASH – UNICEF

  - Identifying relocation sites for WASH facilities.

  - Important that all relocations and bunkhouses are adequately covered by WASH facilities.

  - Want to work with shelter cluster partners to support WASH at household level

  - Many household latrines where damaged. But they are very basic soakaway pits.

  - Interested to supporting latrine repair kits which could be part of any shelter repair kits.

  - Currently developing the WASH cluster strategy.

- CCCM

  - They have specialists coming to do some trainingsnext week (3rd/4th Nov).

  - DSWD camp managers  focal person to link with DSWD.

  - The DTM -  displacement tracking matrix is running. They are looking at new developments on using sms for immediate assessment/real time information.

- REACH assessment

- The detailed shelter and inter sector assessment is underway.

- REACH have trained 30 enumerators who are now in the field.

- Plan to be complete by the end of next week

- Resource mobilization

- Flash appeal was launched for $46.8mto reach 344,300 people over a six-month period until April 2014

  - CERF was released for $1.4m to IOM for emergency shelter and CCCM.Activities:

  - CCCM support including DTM for existing Evacuation Centers and IDP sites in both public and privately-owned lots and open spaces;

  - Procurement, Warehousing and Distribution of Emergency Shelter including emergency shelter kits (ESK) through sub-contracts to INGOs.

  - Humanitarian communications including Social Preparation and Mobilization (SPM) on thematic issues and interactive community mapping

- Shelter Cluster Update- meetings

- TWIG @9.00am at 29th October crab house  -  ER-TWIG

- SAG – Thursday  30th6.00pm at Crab House

### Next meeting time and location :

Tuesday the 5thNovember @1.00pm in JJs