## 1- ALL CHARTs
MARABUT, SAMAR (WESTERN SAMAR) - HSWG Partner Reporting
Recovery Shelter Activities (as of 06-OCT-2014)
The graphs shown below represent the sum of households who have received (HH reached) or who will receive (HH targeted or underway) recovery shelter support by HSWG partner agencies. Numbers reached are those reported to the HSWG by 6th October 2014. Household number do not represent the total needs by Barangay - for this, consult with relevant Barangay or Municipality. PLEASE NOTE - scale differs in each graph.
For explanation of intervention types, please see Shelter Cluster Recovery guidelines: https://www.sheltercluster.org/Asia/Philippines/Typhoon%20Haiyan%202013/Documents/Recovery%20Shelter%20Guidelines.pdf
The full data set of HSWG data can be found here: https://www.sheltercluster.org/Asia/Philippines/Typhoon%20Haiyan%202013/Documents/20141003%20HSWG%20Database%20for%20website.xlsb

## 2- AGENCIES
MARABUT - HSWG Partner reporting
Recovery Shelter activities (as of 06-OCT-2014)
Interventions By AGENCIES
The data shown below represent the sum of households who have received (HH reached) or who will receive (HH targeted or underway) recovery shelter support by HSWG partner agencies. Numbers reached are those reported to the HSWG by 6th October 2014. The full data set of HSWG data can be found here: https://www.sheltercluster.org/Asia/Philippines/Typhoon%20Haiyan%202013/Documents/20141003%20HSWG%20Database%20for%20website.xlsb
Municipality | MARABUT
Column Labels
| Temporary Shelter |  | Repairs & Retrofit |  | Core House |  | Permanent House |  | Total HH Reached | Total HH Targeted
Agency | HH Reached | HH Targeted | HH Reached | HH Targeted | HH Reached | HH Targeted | HH Reached | HH Targeted
CECI-CONCERN INC. |  |  | 319 | 319 |  |  |  |  | 319 | 319
Food for the Hungry Philippines |  |  | 463 | 1737 |  |  |  |  | 463 | 1737
NCCP-ACT ALLIANCE |  |  |  |  | 0 | 146 |  |  | 0 | 146
Plan International |  |  | 2797 | 2797 |  |  |  |  | 2797 | 2797
PRC - ICRC |  |  |  |  | 277 | 558 |  |  | 277 | 558
PRC - Spanish Red Cross |  |  | 96 | 257 | 271 | 517 |  |  | 367 | 774
Tdh Lausanne | 0 | 104 | 0 | 394 |  |  |  |  | 0 | 498
Grand Total | 0 | 104 | 3675 | 5504 | 548 | 1221 |  |  | 4223 | 6829

## 3- BARANGAYS
MARABUT - HSWG Partner reporting
Recovery Shelter activities (as of 06-OCT-2014)
Interventions By BARANGAYS
The data shown below represent the sum of households who have received (HH reached) or who will receive (HH targeted or underway) recovery shelter support by HSWG partner agencies. Numbers reached are those reported to the HSWG by 6th October 2014. The full data set of HSWG data can be found here: https://www.sheltercluster.org/Asia/Philippines/Typhoon%20Haiyan%202013/Documents/20141003%20HSWG%20Database%20for%20website.xlsb
Municipality | MARABUT
Column Labels
| Temporary Shelter |  | Repairs & Retrofit |  | Core House |  | Permanent House |  | Total HH Reached | Total HH Target
Barangay | HH Reached | HH Target | HH Reached | HH Target | HH Reached | HH Target | HH Reached | HH Target
AMAMBUCALE | 0 | 13 | 162 | 167 |  |  |  |  | 162 | 180
AMANTILLO |  |  | 131 | 131 |  |  |  |  | 131 | 131
Binukyahan |  |  | 117 | 215 | 44 | 50 |  |  | 161 | 265
CALUWAYAN |  |  | 205 | 205 | 58 | 123 |  |  | 263 | 328
CANYOYO |  |  | 224 | 328 |  |  |  |  | 224 | 328
Catato Pob. (Dist. I) |  |  | 31 | 31 | 19 | 19 |  |  | 50 | 50
FERRERAS | 0 | 8 | 91 | 236 | 0 | 100 |  |  | 91 | 344
LEGASPI |  |  | 331 | 368 | 41 | 108 |  |  | 372 | 476
LIPATA |  |  | 145 | 145 |  |  |  |  | 145 | 145
LOGERO |  |  | 166 | 253 | 52 | 52 |  |  | 218 | 305
MABUHAY | 0 | 21 | 180 | 498 | 5 | 53 |  |  | 185 | 572
MALOBAGO |  |  | 56 | 56 |  |  |  |  | 56 | 56
ODOC |  |  | 37 | 84 | 10 | 56 |  |  | 47 | 140
OSMEÑA | 0 | 30 | 266 | 574 |  |  |  |  | 266 | 604
PANAN-AWAN | 0 | 9 | 171 | 327 | 53 | 90 |  |  | 224 | 426
Pinalanga |  |  | 203 | 390 | 59 | 83 |  |  | 262 | 473
Pinamitinan (Pob.) |  |  | 244 | 252 | 0 | 19 |  |  | 244 | 271
ROÑO | 0 | 19 | 179 | 183 | 16 | 16 |  |  | 195 | 218
SAN ROQUE | 0 | 4 | 105 | 218 | 38 | 104 |  |  | 143 | 326
SANTA RITA |  |  | 160 | 227 | 31 | 31 |  |  | 191 | 258
Santo Niño Pob. (Dist. II) |  |  | 74 | 74 | 17 | 20 |  |  | 91 | 94
Tagalag |  |  |  |  | 8 | 65 |  |  | 8 | 65
TINABANAN |  |  | 186 | 274 | 48 | 160 |  |  | 234 | 434
VELOSO |  |  | 197 | 254 | 49 | 72 |  |  | 246 | 326
(blank) |  |  | 14 | 14 |  |  |  |  | 14 | 14
Grand Total | 0 | 104 | 3675 | 5504 | 548 | 1221 |  |  | 4223 | 6829

## 4- BRNGY AGENCIES
MARABUT - HSWG Partner reporting
Recovery Shelter activities (as of 06-OCT-2014)
Interventions By BARANGAYS & AGENCIES
The data shown below represent the sum of households who have received (HH reached) or who will receive (HH targeted or underway) recovery shelter support by HSWG partner agencies. Numbers reached are those reported to the HSWG by 6th October 2014. The full data set of HSWG data can be found here: https://www.sheltercluster.org/Asia/Philippines/Typhoon%20Haiyan%202013/Documents/20141003%20HSWG%20Database%20for%20website.xlsb
Municipality | MARABUT
| Temporary Shelter |  | Repairs & Retrofit |  | Core House |  | Permanent House |  | Total HH Reached | Total HH Target
Barangays & Agency | HH Reached | HH Target | HH Reached | HH Target | HH Reached | HH Target | HH Reached | HH Target
AMAMBUCALE | 0 | 13 | 162 | 167 |  |  |  |  | 162 | 180
Plan International |  |  | 162 | 162 |  |  |  |  | 162 | 162
Tdh Lausanne | 0 | 13 | 0 | 5 |  |  |  |  | 0 | 18
AMANTILLO |  |  | 131 | 131 |  |  |  |  | 131 | 131
Plan International |  |  | 131 | 131 |  |  |  |  | 131 | 131
Binukyahan |  |  | 117 | 215 | 44 | 50 |  |  | 161 | 265
Food for the Hungry Philippines |  |  | 47 | 145 |  |  |  |  | 47 | 145
Plan International |  |  | 44 | 44 |  |  |  |  | 44 | 44
PRC - Spanish Red Cross |  |  | 26 | 26 | 44 | 50 |  |  | 70 | 76
CALUWAYAN |  |  | 205 | 205 | 58 | 123 |  |  | 263 | 328
CECI-CONCERN INC. |  |  | 113 | 113 |  |  |  |  | 113 | 113
Plan International |  |  | 84 | 84 |  |  |  |  | 84 | 84
PRC - Spanish Red Cross |  |  | 8 | 8 | 58 | 123 |  |  | 66 | 131
CANYOYO |  |  | 224 | 328 |  |  |  |  | 224 | 328
Food for the Hungry Philippines |  |  | 33 | 137 |  |  |  |  | 33 | 137
Plan International |  |  | 191 | 191 |  |  |  |  | 191 | 191
Catato Pob. (Dist. I) |  |  | 31 | 31 | 19 | 19 |  |  | 50 | 50
Plan International |  |  | 31 | 31 |  |  |  |  | 31 | 31
PRC - ICRC |  |  |  |  | 19 | 19 |  |  | 19 | 19
FERRERAS | 0 | 8 | 91 | 236 | 0 | 100 |  |  | 91 | 344
Food for the Hungry Philippines |  |  | 15 | 120 |  |  |  |  | 15 | 120
NCCP-ACT ALLIANCE |  |  |  |  | 0 | 100 |  |  | 0 | 100
Plan International |  |  | 76 | 76 |  |  |  |  | 76 | 76
Tdh Lausanne | 0 | 8 | 0 | 40 |  |  |  |  | 0 | 48
LEGASPI |  |  | 331 | 368 | 41 | 108 |  |  | 372 | 476
CECI-CONCERN INC. |  |  | 110 | 110 |  |  |  |  | 110 | 110
Plan International |  |  | 159 | 159 |  |  |  |  | 159 | 159
PRC - Spanish Red Cross |  |  | 62 | 65 | 41 | 108 |  |  | 103 | 173
Tdh Lausanne |  |  | 0 | 34 |  |  |  |  | 0 | 34
LIPATA |  |  | 145 | 145 |  |  |  |  | 145 | 145
Plan International |  |  | 145 | 145 |  |  |  |  | 145 | 145
LOGERO |  |  | 166 | 253 | 52 | 52 |  |  | 218 | 305
Food for the Hungry Philippines |  |  | 37 | 124 |  |  |  |  | 37 | 124
Plan International |  |  | 129 | 129 |  |  |  |  | 129 | 129
PRC - ICRC |  |  |  |  | 52 | 52 |  |  | 52 | 52
MABUHAY | 0 | 21 | 180 | 498 | 5 | 53 |  |  | 185 | 572
Food for the Hungry Philippines |  |  | 87 | 296 |  |  |  |  | 87 | 296
Plan International |  |  | 93 | 93 |  |  |  |  | 93 | 93
PRC - ICRC |  |  |  |  | 5 | 53 |  |  | 5 | 53
Tdh Lausanne | 0 | 21 | 0 | 109 |  |  |  |  | 0 | 130
MALOBAGO |  |  | 56 | 56 |  |  |  |  | 56 | 56
Plan International |  |  | 56 | 56 |  |  |  |  | 56 | 56
ODOC |  |  | 37 | 84 | 10 | 56 |  |  | 47 | 140
Food for the Hungry Philippines |  |  | 18 | 64 |  |  |  |  | 18 | 64
NCCP-ACT ALLIANCE |  |  |  |  | 0 | 46 |  |  | 0 | 46
Plan International |  |  | 19 | 19 |  |  |  |  | 19 | 19
PRC - Spanish Red Cross |  |  | 0 | 1 | 10 | 10 |  |  | 10 | 11
OSMEÑA | 0 | 30 | 266 | 574 |  |  |  |  | 266 | 604
Food for the Hungry Philippines |  |  | 71 | 359 |  |  |  |  | 71 | 359
Plan International |  |  | 195 | 195 |  |  |  |  | 195 | 195
Tdh Lausanne | 0 | 30 | 0 | 20 |  |  |  |  | 0 | 50
PANAN-AWAN | 0 | 9 | 171 | 327 | 53 | 90 |  |  | 224 | 426
Food for the Hungry Philippines |  |  | 65 | 215 |  |  |  |  | 65 | 215
Plan International |  |  | 106 | 106 |  |  |  |  | 106 | 106
PRC - ICRC |  |  |  |  | 53 | 90 |  |  | 53 | 90
Tdh Lausanne | 0 | 9 | 0 | 6 |  |  |  |  | 0 | 15
Pinalanga |  |  | 203 | 390 | 59 | 83 |  |  | 262 | 473
Food for the Hungry Philippines |  |  | 76 | 263 |  |  |  |  | 76 | 263
Plan International |  |  | 127 | 127 |  |  |  |  | 127 | 127
PRC - ICRC |  |  |  |  | 59 | 83 |  |  | 59 | 83
Pinamitinan (Pob.) |  |  | 244 | 252 | 0 | 19 |  |  | 244 | 271
Plan International |  |  | 244 | 244 |  |  |  |  | 244 | 244
PRC - Spanish Red Cross |  |  | 0 | 8 | 0 | 19 |  |  | 0 | 27
ROÑO | 0 | 19 | 179 | 183 | 16 | 16 |  |  | 195 | 218
Plan International |  |  | 179 | 179 |  |  |  |  | 179 | 179
PRC - ICRC |  |  |  |  | 16 | 16 |  |  | 16 | 16
Tdh Lausanne | 0 | 19 | 0 | 4 |  |  |  |  | 0 | 23
SAN ROQUE | 0 | 4 | 105 | 218 | 38 | 104 |  |  | 143 | 326
Plan International |  |  | 105 | 105 |  |  |  |  | 105 | 105
PRC - Spanish Red Cross |  |  | 0 | 64 | 38 | 104 |  |  | 38 | 168
Tdh Lausanne | 0 | 4 | 0 | 49 |  |  |  |  | 0 | 53
SANTA RITA |  |  | 160 | 227 | 31 | 31 |  |  | 191 | 258
Plan International |  |  | 160 | 160 |  |  |  |  | 160 | 160
PRC - Spanish Red Cross |  |  | 0 | 67 | 31 | 31 |  |  | 31 | 98
Santo Niño Pob. (Dist. II) |  |  | 74 | 74 | 17 | 20 |  |  | 91 | 94
Plan International |  |  | 74 | 74 |  |  |  |  | 74 | 74
PRC - ICRC |  |  |  |  | 17 | 20 |  |  | 17 | 20
Tagalag |  |  |  |  | 8 | 65 |  |  | 8 | 65
PRC - ICRC |  |  |  |  | 8 | 65 |  |  | 8 | 65
TINABANAN |  |  | 186 | 274 | 48 | 160 |  |  | 234 | 434
Plan International |  |  | 186 | 186 |  |  |  |  | 186 | 186
PRC - ICRC |  |  |  |  | 48 | 160 |  |  | 48 | 160
Tdh Lausanne |  |  | 0 | 88 |  |  |  |  | 0 | 88
VELOSO |  |  | 197 | 254 | 49 | 72 |  |  | 246 | 326
CECI-CONCERN INC. |  |  | 96 | 96 |  |  |  |  | 96 | 96
Plan International |  |  | 101 | 101 |  |  |  |  | 101 | 101
PRC - Spanish Red Cross |  |  | 0 | 18 | 49 | 72 |  |  | 49 | 90
Tdh Lausanne |  |  | 0 | 39 |  |  |  |  | 0 | 39
(blank) |  |  | 14 | 14 |  |  |  |  | 14 | 14
Food for the Hungry Philippines |  |  | 14 | 14 |  |  |  |  | 14 | 14
Grand Total | 0 | 104 | 3675 | 5504 | 548 | 1221 |  |  | 4223 | 6829

## PIVOTS (hidden)
Region | REGION VIII (EASTERN VISAYAS) |  | Region | REGION VIII (EASTERN VISAYAS) |  |  | Region | REGION VIII (EASTERN VISAYAS) |  | Region | REGION VIII (EASTERN VISAYAS) |  | Region | REGION VIII (EASTERN VISAYAS)
Province | SAMAR (WESTERN SAMAR) | 24 | Province | SAMAR (WESTERN SAMAR) |  |  | Province | SAMAR (WESTERN SAMAR) |  | Province | SAMAR (WESTERN SAMAR) |  | Province | SAMAR (WESTERN SAMAR)
Municipality | MARABUT |  | Municipality | MARABUT |  | 3246 | Municipality | MARABUT |  | Municipality | MARABUT |  | Municipality | MARABUT
InterventionType | 2. Temporary Shelter |  | InterventionType | 6. Repairs & Retrofit |  |  | InterventionType | 6. Repairs & Retrofit |  | InterventionType | 7. Core House |  | InterventionType | 8. Permanent House
SubCategory | (All) | 0 | SubCategory | (Multiple Items) |  |  | SubCategory | (Multiple Items) |  | SubCategory | (All) |  | SubCategory | (All)
Agency | HH Reached | HH Targeted or underway | Agency | HH Reached | HH Targeted or underway |  | Agency | HH Reached | HH Targeted or underway | Agency | HH Reached | HH Targeted or underway | Agency | HH Reached | HH Targeted or underway
AMAMBUCALE | 0 | 13 | AMAMBUCALE | 162 | 5 |  | AMAMBUCALE |  | 0 | AMAMBUCALE |  | 0 | AMAMBUCALE |  | 0
AMANTILLO |  | 0 | AMANTILLO | 131 | 0 |  | AMANTILLO |  | 0 | AMANTILLO |  | 0 | AMANTILLO |  | 0
Binukyahan |  | 0 | Binukyahan | 91 | 98 |  | Binukyahan | 26 | 0 | Binukyahan | 44 | 6 | Binukyahan |  | 0
CALUWAYAN |  | 0 | CALUWAYAN | 84 | 0 |  | CALUWAYAN | 121 | 0 | CALUWAYAN | 58 | 65 | CALUWAYAN |  | 0
CANYOYO |  | 0 | CANYOYO | 224 | 104 |  | CANYOYO |  | 0 | CANYOYO |  | 0 | CANYOYO |  | 0
Catato Pob. (Dist. I) |  | 0 | Catato Pob. (Dist. I) | 31 | 0 |  | Catato Pob. (Dist. I) |  | 0 | Catato Pob. (Dist. I) | 19 | 0 | Catato Pob. (Dist. I) |  | 0
FERRERAS | 0 | 8 | FERRERAS | 91 | 145 |  | FERRERAS |  | 0 | FERRERAS | 0 | 100 | FERRERAS |  | 0
LEGASPI |  | 0 | LEGASPI | 159 | 34 |  | LEGASPI | 172 | 3 | LEGASPI | 41 | 67 | LEGASPI |  | 0
LIPATA |  | 0 | LIPATA | 145 | 0 |  | LIPATA |  | 0 | LIPATA |  | 0 | LIPATA |  | 0
LOGERO |  | 0 | LOGERO | 166 | 87 |  | LOGERO |  | 0 | LOGERO | 52 | 0 | LOGERO |  | 0
MABUHAY | 0 | 21 | MABUHAY | 180 | 318 |  | MABUHAY |  | 0 | MABUHAY | 5 | 48 | MABUHAY |  | 0
MALOBAGO |  | 0 | MALOBAGO | 56 | 0 |  | MALOBAGO |  | 0 | MALOBAGO |  | 0 | MALOBAGO |  | 0
ODOC |  | 0 | ODOC | 37 | 46 |  | ODOC | 0 | 1 | ODOC | 10 | 46 | ODOC |  | 0
OSMEÑA | 0 | 30 | OSMEÑA | 266 | 308 |  | OSMEÑA |  | 0 | OSMEÑA |  | 0 | OSMEÑA |  | 0
PANAN-AWAN | 0 | 9 | PANAN-AWAN | 171 | 156 |  | PANAN-AWAN |  | 0 | PANAN-AWAN | 53 | 37 | PANAN-AWAN |  | 0
Pinalanga |  | 0 | Pinalanga | 203 | 187 |  | Pinalanga |  | 0 | Pinalanga | 59 | 24 | Pinalanga |  | 0
Pinamitinan (Pob.) |  | 0 | Pinamitinan (Pob.) | 244 | 0 |  | Pinamitinan (Pob.) | 0 | 8 | Pinamitinan (Pob.) | 0 | 19 | Pinamitinan (Pob.) |  | 0
ROÑO | 0 | 19 | ROÑO | 179 | 4 |  | ROÑO |  | 0 | ROÑO | 16 | 0 | ROÑO |  | 0
SAN ROQUE | 0 | 4 | SAN ROQUE | 105 | 49 |  | SAN ROQUE | 0 | 64 | SAN ROQUE | 38 | 66 | SAN ROQUE |  | 0
SANTA RITA |  | 0 | SANTA RITA | 160 | 0 |  | SANTA RITA | 0 | 67 | SANTA RITA | 31 | 0 | SANTA RITA |  | 0
Santo Niño Pob. (Dist. II) |  | 0 | Santo Niño Pob. (Dist. II) | 74 | 0 |  | Santo Niño Pob. (Dist. II) |  | 0 | Santo Niño Pob. (Dist. II) | 17 | 3 | Santo Niño Pob. (Dist. II) |  | 0
Tagalag |  | 0 | Tagalag |  | 0 |  | Tagalag |  | 0 | Tagalag | 8 | 57 | Tagalag |  | 0
TINABANAN |  | 0 | TINABANAN | 186 | 88 |  | TINABANAN |  | 0 | TINABANAN | 48 | 112 | TINABANAN |  | 0
VELOSO |  | 0 | VELOSO | 101 | 39 |  | VELOSO | 96 | 18 | VELOSO | 49 | 23 | VELOSO |  | 0
Grand Total | 0 | 104 | Grand Total | 3246 | 1668 |  | Grand Total | 415 | 161 | Grand Total | 548 | 673 | Grand Total |  | 0

## Activities (hidden)
ImplementingAgency | OtherAgencies | Program_ID | Region | Province | Municipality | Barangay | RelocRisk | Status | StartDate | EndDate | ProgType | InterventionType | SubCategory | HH_target | HH_reached | Partnership | WASHAccess | Comments | Region_CODE | Province_CODE | Municipality_CODE | Barangay_CODE | AgencyNameForTable
CECI-CONCERN INC. |  |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | CALUWAYAN |  | Completed distributions | 2014-05-26 | 2014-07-05 | Recovery | 6. Repairs & Retrofit | Minor repairs | 113 | 113 | No | No latrine required | Minor repair ( P15,000 ) | 080000000 | 086000000 | 086010000 | 086010002 | CECI-CONCERN INC.
CECI-CONCERN INC. |  |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | LEGASPI |  | Completed distributions | 2014-08-11 | 2014-09-07 | Recovery | 6. Repairs & Retrofit | Minor repairs | 110 | 110 | No | No latrine required | Minor repair ( P15,000 ) | 080000000 | 086000000 | 086010000 | 086010005 | CECI-CONCERN INC.
CECI-CONCERN INC. |  |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | VELOSO |  | Completed distributions | 2014-07-07 | 2014-08-16 | Recovery | 6. Repairs & Retrofit | Minor repairs | 96 | 96 | No | No latrine required | Minor repair ( P15,000 ) | 080000000 | 086000000 | 086010000 | 086010024 | CECI-CONCERN INC.
Food for the Hungry Philippines |  |  | Region VIII (Eastern Visayas) | SAMAR (WESTERN SAMAR) | MARABUT | Binukyahan |  | Ongoing distributions | 2014-05-23 | 2014-09-30 | Recovery | 6. Repairs & Retrofit | Shelter kit | 145 | 47 | Yes | Need WASH partner | Identified Partially Damaged and Totally Damaged and also living in tents, : we received GIK vinyl sheets and marine grade rope; we distributed them along with accompanying nails, umbrella nails, tie wire and information on how to safely secure the vinyl, usage of this kits for improving their current houses. | 080000000 | 086000000 | 086010000 | 086010016 | Food for the Hungry Philippines
Food for the Hungry Philippines |  |  | Region VIII (Eastern Visayas) | SAMAR (WESTERN SAMAR) | MARABUT | CANYOYO |  | Ongoing distributions | 2014-05-23 | 2014-09-30 | Recovery | 6. Repairs & Retrofit | Shelter kit | 137 | 33 | Yes | Need WASH partner | Identified Partially Damaged and Totally Damaged and also living in tents, : we received GIK vinyl sheets and marine grade rope; we distributed them along with accompanying nails, umbrella nails, tie wire and information on how to safely secure the vinyl, usage of this kits for improving their current houses. | 080000000 | 086000000 | 086010000 | 086010003 | Food for the Hungry Philippines
Food for the Hungry Philippines |  |  | Region VIII (Eastern Visayas) | SAMAR (WESTERN SAMAR) | MARABUT | FERRERAS |  | Ongoing distributions | 2014-05-23 | 2014-09-30 | Recovery | 6. Repairs & Retrofit | Shelter kit | 120 | 15 | Yes | Need WASH partner | Identified Partially Damaged and Totally Damaged and also living in tents, : we received GIK vinyl sheets and marine grade rope; we distributed them along with accompanying nails, umbrella nails, tie wire and information on how to safely secure the vinyl, usage of this kits for improving their current houses. | 080000000 | 086000000 | 086010000 | 086010004 | Food for the Hungry Philippines
Food for the Hungry Philippines |  |  | Region VIII (Eastern Visayas) | SAMAR (WESTERN SAMAR) | MARABUT | LOGERO |  | Ongoing distributions | 2014-05-23 | 2014-09-30 | Recovery | 6. Repairs & Retrofit | Shelter kit | 124 | 37 | Yes | Need WASH partner | Identified Partially Damaged and Totally Damaged and also living in tents, : we received GIK vinyl sheets and marine grade rope; we distributed them along with accompanying nails, umbrella nails, tie wire and information on how to safely secure the vinyl, usage of this kits for improving their current houses. | 080000000 | 086000000 | 086010000 | 086010006 | Food for the Hungry Philippines
Food for the Hungry Philippines |  |  | Region VIII (Eastern Visayas) | SAMAR (WESTERN SAMAR) | MARABUT | MABUHAY |  | Ongoing distributions | 2014-05-23 | 2014-09-30 | Recovery | 6. Repairs & Retrofit | Shelter kit | 256 | 47 | Yes | Need WASH partner | Identified Partially Damaged and Totally Damaged and also living in tents, : we received GIK vinyl sheets and marine grade rope; we distributed them along with accompanying nails, umbrella nails, tie wire and information on how to safely secure the vinyl, usage of this kits for improving their current houses. | 080000000 | 086000000 | 086010000 | 086010018 | Food for the Hungry Philippines
Food for the Hungry Philippines |  |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | MABUHAY |  | Planned (funded) | 2014-08-15 | 2015-03-30 | Recovery | 6. Repairs & Retrofit | Shelter kit | 40 | 40 | Yes | Need WASH partner | To distribute shelter kit materials for repair and improve structure resilience houses for future hazard its either in Major or Minor repair and accompanying DRR messages (BBB) for safe shelter and address disaster preparedness will be provided. | 080000000 | 086000000 | 086010000 | 086010018 | Food for the Hungry Philippines
Food for the Hungry Philippines |  |  | Region VIII (Eastern Visayas) | SAMAR (WESTERN SAMAR) | MARABUT | ODOC |  | Ongoing distributions | 2014-05-23 | 2014-09-30 | Recovery | 6. Repairs & Retrofit | Shelter kit | 64 | 18 | Yes | Need WASH partner | Identified Partially Damaged and Totally Damaged and also living in tents, : we received GIK vinyl sheets and marine grade rope; we distributed them along with accompanying nails, umbrella nails, tie wire and information on how to safely secure the vinyl, usage of this kits for improving their current houses. | 080000000 | 086000000 | 086010000 | 086010020 | Food for the Hungry Philippines
Food for the Hungry Philippines |  |  | Region VIII (Eastern Visayas) | SAMAR (WESTERN SAMAR) | MARABUT | OSMEÑA |  | Ongoing distributions | 2014-05-23 | 2014-09-30 | Recovery | 6. Repairs & Retrofit | Shelter kit | 309 | 21 | Yes | Need WASH partner | Identified Partially Damaged and Totally Damaged and also living in tents, : we received GIK vinyl sheets and marine grade rope; we distributed them along with accompanying nails, umbrella nails, tie wire and information on how to safely secure the vinyl, usage of this kits for improving their current houses. | 080000000 | 086000000 | 086010000 | 086010007 | Food for the Hungry Philippines
Food for the Hungry Philippines |  |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | OSMEÑA |  | Planned (funded) | 2014-08-15 | 2015-03-30 | Recovery | 6. Repairs & Retrofit | Shelter kit | 50 | 50 | Yes | Need WASH partner | To distribute shelter kit materials for repair and improve structure resilience houses for future hazard its either in Major or Minor identified repair. Prioritize these the vulnerable HH, Disabled, Female HH and accompanying with DRR messages (BBB) for safe shelter and address disaster preparedness will be provided. | 080000000 | 086000000 | 086010000 | 086010007 | Food for the Hungry Philippines
Food for the Hungry Philippines |  |  | Region VIII (Eastern Visayas) | SAMAR (WESTERN SAMAR) | MARABUT | PANAN-AWAN |  | Ongoing distributions | 2014-05-23 | 2014-09-30 | Recovery | 6. Repairs & Retrofit | Shelter kit | 165 | 15 | Yes | Need WASH partner | Identified Partially Damaged and Totally Damaged and also living in tents, : we received GIK vinyl sheets and marine grade rope; we distributed them along with accompanying nails, umbrella nails, tie wire and information on how to safely secure the vinyl, usage of this kits for improving their current houses. | 080000000 | 086000000 | 086010000 | 086010021 | Food for the Hungry Philippines
Food for the Hungry Philippines |  |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | PANAN-AWAN |  | Planned (funded) | 2014-08-15 | 2015-03-30 | Recovery | 6. Repairs & Retrofit | Shelter kit | 50 | 50 | Yes | Need WASH partner | To distribute shelter kit materials for repair and improve structure resilience houses for future hazard its either in Major or Minor repair and accompanying DRR messages (BBB) for safe shelter and address disaster preparedness will be provided. | 080000000 | 086000000 | 086010000 | 086010021 | Food for the Hungry Philippines
Food for the Hungry Philippines |  |  | Region VIII (Eastern Visayas) | SAMAR (WESTERN SAMAR) | MARABUT | Pinalanga |  | Ongoing distributions | 2014-05-23 | 2014-09-30 | Recovery | 6. Repairs & Retrofit | Shelter kit | 233 | 46 | Yes | Need WASH partner | Identified Partially Damaged and Totally Damaged and also living in tents, : we received GIK vinyl sheets and marine grade rope; we distributed them along with accompanying nails, umbrella nails, tie wire and information on how to safely secure the vinyl, usage of this kits for improving their current houses. | 080000000 | 086000000 | 086010000 | 086010008 | Food for the Hungry Philippines
Food for the Hungry Philippines |  |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | Pinalanga |  | Planned (funded) | 2014-08-15 | 2015-03-30 | Recovery | 6. Repairs & Retrofit | Shelter kit | 30 | 30 | Yes | Need WASH partner | To distribute shelter kit materials for repair and improve structure resilience houses for future hazard its either in Major or Minor repair and accompanying DRR messages(BBB) for safe shelter and address disaster preparedness will be provided. | 080000000 | 086000000 | 086010000 | 086010008 | Food for the Hungry Philippines
Food for the Hungry Philippines |  |  | Region VIII (Eastern Visayas) | SAMAR (WESTERN SAMAR) | MARABUT |  |  | Planned (funded) | 2014-05-23 | 2014-09-30 | Recovery | 6. Repairs & Retrofit | Shelter kit | 14 | 14 | Yes | Need WASH partner | Identified Partially Damaged and Totally Damaged and also living in tents, : we received GIK vinyl sheets and marine grade rope; we distributed them along with accompanying nails, umbrella nails, tie wire and information on how to safely secure the vinyl | 080000000 | 086000000 | 086010000 |  | Food for the Hungry Philippines
NCCP-ACT ALLIANCE |  |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | FERRERAS |  | In pipeline (procurement/onroute) | 2014-06-01 | 2014-10-31 | Recovery | 7. Core House | Not on original site (Resettlement project) | 100 | 0 | No | Provision of new/repaired HH latrines | Land/site development subject to negotiations with LGU/NHA | 080000000 | 086000000 | 086010000 | 086010004 | NCCP-ACT ALLIANCE
NCCP-ACT ALLIANCE |  |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | ODOC |  | In pipeline (procurement/onroute) | 2014-06-01 | 2014-10-31 | Recovery | 7. Core House | Not on original site (Resettlement project) | 46 | 0 | No | Provision of new/repaired HH latrines | Land/site development subject to negotiations with LGU/NHA | 080000000 | 086000000 | 086010000 | 086010020 | NCCP-ACT ALLIANCE
Plan International |  |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | AMAMBUCALE |  | Completed distributions |  | 2014-03-13 | Recovery | 6. Repairs & Retrofit | Shelter kit | 83 | 83 |  |  | CGI sheets, ground mat, rope, coco lumber | 080000000 | 086000000 | 086010000 | 086010001 | Plan International
Plan International |  |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | AMAMBUCALE |  | Completed distributions | 2014-09-15 | 2014-10-07 | Recovery | 6. Repairs & Retrofit | Shelter kit | 79 | 79 |  |  | (* 2nd Round of Distribution*) Shelter kit is composed of 12 pcs CGI sheets, 2 kgs tie wires, 3 CGI ridge roll caps, 2 plain GI sheets, 8 pcs coco lumber, vulca seal roof sealant, 3 kgs galvanized umbrella nails, CW nails and 30 m nylon ropes | 080000000 | 086000000 | 086010000 | 086010001 | Plan International
Plan International |  |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | AMANTILLO |  | Completed distributions |  | 2014-03-13 | Recovery | 6. Repairs & Retrofit | Shelter kit | 54 | 54 |  |  | CGI sheets, ground mat, rope, coco lumber | 080000000 | 086000000 | 086010000 | 086010015 | Plan International
Plan International |  |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | AMANTILLO |  | Completed distributions | 2014-09-15 | 2014-09-16 | Recovery | 6. Repairs & Retrofit | Shelter kit | 77 | 77 |  |  | (* 2nd Round of Distribution*) Shelter kit is composed of 12 pcs CGI sheets, 2 kgs tie wires, 3 CGI ridge roll caps, 2 plain GI sheets, 8 pcs coco lumber, vulca seal roof sealant, 3 kgs galvanized umbrella nails, CW nails and 30 m nylon ropes | 080000000 | 086000000 | 086010000 | 086010015 | Plan International
Plan International |  |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | Binukyahan |  | Completed distributions |  | 2014-03-13 | Recovery | 6. Repairs & Retrofit | Shelter kit | 44 | 44 |  |  | CGI sheets, ground mat, rope, coco lumber | 080000000 | 086000000 | 086010000 | 086010016 | Plan International
Plan International |  |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | CALUWAYAN |  | Completed distributions |  | 2014-03-13 | Recovery | 6. Repairs & Retrofit | Shelter kit | 84 | 84 |  |  | CGI sheets, ground mat, rope, coco lumber | 080000000 | 086000000 | 086010000 | 086010002 | Plan International
Plan International |  |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | CANYOYO |  | Completed distributions |  | 2014-03-13 | Recovery | 6. Repairs & Retrofit | Shelter kit | 86 | 86 |  |  | CGI sheets, ground mat, rope, coco lumber | 080000000 | 086000000 | 086010000 | 086010003 | Plan International
Plan International |  |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | CANYOYO |  | Completed distributions | 2014-09-15 | 2014-09-18 | Recovery | 6. Repairs & Retrofit | Shelter kit | 105 | 105 |  |  | (* 2nd Round of Distribution*) Shelter kit is composed of 12 pcs CGI sheets, 2 kgs tie wires, 3 CGI ridge roll caps, 2 plain GI sheets, 8 pcs coco lumber, vulca seal roof sealant, 3 kgs galvanized umbrella nails, CW nails and 30 m nylon ropes | 080000000 | 086000000 | 086010000 | 086010003 | Plan International
Plan International |  |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | Catato Pob. (Dist. I) |  | Completed distributions |  | 2014-03-13 | Recovery | 6. Repairs & Retrofit | Shelter kit | 21 | 21 |  |  | CGI sheets, ground mat, rope, coco lumber | 080000000 | 086000000 | 086010000 | 086010010 | Plan International
Plan International |  |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | Catato Pob. (Dist. I) |  | Completed distributions | 2014-09-15 | 2014-09-16 | Recovery | 6. Repairs & Retrofit | Shelter kit | 10 | 10 |  |  | (* 2nd Round of Distribution*) Shelter kit is composed of 12 pcs CGI sheets, 2 kgs tie wires, 3 CGI ridge roll caps, 2 plain GI sheets, 8 pcs coco lumber, vulca seal roof sealant, 3 kgs galvanized umbrella nails, CW nails and 30 m nylon ropes | 080000000 | 086000000 | 086010000 | 086010010 | Plan International
Plan International |  |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | FERRERAS |  | Completed distributions |  | 2014-03-13 | Recovery | 6. Repairs & Retrofit | Shelter kit | 76 | 76 |  |  | CGI sheets, ground mat, rope, coco lumber | 080000000 | 086000000 | 086010000 | 086010004 | Plan International
Plan International |  |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | LEGASPI |  | Completed distributions |  | 2014-03-13 | Recovery | 6. Repairs & Retrofit | Shelter kit | 159 | 159 |  |  | CGI sheets, ground mat, rope, coco lumber | 080000000 | 086000000 | 086010000 | 086010005 | Plan International
Plan International |  |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | LIPATA |  | Completed distributions |  | 2014-03-13 | Recovery | 6. Repairs & Retrofit | Shelter kit | 107 | 107 |  |  | CGI sheets, ground mat, rope, coco lumber | 080000000 | 086000000 | 086010000 | 086010017 | Plan International
Plan International |  |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | LIPATA |  | Completed distributions | 2014-09-15 | 2014-09-16 | Recovery | 6. Repairs & Retrofit | Shelter kit | 38 | 38 |  |  | (* 2nd Round of Distribution*) Shelter kit is composed of 12 pcs CGI sheets, 2 kgs tie wires, 3 CGI ridge roll caps, 2 plain GI sheets, 8 pcs coco lumber, vulca seal roof sealant, 3 kgs galvanized umbrella nails, CW nails and 30 m nylon ropes | 080000000 | 086000000 | 086010000 | 086010017 | Plan International
Plan International |  |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | LOGERO |  | Completed distributions |  | 2014-03-13 | Recovery | 6. Repairs & Retrofit | Shelter kit | 70 | 70 |  |  | CGI sheets, ground mat, rope, coco lumber | 080000000 | 086000000 | 086010000 | 086010006 | Plan International
Plan International |  |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | LOGERO |  | Completed distributions | 2014-09-15 | 2014-09-24 | Recovery | 6. Repairs & Retrofit | Shelter kit | 31 | 31 |  |  | (* 2nd Round of Distribution*) Shelter kit is composed of 12 pcs CGI sheets, 2 kgs tie wires, 3 CGI ridge roll caps, 2 plain GI sheets, 8 pcs coco lumber, vulca seal roof sealant, 3 kgs galvanized umbrella nails, CW nails and 30 m nylon ropes | 080000000 | 086000000 | 086010000 | 086010006 | Plan International
Plan International |  |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | LOGERO |  | Completed distributions | 2014-09-15 | 2014-09-29 | Recovery | 6. Repairs & Retrofit | Shelter kit | 28 | 28 |  |  | (* 2nd Round of Distribution*) Shelter kit is composed of 12 pcs CGI sheets, 2 kgs tie wires, 3 CGI ridge roll caps, 2 plain GI sheets, 8 pcs coco lumber, vulca seal roof sealant, 3 kgs galvanized umbrella nails, CW nails and 30 m nylon ropes | 080000000 | 086000000 | 086010000 | 086010006 | Plan International
Plan International |  |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | MABUHAY |  | Completed distributions |  | 2014-03-13 | Recovery | 6. Repairs & Retrofit | Shelter kit | 93 | 93 |  |  | CGI sheets, ground mat, rope, coco lumber | 080000000 | 086000000 | 086010000 | 086010018 | Plan International
Plan International |  |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | MALOBAGO |  | Completed distributions |  | 2014-03-13 | Recovery | 6. Repairs & Retrofit | Shelter kit | 56 | 56 |  |  | CGI sheets, ground mat, rope, coco lumber | 080000000 | 086000000 | 086010000 | 086010019 | Plan International
Plan International |  |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | ODOC |  | Completed distributions |  | 2014-03-13 | Recovery | 6. Repairs & Retrofit | Shelter kit | 19 | 19 |  |  | CGI sheets, ground mat, rope, coco lumber | 080000000 | 086000000 | 086010000 | 086010020 | Plan International
Plan International |  |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | OSMEÑA |  | Completed distributions |  | 2014-03-13 | Recovery | 6. Repairs & Retrofit | Shelter kit | 95 | 95 |  |  | CGI sheets, ground mat, rope, coco lumber | 080000000 | 086000000 | 086010000 | 086010007 | Plan International
Plan International |  |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | OSMEÑA |  | Completed distributions | 2014-09-15 | 2014-09-29 | Recovery | 6. Repairs & Retrofit | Shelter kit | 67 | 67 |  |  | (* 2nd Round of Distribution*) Shelter kit is composed of 12 pcs CGI sheets, 2 kgs tie wires, 3 CGI ridge roll caps, 2 plain GI sheets, 8 pcs coco lumber, vulca seal roof sealant, 3 kgs galvanized umbrella nails, CW nails and 30 m nylon ropes | 080000000 | 086000000 | 086010000 | 086010007 | Plan International
Plan International |  |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | OSMEÑA |  | Completed distributions | 2014-09-15 | 2014-09-29 | Recovery | 6. Repairs & Retrofit | Shelter kit | 33 | 33 |  |  | (* 2nd Round of Distribution*) Shelter kit is composed of 12 pcs CGI sheets, 2 kgs tie wires, 3 CGI ridge roll caps, 2 plain GI sheets, 8 pcs coco lumber, vulca seal roof sealant, 3 kgs galvanized umbrella nails, CW nails and 30 m nylon ropes | 080000000 | 086000000 | 086010000 | 086010007 | Plan International
Plan International |  |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | PANAN-AWAN |  | Completed distributions |  | 2014-03-13 | Recovery | 6. Repairs & Retrofit | Shelter kit | 92 | 92 |  |  | CGI sheets, ground mat, rope, coco lumber | 080000000 | 086000000 | 086010000 | 086010021 | Plan International
Plan International |  |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | PANAN-AWAN |  | Completed distributions | 2014-09-15 | 2014-09-29 | Recovery | 6. Repairs & Retrofit | Shelter kit | 14 | 14 |  |  | (* 2nd Round of Distribution*) Shelter kit is composed of 12 pcs CGI sheets, 2 kgs tie wires, 3 CGI ridge roll caps, 2 plain GI sheets, 8 pcs coco lumber, vulca seal roof sealant, 3 kgs galvanized umbrella nails, CW nails and 30 m nylon ropes | 080000000 | 086000000 | 086010000 | 086010021 | Plan International
Plan International |  |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | Pinalanga |  | Completed distributions |  | 2014-03-13 | Recovery | 6. Repairs & Retrofit | Shelter kit | 127 | 127 |  |  | CGI sheets, ground mat, rope, coco lumber | 080000000 | 086000000 | 086010000 | 086010008 | Plan International
Plan International |  |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | Pinamitinan (Pob.) |  | Completed distributions |  | 2014-03-13 | Recovery | 6. Repairs & Retrofit | Shelter kit | 128 | 128 |  |  | CGI sheets, ground mat, rope, coco lumber | 080000000 | 086000000 | 086010000 | 086010009 | Plan International
Plan International |  |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | Pinamitinan (Pob.) |  | Completed distributions | 2014-09-15 | 2014-09-30 | Recovery | 6. Repairs & Retrofit | Shelter kit | 98 | 98 |  |  | (* 2nd Round of Distribution*) Shelter kit is composed of 12 pcs CGI sheets, 2 kgs tie wires, 3 CGI ridge roll caps, 2 plain GI sheets, 8 pcs coco lumber, vulca seal roof sealant, 3 kgs galvanized umbrella nails, CW nails and 30 m nylon ropes | 080000000 | 086000000 | 086010000 | 086010009 | Plan International
Plan International |  |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | Pinamitinan (Pob.) |  | Completed distributions | 2014-09-15 | 2014-09-30 | Recovery | 6. Repairs & Retrofit | Shelter kit | 18 | 18 |  |  | (* 2nd Round of Distribution*) Shelter kit is composed of 12 pcs CGI sheets, 2 kgs tie wires, 3 CGI ridge roll caps, 2 plain GI sheets, 8 pcs coco lumber, vulca seal roof sealant, 3 kgs galvanized umbrella nails, CW nails and 30 m nylon ropes | 080000000 | 086000000 | 086010000 | 086010009 | Plan International
Plan International |  |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | ROÑO |  | Completed distributions |  | 2014-03-13 | Recovery | 6. Repairs & Retrofit | Shelter kit | 102 | 102 |  |  | CGI sheets, ground mat, rope, coco lumber | 080000000 | 086000000 | 086010000 | 086010022 | Plan International
Plan International |  |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | ROÑO |  | Completed distributions | 2014-09-15 | 2014-09-24 | Recovery | 6. Repairs & Retrofit | Shelter kit | 56 | 56 |  |  | (* 2nd Round of Distribution*) Shelter kit is composed of 12 pcs CGI sheets, 2 kgs tie wires, 3 CGI ridge roll caps, 2 plain GI sheets, 8 pcs coco lumber, vulca seal roof sealant, 3 kgs galvanized umbrella nails, CW nails and 30 m nylon ropes | 080000000 | 086000000 | 086010000 | 086010022 | Plan International
Plan International |  |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | ROÑO |  | Completed distributions | 2014-09-15 | 2014-09-24 | Recovery | 6. Repairs & Retrofit | Shelter kit | 21 | 21 |  |  | (* 2nd Round of Distribution*) Shelter kit is composed of 12 pcs CGI sheets, 2 kgs tie wires, 3 CGI ridge roll caps, 2 plain GI sheets, 8 pcs coco lumber, vulca seal roof sealant, 3 kgs galvanized umbrella nails, CW nails and 30 m nylon ropes | 080000000 | 086000000 | 086010000 | 086010022 | Plan International
Plan International |  |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | SAN ROQUE |  | Completed distributions |  | 2014-03-13 | Recovery | 6. Repairs & Retrofit | Shelter kit | 105 | 105 |  |  | CGI sheets, ground mat, rope, coco lumber | 080000000 | 086000000 | 086010000 | 086010011 | Plan International
Plan International |  |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | SANTA RITA |  | Completed distributions |  | 2014-03-13 | Recovery | 6. Repairs & Retrofit | Shelter kit | 128 | 128 |  |  | CGI sheets, ground mat, rope, coco lumber | 080000000 | 086000000 | 086010000 | 086010023 | Plan International
Plan International |  |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | SANTA RITA |  | Completed distributions | 2014-09-15 | 2014-09-30 | Recovery | 6. Repairs & Retrofit | Shelter kit | 26 | 26 |  |  | (* 2nd Round of Distribution*) Shelter kit is composed of 12 pcs CGI sheets, 2 kgs tie wires, 3 CGI ridge roll caps, 2 plain GI sheets, 8 pcs coco lumber, vulca seal roof sealant, 3 kgs galvanized umbrella nails, CW nails and 30 m nylon ropes | 080000000 | 086000000 | 086010000 | 086010023 | Plan International
Plan International |  |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | SANTA RITA |  | Completed distributions | 2014-09-15 | 2014-09-30 | Recovery | 6. Repairs & Retrofit | Shelter kit | 6 | 6 |  |  | (* 2nd Round of Distribution*) Shelter kit is composed of 12 pcs CGI sheets, 2 kgs tie wires, 3 CGI ridge roll caps, 2 plain GI sheets, 8 pcs coco lumber, vulca seal roof sealant, 3 kgs galvanized umbrella nails, CW nails and 30 m nylon ropes | 080000000 | 086000000 | 086010000 | 086010023 | Plan International
Plan International |  |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | Santo Niño Pob. (Dist. II) |  | Completed distributions |  | 2014-03-13 | Recovery | 6. Repairs & Retrofit | Shelter kit | 59 | 59 |  |  | CGI sheets, ground mat, rope, coco lumber | 080000000 | 086000000 | 086010000 | 086010012 | Plan International
Plan International |  |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | Santo Niño Pob. (Dist. II) |  | Completed distributions | 2014-09-15 | 2014-09-16 | Recovery | 6. Repairs & Retrofit | Shelter kit | 15 | 15 |  |  | (* 2nd Round of Distribution*) Shelter kit is composed of 12 pcs CGI sheets, 2 kgs tie wires, 3 CGI ridge roll caps, 2 plain GI sheets, 8 pcs coco lumber, vulca seal roof sealant, 3 kgs galvanized umbrella nails, CW nails and 30 m nylon ropes | 080000000 | 086000000 | 086010000 | 086010012 | Plan International
Plan International |  |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | TINABANAN |  | Completed distributions |  | 2014-03-13 | Recovery | 6. Repairs & Retrofit | Shelter kit | 186 | 186 |  |  | CGI sheets, ground mat, rope, coco lumber | 080000000 | 086000000 | 086010000 | 086010014 | Plan International
Plan International |  |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | VELOSO |  | Completed distributions |  | 2014-03-13 | Recovery | 6. Repairs & Retrofit | Shelter kit | 101 | 101 |  |  | CGI sheets, ground mat, rope, coco lumber | 080000000 | 086000000 | 086010000 | 086010024 | Plan International
PRC | Spanish Red Cross |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | Binukyahan |  | Completed distributions |  |  | Recovery | 6. Repairs & Retrofit | Minor repairs | 26 | 26 |  |  |  | 080000000 | 086000000 | 086010000 | 086010016 | PRC - Spanish Red Cross
PRC | Spanish Red Cross |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | Binukyahan |  | Ongoing distributions |  |  | Recovery | 7. Core House | On original site | 50 | 44 |  |  |  | 080000000 | 086000000 | 086010000 | 086010016 | PRC - Spanish Red Cross
PRC | Spanish Red Cross |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | CALUWAYAN |  | Completed distributions |  |  | Recovery | 6. Repairs & Retrofit | Minor repairs | 8 | 8 |  |  |  | 080000000 | 086000000 | 086010000 | 086010002 | PRC - Spanish Red Cross
PRC | Spanish Red Cross |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | CALUWAYAN |  | Ongoing distributions |  |  | Recovery | 7. Core House | On original site | 123 | 58 |  |  |  | 080000000 | 086000000 | 086010000 | 086010002 | PRC - Spanish Red Cross
PRC | ICRC |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | Catato Pob. (Dist. I) |  | Ongoing distributions |  |  | Recovery | 7. Core House |  | 19 | 19 |  | Provision of new/repaired HH latrines |  | 080000000 | 086000000 | 086010000 | 086010010 | PRC - ICRC
PRC | Spanish Red Cross |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | LEGASPI |  | Ongoing distributions |  |  | Recovery | 6. Repairs & Retrofit | Minor repairs | 65 | 62 |  |  |  | 080000000 | 086000000 | 086010000 | 086010005 | PRC - Spanish Red Cross
PRC | Spanish Red Cross |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | LEGASPI |  | Ongoing distributions |  |  | Recovery | 7. Core House | On original site | 108 | 41 |  |  |  | 080000000 | 086000000 | 086010000 | 086010005 | PRC - Spanish Red Cross
PRC | ICRC |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | Logero |  | Ongoing distributions |  |  | Recovery | 7. Core House |  | 52 | 52 |  | Provision of new/repaired HH latrines |  | 080000000 | 086000000 | 086010000 | 086010006 | PRC - ICRC
PRC | ICRC |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | Mabuhay |  | In pipeline (procurement/onroute) |  |  | Recovery | 7. Core House |  | 53 | 5 |  | Provision of new/repaired HH latrines |  | 080000000 | 086000000 | 086010000 | 086010018 | PRC - ICRC
PRC | Spanish Red Cross |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | ODOC |  | In pipeline (procurement/onroute) |  |  | Recovery | 6. Repairs & Retrofit | Minor repairs | 1 | 0 |  |  |  | 080000000 | 086000000 | 086010000 | 086010020 | PRC - Spanish Red Cross
PRC | Spanish Red Cross |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | ODOC |  | Ongoing distributions |  |  | Recovery | 7. Core House | On original site | 10 | 10 |  |  |  | 080000000 | 086000000 | 086010000 | 086010020 | PRC - Spanish Red Cross
PRC | ICRC |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | Panan-awan |  | Ongoing distributions |  |  | Recovery | 7. Core House |  | 90 | 53 |  | Provision of new/repaired HH latrines |  | 080000000 | 086000000 | 086010000 | 086010021 | PRC - ICRC
PRC | ICRC |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | Pinalanga |  | Ongoing distributions |  |  | Recovery | 7. Core House |  | 83 | 59 |  | Provision of new/repaired HH latrines |  | 080000000 | 086000000 | 086010000 | 086010008 | PRC - ICRC
PRC | Spanish Red Cross |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | Pinamitinan (Pob.) |  | In pipeline (procurement/onroute) |  |  | Recovery | 6. Repairs & Retrofit | Minor repairs | 8 | 0 |  |  |  | 080000000 | 086000000 | 086010000 | 086010009 | PRC - Spanish Red Cross
PRC | Spanish Red Cross |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | Pinamitinan (Pob.) |  | In pipeline (procurement/onroute) |  |  | Recovery | 7. Core House | On original site | 19 | 0 |  |  |  | 080000000 | 086000000 | 086010000 | 086010009 | PRC - Spanish Red Cross
PRC | ICRC |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | Roño |  | Ongoing distributions |  |  | Recovery | 7. Core House |  | 16 | 16 |  | Provision of new/repaired HH latrines |  | 080000000 | 086000000 | 086010000 | 086010022 | PRC - ICRC
PRC | Spanish Red Cross |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | SAN ROQUE |  | In pipeline (procurement/onroute) |  |  | Recovery | 6. Repairs & Retrofit | Minor repairs | 64 | 0 |  |  |  | 080000000 | 086000000 | 086010000 | 086010011 | PRC - Spanish Red Cross
PRC | Spanish Red Cross |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | SAN ROQUE |  | Ongoing distributions |  |  | Recovery | 7. Core House | On original site | 104 | 38 |  |  |  | 080000000 | 086000000 | 086010000 | 086010011 | PRC - Spanish Red Cross
PRC | Spanish Red Cross |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | SANTA RITA |  | In pipeline (procurement/onroute) |  |  | Recovery | 6. Repairs & Retrofit | Minor repairs | 67 | 0 |  |  |  | 080000000 | 086000000 | 086010000 | 086010023 | PRC - Spanish Red Cross
PRC | Spanish Red Cross |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | SANTA RITA |  | Ongoing distributions |  |  | Recovery | 7. Core House | On original site | 31 | 31 |  |  |  | 080000000 | 086000000 | 086010000 | 086010023 | PRC - Spanish Red Cross
PRC | ICRC |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | Santo Niño Pob. (Dist. II) |  | Ongoing distributions |  |  | Recovery | 7. Core House |  | 20 | 17 |  | Provision of new/repaired HH latrines |  | 080000000 | 086000000 | 086010000 | 086010012 | PRC - ICRC
PRC | ICRC |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | Tagalag |  | In pipeline (procurement/onroute) |  |  | Recovery | 7. Core House |  | 65 | 8 |  | Provision of new/repaired HH latrines |  | 080000000 | 086000000 | 086010000 | 086010013 | PRC - ICRC
PRC | ICRC |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | Tinabanan |  | In pipeline (procurement/onroute) |  |  | Recovery | 7. Core House |  | 65 | 13 |  | Provision of new/repaired HH latrines |  | 080000000 | 086000000 | 086010000 | 086010014 | PRC - ICRC
PRC | ICRC |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | Tinabanan |  | Ongoing distributions |  |  | Recovery | 7. Core House |  | 95 | 35 |  | Provision of new/repaired HH latrines |  | 080000000 | 086000000 | 086010000 | 086010014 | PRC - ICRC
PRC | Spanish Red Cross |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | VELOSO |  | In pipeline (procurement/onroute) |  |  | Recovery | 6. Repairs & Retrofit | Minor repairs | 18 | 0 |  |  |  | 080000000 | 086000000 | 086010000 | 086010024 | PRC - Spanish Red Cross
PRC | Spanish Red Cross |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | VELOSO |  | Ongoing distributions |  |  | Recovery | 7. Core House | On original site | 72 | 49 |  |  |  | 080000000 | 086000000 | 086010000 | 086010024 | PRC - Spanish Red Cross
Tdh Lausanne |  |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | Amambucale |  | In pipeline (procurement/onroute) | 2014-04-01 | 2015-07-15 | Recovery | 2. Temporary Shelter | On original site | 13 | 0 | No | WASH partner needed | Phase 2 project | 080000000 | 086000000 | 086010000 | 086010001 | Tdh Lausanne
Tdh Lausanne |  |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | Amambucale |  | In pipeline (procurement/onroute) | 2014-04-01 | 2015-07-15 | Recovery | 6. Repairs & Retrofit | On original site | 5 | 0 | No | WASH partner needed | Phase 2 project | 080000000 | 086000000 | 086010000 | 086010001 | Tdh Lausanne
Tdh Lausanne |  |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | Ferreras |  | In pipeline (procurement/onroute) | 2014-04-01 | 2015-07-15 | Recovery | 2. Temporary Shelter | On original site | 8 | 0 | No | WASH partner needed | Phase 2 project | 080000000 | 086000000 | 086010000 | 086010004 | Tdh Lausanne
Tdh Lausanne |  |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | Ferreras |  | In pipeline (procurement/onroute) | 2014-04-01 | 2015-07-15 | Recovery | 6. Repairs & Retrofit | On original site | 40 | 0 | No | WASH partner needed | Phase 2 project | 080000000 | 086000000 | 086010000 | 086010004 | Tdh Lausanne
Tdh Lausanne |  |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | Legaspi |  | In pipeline (procurement/onroute) | 2014-04-01 | 2015-07-15 | Recovery | 6. Repairs & Retrofit | On original site | 34 | 0 | No | WASH partner needed | Phase 2 project | 080000000 | 086000000 | 086010000 | 086010005 | Tdh Lausanne
Tdh Lausanne |  |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | Mabuhay |  | In pipeline (procurement/onroute) | 2014-04-01 | 2015-07-15 | Recovery | 2. Temporary Shelter | On original site | 21 | 0 | No | WASH partner needed | Phase 2 project | 080000000 | 086000000 | 086010000 | 086010018 | Tdh Lausanne
Tdh Lausanne |  |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | Mabuhay |  | In pipeline (procurement/onroute) | 2014-04-01 | 2015-07-15 | Recovery | 6. Repairs & Retrofit | On original site | 109 | 0 | No | WASH partner needed | Phase 2 project | 080000000 | 086000000 | 086010000 | 086010018 | Tdh Lausanne
Tdh Lausanne |  |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | OSMEÑA |  | In pipeline (procurement/onroute) | 2014-04-01 | 2015-07-15 | Recovery | 2. Temporary Shelter | On original site | 30 | 0 | No | WASH partner needed | Phase 2 project | 080000000 | 086000000 | 086010000 | 086010007 | Tdh Lausanne
Tdh Lausanne |  |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | OSMEÑA |  | In pipeline (procurement/onroute) | 2014-04-01 | 2015-07-15 | Recovery | 6. Repairs & Retrofit | On original site | 20 | 0 | No | WASH partner needed | Phase 2 project | 080000000 | 086000000 | 086010000 | 086010007 | Tdh Lausanne
Tdh Lausanne |  |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | Panan-awan |  | In pipeline (procurement/onroute) | 2014-04-01 | 2015-07-15 | Recovery | 2. Temporary Shelter | On original site | 9 | 0 | No | WASH partner needed | Phase 2 project | 080000000 | 086000000 | 086010000 | 086010021 | Tdh Lausanne
Tdh Lausanne |  |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | Panan-awan |  | In pipeline (procurement/onroute) | 2014-04-01 | 2015-07-15 | Recovery | 6. Repairs & Retrofit | On original site | 6 | 0 | No | WASH partner needed | Phase 2 project | 080000000 | 086000000 | 086010000 | 086010021 | Tdh Lausanne
Tdh Lausanne |  |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | ROÑO |  | In pipeline (procurement/onroute) | 2014-04-01 | 2015-07-15 | Recovery | 2. Temporary Shelter | On original site | 19 | 0 | No | WASH partner needed | Phase 2 project | 080000000 | 086000000 | 086010000 | 086010022 | Tdh Lausanne
Tdh Lausanne |  |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | ROÑO |  | In pipeline (procurement/onroute) | 2014-04-01 | 2015-07-15 | Recovery | 6. Repairs & Retrofit | On original site | 4 | 0 | No | WASH partner needed | Phase 2 project | 080000000 | 086000000 | 086010000 | 086010022 | Tdh Lausanne
Tdh Lausanne |  |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | San roque |  | In pipeline (procurement/onroute) | 2014-04-01 | 2015-07-15 | Recovery | 2. Temporary Shelter | On original site | 4 | 0 | No | WASH partner needed | Phase 2 project | 080000000 | 086000000 | 086010000 | 086010011 | Tdh Lausanne
Tdh Lausanne |  |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | San roque |  | In pipeline (procurement/onroute) | 2014-04-01 | 2015-07-15 | Recovery | 6. Repairs & Retrofit | On original site | 49 | 0 | No | WASH partner needed | Phase 2 project | 080000000 | 086000000 | 086010000 | 086010011 | Tdh Lausanne
Tdh Lausanne |  |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | Tinabanan |  | In pipeline (procurement/onroute) | 2014-04-01 | 2015-07-15 | Recovery | 6. Repairs & Retrofit | On original site | 88 | 0 | No | WASH partner needed | Phase 2 project | 080000000 | 086000000 | 086010000 | 086010014 | Tdh Lausanne
Tdh Lausanne |  |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | Veloso |  | In pipeline (procurement/onroute) | 2014-04-01 | 2015-07-15 | Recovery | 6. Repairs & Retrofit | On original site | 39 | 0 | No | WASH partner needed | Phase 2 project | 080000000 | 086000000 | 086010000 | 086010024 | Tdh Lausanne
|  |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | AMAMBUCALE |  |  |  |  | Recovery | 2. Temporary Shelter | [5 empty] | <<BLANK LOCATION RECORD>> | 080000000 | 086000000 | 086010000 | 086010001
|  |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | AMAMBUCALE |  |  |  |  | Recovery | 6. Repairs & Retrofit | Cash |  |  |  |  | <<BLANK LOCATION RECORD>> | 080000000 | 086000000 | 086010000 | 086010001
|  |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | AMAMBUCALE |  |  |  |  | Recovery | 6. Repairs & Retrofit | Major repairs |  |  |  |  | <<BLANK LOCATION RECORD>> | 080000000 | 086000000 | 086010000 | 086010001
|  |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | AMAMBUCALE |  |  |  |  | Recovery | 7. Core House | [5 empty] | <<BLANK LOCATION RECORD>> | 080000000 | 086000000 | 086010000 | 086010001
|  |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | AMAMBUCALE |  |  |  |  | Recovery | 8. Permanent House | [5 empty] | <<BLANK LOCATION RECORD>> | 080000000 | 086000000 | 086010000 | 086010001
|  |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | AMANTILLO |  |  |  |  | Recovery | 2. Temporary Shelter | [5 empty] | <<BLANK LOCATION RECORD>> | 080000000 | 086000000 | 086010000 | 086010015
|  |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | AMANTILLO |  |  |  |  | Recovery | 6. Repairs & Retrofit | Cash |  |  |  |  | <<BLANK LOCATION RECORD>> | 080000000 | 086000000 | 086010000 | 086010015
|  |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | AMANTILLO |  |  |  |  | Recovery | 6. Repairs & Retrofit | Major repairs |  |  |  |  | <<BLANK LOCATION RECORD>> | 080000000 | 086000000 | 086010000 | 086010015
|  |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | AMANTILLO |  |  |  |  | Recovery | 7. Core House | [5 empty] | <<BLANK LOCATION RECORD>> | 080000000 | 086000000 | 086010000 | 086010015
|  |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | AMANTILLO |  |  |  |  | Recovery | 8. Permanent House | [5 empty] | <<BLANK LOCATION RECORD>> | 080000000 | 086000000 | 086010000 | 086010015
|  |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | BINUKYAHAN |  |  |  |  | Recovery | 2. Temporary Shelter | [5 empty] | <<BLANK LOCATION RECORD>> | 080000000 | 086000000 | 086010000 | 086010016
|  |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | BINUKYAHAN |  |  |  |  | Recovery | 6. Repairs & Retrofit | Cash |  |  |  |  | <<BLANK LOCATION RECORD>> | 080000000 | 086000000 | 086010000 | 086010016
|  |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | BINUKYAHAN |  |  |  |  | Recovery | 6. Repairs & Retrofit | Major repairs |  |  |  |  | <<BLANK LOCATION RECORD>> | 080000000 | 086000000 | 086010000 | 086010016
|  |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | BINUKYAHAN |  |  |  |  | Recovery | 7. Core House | [5 empty] | <<BLANK LOCATION RECORD>> | 080000000 | 086000000 | 086010000 | 086010016
|  |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | BINUKYAHAN |  |  |  |  | Recovery | 8. Permanent House | [5 empty] | <<BLANK LOCATION RECORD>> | 080000000 | 086000000 | 086010000 | 086010016
|  |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | CALUWAYAN |  |  |  |  | Recovery | 2. Temporary Shelter | [5 empty] | <<BLANK LOCATION RECORD>> | 080000000 | 086000000 | 086010000 | 086010002
|  |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | CALUWAYAN |  |  |  |  | Recovery | 6. Repairs & Retrofit | Cash |  |  |  |  | <<BLANK LOCATION RECORD>> | 080000000 | 086000000 | 086010000 | 086010002
|  |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | CALUWAYAN |  |  |  |  | Recovery | 6. Repairs & Retrofit | Major repairs |  |  |  |  | <<BLANK LOCATION RECORD>> | 080000000 | 086000000 | 086010000 | 086010002
|  |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | CALUWAYAN |  |  |  |  | Recovery | 7. Core House | [5 empty] | <<BLANK LOCATION RECORD>> | 080000000 | 086000000 | 086010000 | 086010002
|  |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | CALUWAYAN |  |  |  |  | Recovery | 8. Permanent House | [5 empty] | <<BLANK LOCATION RECORD>> | 080000000 | 086000000 | 086010000 | 086010002
|  |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | CANYOYO |  |  |  |  | Recovery | 2. Temporary Shelter | [5 empty] | <<BLANK LOCATION RECORD>> | 080000000 | 086000000 | 086010000 | 086010003
|  |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | CANYOYO |  |  |  |  | Recovery | 6. Repairs & Retrofit | Cash |  |  |  |  | <<BLANK LOCATION RECORD>> | 080000000 | 086000000 | 086010000 | 086010003
|  |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | CANYOYO |  |  |  |  | Recovery | 6. Repairs & Retrofit | Major repairs |  |  |  |  | <<BLANK LOCATION RECORD>> | 080000000 | 086000000 | 086010000 | 086010003
|  |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | CANYOYO |  |  |  |  | Recovery | 7. Core House | [5 empty] | <<BLANK LOCATION RECORD>> | 080000000 | 086000000 | 086010000 | 086010003
|  |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | CANYOYO |  |  |  |  | Recovery | 8. Permanent House | [5 empty] | <<BLANK LOCATION RECORD>> | 080000000 | 086000000 | 086010000 | 086010003
|  |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | CATATO POB. (DIST. I) |  |  |  |  | Recovery | 2. Temporary Shelter | [5 empty] | <<BLANK LOCATION RECORD>> | 080000000 | 086000000 | 086010000 | 086010010
|  |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | CATATO POB. (DIST. I) |  |  |  |  | Recovery | 6. Repairs & Retrofit | Cash |  |  |  |  | <<BLANK LOCATION RECORD>> | 080000000 | 086000000 | 086010000 | 086010010
|  |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | CATATO POB. (DIST. I) |  |  |  |  | Recovery | 6. Repairs & Retrofit | Major repairs |  |  |  |  | <<BLANK LOCATION RECORD>> | 080000000 | 086000000 | 086010000 | 086010010
|  |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | CATATO POB. (DIST. I) |  |  |  |  | Recovery | 7. Core House | [5 empty] | <<BLANK LOCATION RECORD>> | 080000000 | 086000000 | 086010000 | 086010010
|  |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | CATATO POB. (DIST. I) |  |  |  |  | Recovery | 8. Permanent House | [5 empty] | <<BLANK LOCATION RECORD>> | 080000000 | 086000000 | 086010000 | 086010010
|  |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | FERRERAS |  |  |  |  | Recovery | 2. Temporary Shelter | [5 empty] | <<BLANK LOCATION RECORD>> | 080000000 | 086000000 | 086010000 | 086010004
|  |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | FERRERAS |  |  |  |  | Recovery | 6. Repairs & Retrofit | Cash |  |  |  |  | <<BLANK LOCATION RECORD>> | 080000000 | 086000000 | 086010000 | 086010004
|  |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | FERRERAS |  |  |  |  | Recovery | 6. Repairs & Retrofit | Major repairs |  |  |  |  | <<BLANK LOCATION RECORD>> | 080000000 | 086000000 | 086010000 | 086010004
|  |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | FERRERAS |  |  |  |  | Recovery | 7. Core House | [5 empty] | <<BLANK LOCATION RECORD>> | 080000000 | 086000000 | 086010000 | 086010004
|  |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | FERRERAS |  |  |  |  | Recovery | 8. Permanent House | [5 empty] | <<BLANK LOCATION RECORD>> | 080000000 | 086000000 | 086010000 | 086010004
|  |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | LEGASPI |  |  |  |  | Recovery | 2. Temporary Shelter | [5 empty] | <<BLANK LOCATION RECORD>> | 080000000 | 086000000 | 086010000 | 086010005
|  |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | LEGASPI |  |  |  |  | Recovery | 6. Repairs & Retrofit | Cash |  |  |  |  | <<BLANK LOCATION RECORD>> | 080000000 | 086000000 | 086010000 | 086010005
|  |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | LEGASPI |  |  |  |  | Recovery | 6. Repairs & Retrofit | Major repairs |  |  |  |  | <<BLANK LOCATION RECORD>> | 080000000 | 086000000 | 086010000 | 086010005
|  |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | LEGASPI |  |  |  |  | Recovery | 7. Core House | [5 empty] | <<BLANK LOCATION RECORD>> | 080000000 | 086000000 | 086010000 | 086010005
|  |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | LEGASPI |  |  |  |  | Recovery | 8. Permanent House | [5 empty] | <<BLANK LOCATION RECORD>> | 080000000 | 086000000 | 086010000 | 086010005
|  |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | LIPATA |  |  |  |  | Recovery | 2. Temporary Shelter | [5 empty] | <<BLANK LOCATION RECORD>> | 080000000 | 086000000 | 086010000 | 086010017
|  |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | LIPATA |  |  |  |  | Recovery | 6. Repairs & Retrofit | Cash |  |  |  |  | <<BLANK LOCATION RECORD>> | 080000000 | 086000000 | 086010000 | 086010017
|  |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | LIPATA |  |  |  |  | Recovery | 6. Repairs & Retrofit | Major repairs |  |  |  |  | <<BLANK LOCATION RECORD>> | 080000000 | 086000000 | 086010000 | 086010017
|  |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | LIPATA |  |  |  |  | Recovery | 7. Core House | [5 empty] | <<BLANK LOCATION RECORD>> | 080000000 | 086000000 | 086010000 | 086010017
|  |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | LIPATA |  |  |  |  | Recovery | 8. Permanent House | [5 empty] | <<BLANK LOCATION RECORD>> | 080000000 | 086000000 | 086010000 | 086010017
|  |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | LOGERO |  |  |  |  | Recovery | 2. Temporary Shelter | [5 empty] | <<BLANK LOCATION RECORD>> | 080000000 | 086000000 | 086010000 | 086010006
|  |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | LOGERO |  |  |  |  | Recovery | 6. Repairs & Retrofit | Cash |  |  |  |  | <<BLANK LOCATION RECORD>> | 080000000 | 086000000 | 086010000 | 086010006
|  |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | LOGERO |  |  |  |  | Recovery | 6. Repairs & Retrofit | Major repairs |  |  |  |  | <<BLANK LOCATION RECORD>> | 080000000 | 086000000 | 086010000 | 086010006
|  |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | LOGERO |  |  |  |  | Recovery | 7. Core House | [5 empty] | <<BLANK LOCATION RECORD>> | 080000000 | 086000000 | 086010000 | 086010006
|  |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | LOGERO |  |  |  |  | Recovery | 8. Permanent House | [5 empty] | <<BLANK LOCATION RECORD>> | 080000000 | 086000000 | 086010000 | 086010006
|  |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | MABUHAY |  |  |  |  | Recovery | 2. Temporary Shelter | [5 empty] | <<BLANK LOCATION RECORD>> | 080000000 | 086000000 | 086010000 | 086010018
|  |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | MABUHAY |  |  |  |  | Recovery | 6. Repairs & Retrofit | Cash |  |  |  |  | <<BLANK LOCATION RECORD>> | 080000000 | 086000000 | 086010000 | 086010018
|  |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | MABUHAY |  |  |  |  | Recovery | 6. Repairs & Retrofit | Major repairs |  |  |  |  | <<BLANK LOCATION RECORD>> | 080000000 | 086000000 | 086010000 | 086010018
|  |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | MABUHAY |  |  |  |  | Recovery | 7. Core House | [5 empty] | <<BLANK LOCATION RECORD>> | 080000000 | 086000000 | 086010000 | 086010018
|  |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | MABUHAY |  |  |  |  | Recovery | 8. Permanent House | [5 empty] | <<BLANK LOCATION RECORD>> | 080000000 | 086000000 | 086010000 | 086010018
|  |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | MALOBAGO |  |  |  |  | Recovery | 2. Temporary Shelter | [5 empty] | <<BLANK LOCATION RECORD>> | 080000000 | 086000000 | 086010000 | 086010019
|  |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | MALOBAGO |  |  |  |  | Recovery | 6. Repairs & Retrofit | Cash |  |  |  |  | <<BLANK LOCATION RECORD>> | 080000000 | 086000000 | 086010000 | 086010019
|  |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | MALOBAGO |  |  |  |  | Recovery | 6. Repairs & Retrofit | Major repairs |  |  |  |  | <<BLANK LOCATION RECORD>> | 080000000 | 086000000 | 086010000 | 086010019
|  |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | MALOBAGO |  |  |  |  | Recovery | 7. Core House | [5 empty] | <<BLANK LOCATION RECORD>> | 080000000 | 086000000 | 086010000 | 086010019
|  |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | MALOBAGO |  |  |  |  | Recovery | 8. Permanent House | [5 empty] | <<BLANK LOCATION RECORD>> | 080000000 | 086000000 | 086010000 | 086010019
|  |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | ODOC |  |  |  |  | Recovery | 2. Temporary Shelter | [5 empty] | <<BLANK LOCATION RECORD>> | 080000000 | 086000000 | 086010000 | 086010020
|  |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | ODOC |  |  |  |  | Recovery | 6. Repairs & Retrofit | Cash |  |  |  |  | <<BLANK LOCATION RECORD>> | 080000000 | 086000000 | 086010000 | 086010020
|  |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | ODOC |  |  |  |  | Recovery | 6. Repairs & Retrofit | Major repairs |  |  |  |  | <<BLANK LOCATION RECORD>> | 080000000 | 086000000 | 086010000 | 086010020
|  |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | ODOC |  |  |  |  | Recovery | 7. Core House | [5 empty] | <<BLANK LOCATION RECORD>> | 080000000 | 086000000 | 086010000 | 086010020
|  |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | ODOC |  |  |  |  | Recovery | 8. Permanent House | [5 empty] | <<BLANK LOCATION RECORD>> | 080000000 | 086000000 | 086010000 | 086010020
|  |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | OSMEÑA |  |  |  |  | Recovery | 2. Temporary Shelter | [5 empty] | <<BLANK LOCATION RECORD>> | 080000000 | 086000000 | 086010000 | 086010007
|  |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | OSMEÑA |  |  |  |  | Recovery | 6. Repairs & Retrofit | Cash |  |  |  |  | <<BLANK LOCATION RECORD>> | 080000000 | 086000000 | 086010000 | 086010007
|  |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | OSMEÑA |  |  |  |  | Recovery | 6. Repairs & Retrofit | Major repairs |  |  |  |  | <<BLANK LOCATION RECORD>> | 080000000 | 086000000 | 086010000 | 086010007
|  |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | OSMEÑA |  |  |  |  | Recovery | 7. Core House | [5 empty] | <<BLANK LOCATION RECORD>> | 080000000 | 086000000 | 086010000 | 086010007
|  |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | OSMEÑA |  |  |  |  | Recovery | 8. Permanent House | [5 empty] | <<BLANK LOCATION RECORD>> | 080000000 | 086000000 | 086010000 | 086010007
|  |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | PANAN-AWAN |  |  |  |  | Recovery | 2. Temporary Shelter | [5 empty] | <<BLANK LOCATION RECORD>> | 080000000 | 086000000 | 086010000 | 086010021
|  |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | PANAN-AWAN |  |  |  |  | Recovery | 6. Repairs & Retrofit | Cash |  |  |  |  | <<BLANK LOCATION RECORD>> | 080000000 | 086000000 | 086010000 | 086010021
|  |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | PANAN-AWAN |  |  |  |  | Recovery | 6. Repairs & Retrofit | Major repairs |  |  |  |  | <<BLANK LOCATION RECORD>> | 080000000 | 086000000 | 086010000 | 086010021
|  |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | PANAN-AWAN |  |  |  |  | Recovery | 7. Core House | [5 empty] | <<BLANK LOCATION RECORD>> | 080000000 | 086000000 | 086010000 | 086010021
|  |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | PANAN-AWAN |  |  |  |  | Recovery | 8. Permanent House | [5 empty] | <<BLANK LOCATION RECORD>> | 080000000 | 086000000 | 086010000 | 086010021
|  |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | PINALANGA |  |  |  |  | Recovery | 2. Temporary Shelter | [5 empty] | <<BLANK LOCATION RECORD>> | 080000000 | 086000000 | 086010000 | 086010008
|  |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | PINALANGA |  |  |  |  | Recovery | 6. Repairs & Retrofit | Cash |  |  |  |  | <<BLANK LOCATION RECORD>> | 080000000 | 086000000 | 086010000 | 086010008
|  |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | PINALANGA |  |  |  |  | Recovery | 6. Repairs & Retrofit | Major repairs |  |  |  |  | <<BLANK LOCATION RECORD>> | 080000000 | 086000000 | 086010000 | 086010008
|  |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | PINALANGA |  |  |  |  | Recovery | 7. Core House | [5 empty] | <<BLANK LOCATION RECORD>> | 080000000 | 086000000 | 086010000 | 086010008
|  |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | PINALANGA |  |  |  |  | Recovery | 8. Permanent House | [5 empty] | <<BLANK LOCATION RECORD>> | 080000000 | 086000000 | 086010000 | 086010008
|  |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | PINAMITINAN (POB.) |  |  |  |  | Recovery | 2. Temporary Shelter | [5 empty] | <<BLANK LOCATION RECORD>> | 080000000 | 086000000 | 086010000 | 086010009
|  |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | PINAMITINAN (POB.) |  |  |  |  | Recovery | 6. Repairs & Retrofit | Cash |  |  |  |  | <<BLANK LOCATION RECORD>> | 080000000 | 086000000 | 086010000 | 086010009
|  |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | PINAMITINAN (POB.) |  |  |  |  | Recovery | 6. Repairs & Retrofit | Major repairs |  |  |  |  | <<BLANK LOCATION RECORD>> | 080000000 | 086000000 | 086010000 | 086010009
|  |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | PINAMITINAN (POB.) |  |  |  |  | Recovery | 7. Core House | [5 empty] | <<BLANK LOCATION RECORD>> | 080000000 | 086000000 | 086010000 | 086010009
|  |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | PINAMITINAN (POB.) |  |  |  |  | Recovery | 8. Permanent House | [5 empty] | <<BLANK LOCATION RECORD>> | 080000000 | 086000000 | 086010000 | 086010009
|  |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | ROÑO |  |  |  |  | Recovery | 2. Temporary Shelter | [5 empty] | <<BLANK LOCATION RECORD>> | 080000000 | 086000000 | 086010000 | 086010022
|  |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | ROÑO |  |  |  |  | Recovery | 6. Repairs & Retrofit | Cash |  |  |  |  | <<BLANK LOCATION RECORD>> | 080000000 | 086000000 | 086010000 | 086010022
|  |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | ROÑO |  |  |  |  | Recovery | 6. Repairs & Retrofit | Major repairs |  |  |  |  | <<BLANK LOCATION RECORD>> | 080000000 | 086000000 | 086010000 | 086010022
|  |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | ROÑO |  |  |  |  | Recovery | 7. Core House | [5 empty] | <<BLANK LOCATION RECORD>> | 080000000 | 086000000 | 086010000 | 086010022
|  |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | ROÑO |  |  |  |  | Recovery | 8. Permanent House | [5 empty] | <<BLANK LOCATION RECORD>> | 080000000 | 086000000 | 086010000 | 086010022
|  |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | SAN ROQUE |  |  |  |  | Recovery | 2. Temporary Shelter | [5 empty] | <<BLANK LOCATION RECORD>> | 080000000 | 086000000 | 086010000 | 086010011
|  |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | SAN ROQUE |  |  |  |  | Recovery | 6. Repairs & Retrofit | Cash |  |  |  |  | <<BLANK LOCATION RECORD>> | 080000000 | 086000000 | 086010000 | 086010011
|  |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | SAN ROQUE |  |  |  |  | Recovery | 6. Repairs & Retrofit | Major repairs |  |  |  |  | <<BLANK LOCATION RECORD>> | 080000000 | 086000000 | 086010000 | 086010011
|  |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | SAN ROQUE |  |  |  |  | Recovery | 7. Core House | [5 empty] | <<BLANK LOCATION RECORD>> | 080000000 | 086000000 | 086010000 | 086010011
|  |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | SAN ROQUE |  |  |  |  | Recovery | 8. Permanent House | [5 empty] | <<BLANK LOCATION RECORD>> | 080000000 | 086000000 | 086010000 | 086010011
|  |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | SANTA RITA |  |  |  |  | Recovery | 2. Temporary Shelter | [5 empty] | <<BLANK LOCATION RECORD>> | 080000000 | 086000000 | 086010000 | 086010023
|  |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | SANTA RITA |  |  |  |  | Recovery | 6. Repairs & Retrofit | Cash |  |  |  |  | <<BLANK LOCATION RECORD>> | 080000000 | 086000000 | 086010000 | 086010023
|  |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | SANTA RITA |  |  |  |  | Recovery | 6. Repairs & Retrofit | Major repairs |  |  |  |  | <<BLANK LOCATION RECORD>> | 080000000 | 086000000 | 086010000 | 086010023
|  |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | SANTA RITA |  |  |  |  | Recovery | 7. Core House | [5 empty] | <<BLANK LOCATION RECORD>> | 080000000 | 086000000 | 086010000 | 086010023
|  |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | SANTA RITA |  |  |  |  | Recovery | 8. Permanent House | [5 empty] | <<BLANK LOCATION RECORD>> | 080000000 | 086000000 | 086010000 | 086010023
|  |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | SANTO NIÑO POB. (DIST. II) |  |  |  |  | Recovery | 2. Temporary Shelter | [5 empty] | <<BLANK LOCATION RECORD>> | 080000000 | 086000000 | 086010000 | 086010012
|  |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | SANTO NIÑO POB. (DIST. II) |  |  |  |  | Recovery | 6. Repairs & Retrofit | Cash |  |  |  |  | <<BLANK LOCATION RECORD>> | 080000000 | 086000000 | 086010000 | 086010012
|  |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | SANTO NIÑO POB. (DIST. II) |  |  |  |  | Recovery | 6. Repairs & Retrofit | Major repairs |  |  |  |  | <<BLANK LOCATION RECORD>> | 080000000 | 086000000 | 086010000 | 086010012
|  |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | SANTO NIÑO POB. (DIST. II) |  |  |  |  | Recovery | 7. Core House | [5 empty] | <<BLANK LOCATION RECORD>> | 080000000 | 086000000 | 086010000 | 086010012
|  |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | SANTO NIÑO POB. (DIST. II) |  |  |  |  | Recovery | 8. Permanent House | [5 empty] | <<BLANK LOCATION RECORD>> | 080000000 | 086000000 | 086010000 | 086010012
|  |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | TAGALAG |  |  |  |  | Recovery | 2. Temporary Shelter | [5 empty] | <<BLANK LOCATION RECORD>> | 080000000 | 086000000 | 086010000 | 086010013
|  |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | TAGALAG |  |  |  |  | Recovery | 6. Repairs & Retrofit | Cash |  |  |  |  | <<BLANK LOCATION RECORD>> | 080000000 | 086000000 | 086010000 | 086010013
|  |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | TAGALAG |  |  |  |  | Recovery | 6. Repairs & Retrofit | Major repairs |  |  |  |  | <<BLANK LOCATION RECORD>> | 080000000 | 086000000 | 086010000 | 086010013
|  |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | TAGALAG |  |  |  |  | Recovery | 7. Core House | [5 empty] | <<BLANK LOCATION RECORD>> | 080000000 | 086000000 | 086010000 | 086010013
|  |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | TAGALAG |  |  |  |  | Recovery | 8. Permanent House | [5 empty] | <<BLANK LOCATION RECORD>> | 080000000 | 086000000 | 086010000 | 086010013
|  |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | TINABANAN |  |  |  |  | Recovery | 2. Temporary Shelter | [5 empty] | <<BLANK LOCATION RECORD>> | 080000000 | 086000000 | 086010000 | 086010014
|  |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | TINABANAN |  |  |  |  | Recovery | 6. Repairs & Retrofit | Cash |  |  |  |  | <<BLANK LOCATION RECORD>> | 080000000 | 086000000 | 086010000 | 086010014
|  |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | TINABANAN |  |  |  |  | Recovery | 6. Repairs & Retrofit | Major repairs |  |  |  |  | <<BLANK LOCATION RECORD>> | 080000000 | 086000000 | 086010000 | 086010014
|  |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | TINABANAN |  |  |  |  | Recovery | 7. Core House | [5 empty] | <<BLANK LOCATION RECORD>> | 080000000 | 086000000 | 086010000 | 086010014
|  |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | TINABANAN |  |  |  |  | Recovery | 8. Permanent House | [5 empty] | <<BLANK LOCATION RECORD>> | 080000000 | 086000000 | 086010000 | 086010014
|  |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | VELOSO |  |  |  |  | Recovery | 2. Temporary Shelter | [5 empty] | <<BLANK LOCATION RECORD>> | 080000000 | 086000000 | 086010000 | 086010024
|  |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | VELOSO |  |  |  |  | Recovery | 6. Repairs & Retrofit | Cash |  |  |  |  | <<BLANK LOCATION RECORD>> | 080000000 | 086000000 | 086010000 | 086010024
|  |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | VELOSO |  |  |  |  | Recovery | 6. Repairs & Retrofit | Major repairs |  |  |  |  | <<BLANK LOCATION RECORD>> | 080000000 | 086000000 | 086010000 | 086010024
|  |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | VELOSO |  |  |  |  | Recovery | 7. Core House | [5 empty] | <<BLANK LOCATION RECORD>> | 080000000 | 086000000 | 086010000 | 086010024
|  |  | REGION VIII (EASTERN VISAYAS) | SAMAR (WESTERN SAMAR) | MARABUT | VELOSO |  |  |  |  | Recovery | 8. Permanent House | [5 empty] | <<BLANK LOCATION RECORD>> | 080000000 | 086000000 | 086010000 | 086010024

## Filters (hidden)
1 | 2 | 3
This shape represents a slicer. Slicers can be used in at least Excel 2010. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers can be used in at least Excel 2010. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers can be used in at least Excel 2010. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.