Shelter Cluster Accountability Working Group

Meeting minutes

Date: 24 September 2014

Location: Impact Initiatives, Geneva + dial in

Attendance: Joseph Ashmore (IOM / co-chair), Megan Passey (Impact Initiatives), Clay Westhorpe (REACH Initiative), online: Pablo Medina (IFRC), Miguel Urquia (UNHCR), Charles Parrack (Oxford Brookes)

Apologies: Vincent Annoni (Impact Initiatives), Victoria Murtagh (Christian Aid)

Meeting Minutes:

- Minutes from previous meeting:

  - The minutes of the last AWG meeting were discussed.

- Evaluation and impact:

  - Pakistan cluster evaluation: took place as planned. Comments were due by 29/09/2014 and the final document should be ready to present at the cluster workshop.

- Cluster Information management systems: SIP tender

- To date, no suitable candidates have come forward for the Web Development and Database Consultancy to establish the Shelter Information Portal (SIP).

- Impact Initiatives offered to develop a tool for the Myanmar Shelter Cluster, which will hold country-level assessment data and additional IM information. This tool will be developed for free and act as a working prototype, which could be later scaled-up as a global cluster tool.

- MP (Impact) to share TOR for Myanmar project when this is ready

- In parallel, it was agreed to use the Shelter Cluster Meeting as an opportunity to collect tools form cluster members and partners

- JA (IOM) to write a short consultancy TOR for this

- MP to inform Joseph of timeframe for advertising consultancy

- Accountability to Affected Populations:

  - It was suggested that the shelter coordination workshop be used as an opportunity to collect ideas about what Accountability to Affected Populations looks like and how it can be measured

- JA to make suggestions box for marketplace stand

- JA to follow up on training materials on Accountability

  - We were reminded that Accountability is a broad term to which all of the different activities supported by this Working Group contribute (assessment, monitoring, evaluation and information management)

- Shelter cluster Indicators

  - The most up to date list of Shelter Cluster Indicators on the Humanitarian Indicators Registry does not match the latest evaluation or assessment guidance on the Shelter Cluster Website

- Website should be updates