# Shelter Cluster Accountability Working Group

# Meeting minutes

Date: 20 November 2015

Location: Skype meeting

Attendance: Joseph Ashmore (IOM / co-chair), Megan Passey (Impact Initiatives), Bo Hurkmans (UNHCR), Neil Bauman (IFRC), Charles Parrack (Oxford Brookes), Victoria Murtagh (Christian Aid), Mohamed Hilmi (INTERACTION)

Meeting Minutes:

- IM Toolkit:

  - ACTION: BH and NB will review new tools fro inclusion

  - ACTION: NB to travel to Nepal and follow up with tools for use.

NOTE: Toolkit needs to be completed by June/July 2016.

  - Need to review several points raised in the workshop last month

  - IM team in Nepal is producing interesting tools that could be adapted for all

  - Toolkit needs to be distributed to many actors (on USB drives plus website)

- IM Training

- An IM training could be linked to the Master’s course on coordination (ongoing discussion between UNHCR, MAP action and WFP).

- Oxford Brookes can repeat the same process for the IM trainings

- Discussion on dividing the training in stages, so that there can be a freely available part, and a second tutored part.

- ACTION: VM to share training content for reference

- ACTION: NB to develop concept note on the training (early January).

- SC Website:

  - ACTION: in process. UNHCR contracting software developers to work to an agreed upgrades by end 2015.

  - Main issues were pointed out, including page structure, search function, overall navigation.

  - Funding has been already used, for more enhancements and next steps more funds are needed.

  - Some country level clusters are still developing their own sites, and are requesting to have web diversion enabled. There is a challenge of meeting the cluster aim of having one website and meeting specific operational needs. However these are mainly using legacy code as a basis. In the long term it expected there will be more convergence as the global site gains more features..

- Activity info, OCHA and HPC

- ACTION: BH will follow up and share

- CCPM (Cluster Performance Monitoring):

- ACTION: Minutes of UNICEF meeting will be distributed

- Coordination examples: ):

ACTION: JA to revise by Cob 23rd November and MP to review the current draft

  - JA received many simple examples of good/bad practices of coordination, both through preliminary round of email and SC meeting. Decision on how to disseminate still pending.

- AOB:

  - Accountability questions in assessments.

- ACTION: MP and VM to follow up with Nick Pragg for involvement/ one-off meeting

- Conclusion/Discussion:

  - Some discussion was held about the working group and direction. As a WG, the focus is on deliverables. There is a risk that making it a CoP it will be less results oriented.

  - Being a closed WG has the risk of not hearing others’ (non-HQ) opinions.

- ACTION: NB to send a document on communities of practice. WG to comment by Friday 27th

- ACTION: JA to compile comments and propose the document to the SAG