## Sheet1
Government Grants provided to Ramechhap District for building Temporary Shelter (till 30 July 2015)
S.N | VDC /Ramechhap | Estimated (NPR) | Estimate Distribution No of HHs | Completed Distribution(NPR) | Completed HHs | Ongoing Distribution(NPR) | Remaining HH | Additional Comment
1 | Manthali NP | 74550000 | 4970 | 74550000 | 4970 | 0 | 0
2 | Ramechhap NP | 42300000 | 2820 | 41445000 | 2763 | 855000 | 57
3 | Rampur | 10125000 | 675 | 10125000 | 675 | 0 | 0
4 | Bhuji | 8955000 | 597 | 8775000 | 585 | 180000 | 12
5 | Gumdel | 9090000 | 606 | 8250000 | 550 | 840000 | 56
6 | Saipu | 11065000 | 737 | 10725000 | 715 | 340000 | 22
7 | Kubukasthali | 12330000 | 822 | 10215000 | 681 | 2115000 | 141
8 | Farpu | 9975000 | 665 | 9975000 | 665 | 0 | 0
9 | Makadum | 6315000 | 421 | 6195000 | 413 | 120000 | 8
10 | Bijulikot | 19575000 | 1305 | 18570000 | 1238 | 1005000 | 67
11 | Khimti | 12675000 | 845 | 9000000 | 600 | 3675000 | 245 | NRCS distributed in one ward
12 | Namadi | 14850000 | 990 | 13995000 | 933 | 855000 | 57
13 | Rasnalu | 12000000 | 800 | 12000000 | 800 | 0 | 0 | Need additional
14 | Bamtibhandar | 12800000 | 853 | 12165000 | 811 | 635000 | 42
15 | Bhirpani | 13185000 | 879 | 12930000 | 862 | 255000 | 17
16 | Rakathum | 11640000 | 776 | 11610000 | 774 | 30000 | 2
17 | Chuchure | 11090000 | 739 | 11025000 | 735 | 65000 | 4
18 | Those | 9000000 | 600 | 9000000 | 600 | 0 | 0
19 | Betali | 18285000 | 1219 | 17775000 | 1185 | 510000 | 34
20 | Pakarbas | 20205000 | 1347 | 19995000 | 1333 | 210000 | 14
21 | Duragaun | NRCS
22 | Nagdaha | 17580000 | 1172 | 17025000 | 1135 | 555000 | 37
23 | Pingkhuri | 8550000 | 570 | 8370000 | 558 | 180000 | 12
24 | Tokarpur | 12150000 | 810 | 11580000 | 772 | 570000 | 38
25 | Gothgaun | 11100000 | 740 | 9165000 | 611 | 1935000 | 129
26 | Daduwa | 18105000 | 1207 | 18105000 | 1207 | 0 | 0
27 | Fulasi | 23010000 | 1534 | 23010000 | 1534 | 0 | 0
28 | Gelu | Distributed by RRN
29 | Himganga | 16125000 | 1075 | 1575000 | 1050 | 375000 | 25
30 | Puranagaun | 11760000 | 784 | 11760000 | 784 | 0 | 0
31 | Gupteshwor | 6195000 | 413 | 6195000 | 413 | 0 | 0
32 | Gaushwara | 9150000 | 610 | 8805000 | 587 | 345000 | 23
33 | Khaniyapani | 15435000 | 1029 | 15435000 | 1029 | 0 | 0
34 | Doramba | 13230000 | 882 | 13230000 | 882 | 0 | 0
35 | Majhuwa | 8225000 | 548 | 8190000 | 546 | 35000 | 2.33
36 | Sanghutar | 8295000 | 553 | 7830000 | 522 | 465000 | 31
37 | Deurali | 13125000 | 875 | 13125000 | 875 | 0 | 0
38 | Lakhanpur | 25680000 | 1712 | 25680000 | 1712 | 0 | 0
39 | Gunsibhadaure | 18600000 | 1240 | 0 | 0 | 18600000 | 1240
40 | Gagalbhadaure | 11340000 | 756 | 8280000 | 552 | 3060000 | 204
41 | Khandadevi | 15300000 | 1020 | 0 | 0 | 15300000 | 1020
42 | Hiledevi | 13050000 | 870 | 0 | 0 | 13050000 | 870
43 | Chanakhu | 8820000 | 588 | 0 | 0 | 8820000 | 588
44 | Dimipokhari | 15450000 | 1030 | 0 | 0 | 15450000 | 1030
45 | Bethan | 20970000 | 1398 | 20970000 | 1398 | 0 | 0
46 | Priti | 23250000 | 1550 | 0 | 0 | 23250000 | 1550
47 | Tiplung | 18300000 | 1220 | 510000 | 34 | 17790000 | 1186
| Total | 272300000 | 18153 | 141585000 | 10384 | 116540000 | 7769.33
18153

## Sheet3
VDC /Ramechhap | Completed HH | Ongoing HH
Manthali NP | 4970 | 0
Ramechhap NP | 2763 | 57
Rampur | 675 | 0
Bhuji | 585 | 12
Gumdel | 550 | 56
Saipu | 715 | 22
Kubukasthali | 681 | 141
Farpu | 665 | 0
Makadum | 413 | 8
Bijulikot | 1238 | 67
Khimti | 600 | 245
Namadi | 933 | 57
Rasnalu | 800 | 0
Bamtibhandar | 811 | 42
Bhirpani | 862 | 17
Rakathum | 774 | 2
Chuchure | 735 | 4
Those | 600 | 0
Betali | 1185 | 34
Pakarbas | 1333 | 14
Nagdaha | 1135 | 37
Pingkhuri | 558 | 12
Tokarpur | 772 | 38
Gothgaun | 611 | 129
Daduwa | 1207 | 0
Fulasi | 1534 | 0
Himganga | 1050 | 25
Puranagaun | 784 | 0
Gupteshwor | 413 | 0
Gaushwara | 587 | 23
Khaniyapani | 1029 | 0
Doramba | 882 | 0
Majhuwa | 546 | 2.33
Sanghutar | 522 | 31
Deurali | 875 | 0
Lakhanpur | 1712 | 0
Gunsibhadaure | 0 | 1240
Gagalbhadaure | 552 | 204
Khandadevi | 0 | 1020
Hiledevi | 0 | 870
Chanakhu | 0 | 588
Dimipokhari | 0 | 1030
Bethan | 1398 | 0
Priti | 0 | 1550
Tiplung | 34 | 1186
| 10384 | 7769.33

## Sheet5
Ongoing Distribution(NPR) | (All)
Completed HHs | (All)
Row Labels | Sum of Estimate Distribution No of HHs
Bamtibhandar | 853
Betali | 1219
Bethan | 1398
Bhirpani | 879
Bhuji | 597
Bijulikot | 1305
Chanakhu | 588
Chuchure | 739
Daduwa | 1207
Deurali | 875
Dimipokhari | 1030
Doramba | 882
Duragaun
Farpu | 665
Fulasi | 1534
Gagalbhadaure | 756
Gaushwara | 610
Gelu
Gothgaun | 740
Gumdel | 606
Gunsibhadaure | 1240
Gupteshwor | 413
Hiledevi | 870
Himganga | 1075
Khandadevi | 1020
Khaniyapani | 1029
Khimti | 845
Kubukasthali | 822
Lakhanpur | 1712
Majhuwa | 548
Makadum | 421
Manthali NP | 4970
Nagdaha | 1172
Namadi | 990
Pakarbas | 1347
Pingkhuri | 570
Priti | 1550
Puranagaun | 784
Rakathum | 776
Ramechhap NP | 2820
Rampur | 675
Rasnalu | 800
Saipu | 737
Sanghutar | 553
Those | 600
Tiplung | 1220
Tokarpur | 810
Grand Total | 46852