National Flood Response Matrix – Afar, Somali and SNNPR

| Region | Sector | Activities | Number of people receiving assistance | Partner | Budget/Supplies required | Dispatched so far | Available | Gap | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Afar* | WASH | Provision of Water purification and hygiene supply | 62,572 | RWB, CARE Ethiopia, Save the children | 319410 sachets of Bishangari or 638820 sachets of Pure | 618,210 sachets of Pure and 46000 sachets of Bishangari by UNICEF, GOAL, RWB, RHB, CARE for Amibar and Dulsa. 500,000 sachets of water Pur and 87780 sachets of bishangari by Care for Buremodito and Gewane woreda. | 1 sachet of Bishangari purifies 20 litre water and 1 sachet of Pure purifies 10 litre water | none | SCI has secured us$50,000 for Gewane and Burimodayto woredas including health and NFI. |
|  |  | rehabilitation of damaged water schemes | 29,592 (Dulecha and Amibara and AwshFental | RWB | 7 water schemes and 3 hand pup need to be rehabilitated in Amibara, Dulsa and AwashFental woredas. | none |  | none | Assessment of damaged schemes should be conducted after the water recedes |
|  | Health (Input from Cluster) | Strengthen surveillance for AWD, Malaria and other outbreaks and through supportive supervision | 28392 (Dulecha and Amibara | RHB WHO | Supervision – USD 30,000 | A team of health professionals from FMOH , RHB and MHNT arrived to the flood affected kebeles and are conducting both curative and preventive services |  | USD 25,000 |  |
|  |  | Provision of malaria Treatment drugs ( Coartum +RDT) | 28392 (Dulecha and Amibara) | RHB | For procurement of drugs and medical supplies – USD 170,000 | 1012 PKTs of coartum and 3000 kits of RDT, chloroquine 160 tin, quinine tab of 300mg=160 PKT, paracetamole syrup=40 bottle, 2 box of paracetamole tab by FMOH and RHB Arthmetrin injection - 400 EPHI |  | USD 170,000 |  |
|  |  | Provision of for prevention of AWD and other outbreaks Emergency drugs and CTC Kits ( for prepositioning ) | 28,392 | RHB |  | 5 EDK from GOAL 8 EDK from UNICEF 5 IEHK were also received from EPHI 20,000 ORS sachet from EPHI 1000 bottle of Amoxicillin suspension from EPHI Ringer lactate 500 (UNICEF) IV cannula - 280 Scalp vein - 23 |  |  |  |
|  |  | Provision of ITNs to kebeles in Amibara, Dulecha, Gewane,Asayta woredas and RHB | 38,392 | RHB, FMOH, Goal, Unicef | For procurement of LLITNS – USD 756 | 30, 600 LLITN (FMOH, GOAL,UNICEF, RHB…) |  | USD 756 |  |
|  |  |  |  |  |  |  |  | USD 200,756 | Supply matrix attached |
|  | Food | Provision of Emergency food | 61372 | DRMFSS, DPFSPCO | wheat, CSB, oil, salt and pulse | 11413.5 Wheat, 138.6 CSB, 118.2 Pulse, 37.5 Oil, |  | For 11944 Gewane and 10536 Affected people need of 3371 Quintals of wheat, 1011Q CSB, 105 Q of oil and 337 Q of pulse. | The food has on the process to dispatch from DRMFSS for Gewane Burimoditu and AwashFental woredas. |
|  | NFI (Input by the cluster) |  |  |  | Blanket, Plastic sheet, Cooking pot, Plastic cup, Plastic plate, Water jag, Ladle, Jerrican | Delivered by DRMFSS: 2879 blanket, 100 cooking pot, 2500 plastic sheets, 1100 Jerican, 5000 cup, 500 jog, 5000 plates, 100 laddel, |  | No gap - The ES/NFI needs of Afar Region will be addressed fully with the joint IRC/Goal delivery of 2,000 ES/NFI kits. |  |
|  | Livelihood | Provision of animal feed( Hay and concentration) | 9000 | APADB and CARE | 60592 bell grass and hay 95507 bell concentration | Delivered by CARE 17313 bell hay and 7286 concentration for Gewane. 14426 hay and 6075 concentration for Burimoditu, 11540 hay and 4860 concentration for Awsh Fentail and 17313 hay and 7286 concentration for Amibara | noon |  | Requests for extra support will be made based on the woreda assessment |
|  |  | Provision of seed | 5251 hectares of land in Amibara woreda and 480 hectares of land in Dulsa. | APADB | none | none |  | noon |  |
|  | Education | School maintenance | Maintenance of 3 schools in Amibara & 4 schools in Dulesa |  |  | UNICEF dispatched 3006 school in a bag kits, 30 tents , 932 plastic sheets and 49 black boards that benefit 3006 school children REB has been widely distributing education materials but accurate figures not yet found |  | - Maintenance of 3 schools in Amibara & 4 schools in Dulesa - Teachers and school management kits, Text book and sport materials for 3857 children and - 54 blackboards for 2700 children |  |
|  |  | Provision of school materials | Provision of education supplies and tents that benefit 3857 school children |  |  |  |  |  |  |
| Region | Sector | Activities | Number of people receiving assistance | Partner | Budget/Supplies required | Dispatched so far | Available | Gap | Remarks |
| Somali | NFI/shelter materials | Provision of NFI and Shelter | 25,092 HH kits |  | 25,092 HH kits | Dispatch of 2000 kits from IOM started on October 27, 2014 | 3000 HH kits by (ICRC<500,ERCS-500,IOM-2000,FHI-1000,SCI-1000,)Humanitarian Agencies 10,000 HH kits by SRS government | 11670 HH kits | Actual number of flood affected people VERFIED Request received by Cluster is 3,000HH – the gap11,670 HH kits of needs to be verified with the Regional DPPB requesting through DRMFSS in Addis as per the standard structure. |
|  | WASH | Water Purification Chemicals) Water Guards * | 41,754 affected hh and 27,258 displaced hh |  | 54,516 |  | 3,000 | 51,516.00 | * = water purification chemicals are calculated initially for two month and the sector has secured requirement amount. |
|  |  | Bishangari * | 41,754 affected hh and 27,258 displaced hh | IRC, SCI, UNICEF, RWB, SAAD, HAVAYOCO, Oxfam Inter, | 1,635 |  | 1,497 |  |  |
|  |  | Aquat tab * | 41,754 affected hh and 27,258 displaced hh | UNICEF/RWB | 54 |  | 3 | 50.70 |  |
|  |  | Emwat Kits * | 41,754 affected hh and 27,258 displaced hh | UNICEF | 5 |  | 5 |  |  |
|  |  | Body Soap | 41,754 affected hh and 27,258 displaced hh | IRC, SCI, UNICEF, RWB, SAAD, HAVAYOCO, Oxfam Inter, | 24,000 |  | 22,700 | 1,300 |  |
|  |  | Jerry-cans distributions | 41,754 affected hh and 27,258 displaced hh |  | 70,368 |  | 4,575 | 65,793 | Jerry cans and soap will be distributed as part of the NFI and the WASH cluster will monitor the need |
|  |  | Hygeine Promotions |  | UNICEF/RHB |  |  |  |  |  |
|  |  | Communication Materials |  | UNICEF/RHB |  |  |  |  | IEC – materials are not available and will be prepared/distributed before 15Nov14 as part the GHWD celebration in Somali region. |
|  | Education | Rebuild/renovate schools | 49 schools |  |  |  | 720 Tarpaulins that benefit 3000 school children | 3 schools need rebuilding 33 schoold require renovation | In kelafo (3 schools to rebuild and 33 schools require renovation and furniture) and Ferefer (13 schools require renovation). No data on Mustahil. |
|  |  | Provision of education supplies and materials | 17,302 school aged children | UNICEF |  |  | 3000 School in a bag kits that benefit 3000 school children | 12,340 school age children require education materials | Kelafo (15,340) and Ferefer (1,962) |
|  | Health | Assign Health professionals for 3 months at Gode, Hargelle& D/ado to Coordinate all Health Responses |  |  | USD 21,905 |  |  |  | Includes 1 car rent for 2 months |
|  |  | Train 25 HWs from each woreda & Health facilities in the affected Woreda on Epidemic investigation & Diseases management and laboratory |  |  | USD 23,810 |  |  |  | Increase the capacity of Health workers in of epidemic management |
|  |  | Deploy 8 Mobile Health Teams in Kalafo, Mustahil, Ferfer , D/bay, Hargelle, D/ado for 3 months |  |  | USD 114,857 |  |  |  | Provide preventive and Curative health services for case management |
|  |  | Provision of 12 Emergency Drug Kits |  | UNICEF, WHO, FMOH may provide |  |  | 12 EDKs for all affected woreda |  |  |
|  |  | Community based health education |  |  | USD 2019 |  |  |  |  |
|  |  | Prepare 150 Dry waste disposal pits one for each kebele affected |  |  | USD 8,071 |  |  |  | Hygiene and Sanitation |
|  |  | Decrease malaria Morbidity and Mortality - ITN/mosquito Net Distribution 16,200 pcs. | 26,693hh |  | USD 254,219 |  |  |  | Budget for HH distribution through other logistics |
|  |  | Anti-malaria drug Distribution |  |  |  |  | RHB will provide drugs & supplies |  | Distributed by the mobile teams |
|  |  | Nutrition - Distribution of High energy foods for selected <5 children and pregnant and lactating women (600 cartons of BP5) |  |  |  |  | RHB will provide the Plumpty nets |  | Distributed by the mobile teams |
|  |  | SRHB Emergency Drugs & Medical Supplies kit |  |  | 28,571 |  |  |  | Quantity – 12 Unit cost – 2,381 |
|  |  | Logistics costs drug kit collection & distribution |  |  | 34,286 |  |  |  | Quantity 12 Unit cost - 2,857 |
|  |  |  |  |  | Total Cost – 487,738 |  |  | Total Cost – 487,738 |  |
|  | Livelihood |  |  |  |  |  |  |  |  |
|  | Food |  |  |  |  |  |  |  |  |
| SNNPR |  |  |  |  |  |  |  |  |  |
| SNNPR | NFI/shelter materials | Provision of NFI and Shelter | 4114 HH |  | 4,114 ES/NFI kits |  | To be discussed | 4114 kits | This is based on report from IOM DTM exercises in October, 2014. The displaced are in need of humanitarian assistance. Specifically Butajira-174HHs, Silte Zone-3125HHs, Lanfiro Woreda-26HHs, Dalocha- 77HHs, Mareko-282 HHs, Meskan-430HHs |

* Number of people affected: 23752 people in Amibara woreda and 4640 people in Dulecha Woreda, 10500 people in Asayta woreda, 11944 people in Gewane woreda, and 10536 people in Burimodayto Woreda and 1200 people in AwashFenatal woreda.

Nutrition – Afar and Somali Regions

| Region | zone | woreda | Number of OTP posts affected ( not operational) | TFU/SC | number of beneficiaries ( <5s children) affected | Type of response going on |  |  |  |  | Gaps in response in the flood affected areas | Recommended actions for gaps | Implementing partner | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | OTP ( RUTF, routine drugs) |  | SC/TFU | MHNT | TSF |  |  |  |  |
| Somali | Shebele | Kelafo | 9 | 1 |  | Yes | yes |  | yes | CSB, oil for flood affected population | 1 MHNT,SC, TSF, Screening | 1: SCI to establish temporary TFU/SC in the woreda and 2: UNICEF to provide the supplies in cluding tents for temporary SC and 3: SCI to conduct screening and manage children in the displaced areas if not done by the MNHTs. Screening for TSF to commence first week November | SCI/RHB | Additional 1 SC and 1 MHNT needed for 3mo |
|  | Sheble | Mustahili | 3 | 1 |  | Yes | no |  | yes | Yes (implemented in September for three months up mid December), CSB and Oil for flood affected population | SC , Screening ,Logistics for delivering supplies | 1: SCI to establish temporary TFU/SC in the woreda and 2: UNICEF to provide the supplies in cluding tents for temporary SC and 3. SCI to conduct screening and manage children in the displaced areas if not done by the MNHTs | SCI/RHB | Additional 1SC needed |
|  |  | Dolo Bay | very few affected |  |  | Yes | no |  | yes | Yes (implemented in September for three months up mid December) | MHNT | UNICEF to supoort the additional MNHTs as soon as possible | RHB | 1 additional MHNT needed for 3mo |
|  | Shebele | Ferfer | nill | 1 (not functional) |  | yes | no |  | yes | Yes (implemented in September for three months up mid December) | SCI | SCI to start TFU/SCI as soon as possible | SCI/RHB |  |
|  |  | East Emey |  |  |  | yes | no |  | no | No yet started | MHNT, TSF | UNICEF to supoort the additional MNHTs as soon as possible. Ad hoc Screening for TSF to commence first week November | RHB | additional 1 MHNT needed for 3mo |
|  |  | West Emely | nil |  |  |  |  |  |  |  |  | RHB with support from UNICEF to strengthening of the existing TFP services in the woreda | RHB/UNICEF |  |
|  |  | Shinile | nil | 1 |  |  |  |  |  |  |  | RHB with support from UNICEF to strengthening of the existing TFP services in the woreda | RHB/UNICEF |  |
|  |  | Kebridah | nil |  |  |  |  |  |  |  |  | RHB with support from UNICEF to strengthening of the existing TFP services in the woreda | RHB |  |
|  |  |  |  |  |  |  |  |  |  |  |  | RHB with support from UNICEF to strengthening of the existing TFP services in the woreda |  |  |
| Region | zone | woreda | Number of OTP posts affected ( not operational) | TFU/SC | number of beneficiaries ( <5s children) affected | Type of response going on OTP ( RUTF, routine drugs); SC/TFU; MHNT; TSF. | Gaps in response in the flood affected areas | Recommended actions for gaps | Implementing partner | Remarks |
| Afar |  | Amibara | 4 | 2 |  | Yes | yes ( all two operational) |  | MHNT relocated from Kori | No yet started | TSF | TFP/TSF services provision assessment to be conducted first week of November | RHB/REW/AMREF | TSF is supposed to be implemented by regional early warning. AMREF proposal recommended for funding, response expected in 2 weeks? |
|  |  | Gewane | 3 | 1 |  | Yes | Yes |  | MHNT relocated from Buremudaytu | No yet started | TSF | TFP/TSF services provision assessment to be conducted first week of November | RHB/REW/AMREF | TSF is supposed to be implemented by regional early warning. AMREF proposal recommended for funding, response expected in 2 weeks? |