Action points from EOC Flood Coordination Meeting

30 October 2014

Participants: DRMFSS EOC, DRMFSS ICP Jijiga, DRMFSS ICP Amibara, WFP, OCHA, UNICEF, MoWE, IOM, ENCU DRMFSS

Absent: EHNRI, WHO, FAO

Afar Flood Response Matrix

WASH

- DRMFSS in collaboration with the Afar ICP to clarify the number of flood affected people in Afar Region to agree on a working figure for sector response;

- WASH Sector reported that post damage assessment of water schemes was undertaken and adequate funding has been secured to rehabilitate damaged water sources: WASH sector to update the matrix accordingly. The group also noted that provision of water chemicals will be the prioritized response to ensure continued provision of potable water; while water trucking remains the last resort and not recommended for the current emergency situation.

Health

- Input was not discussed as sector representatives were not present. DRMFSS bilaterally to discuss with EHNRI the health sector input.

Food

- Relief food has been dispatched to  all affected caseload – xxx – through PSNP and relief food resources.  DRMFSS to update the matrix accordingly;

TSF

- Nutrition screening has been undertaken to form the basis for the regular TSF distribution. TSF provision was delayed due to logistical constraints which has been addressed and is expected to be commencing in the coming days. WFP to provide an update of TSF provision and update the matrix accordingly;

ES/NFI

- The ES/NFI cluster noted that with the prior agreed working figure – 7000hh all gaps have been addressed with input from IRC/GOAL amounting to 2,000 kits complimenting assistance provided by DRMFSS. The ICP focal point also reported that the gaps has been met with ongoing response and with the water level dropping, the ES/NFI needs have reduced. It was, however, reported some gaps were reported by some actors in the region that needs to be verified: Afar ICP and NFI cluster to work with the region to verify that there is no gap in the sector response; the NFI cluster to update the response matrix accordingly;

Nutrition

- In the affected 4 kebeles in Amibara, OTP services are provided in temporary structures along with health services with support from MHNT relocated from Kori. Similarly, in 8 kebeles in Gewane, OTP services are provided by MHNT relocated from Buremudaytu woreda and in temporary structures by the RHB/woreda health office. TFU services are provided in 2 SC/TFU sites in Amibara and one SC in Gewane woreda.  An assessment is planned to be conducted in first week of November on nutrition services and take action accordingly. No shortage of TFP supplies in for the time being.

Education

- The need to undertake a post damage joint assessment to determine the level of damage to determine the required intervention was noted by the group. The education cluster to organize a joint post damage assessment and update the matrix accordingly;

Livelihood

- Input was not discussed as sector representatives were not present. DRMFSS bilaterally to discuss with FAO the regional Livelihood inputs.

Somali Flood Response Matrix

NFI

- Out of the total NFI required for 26, 670 Households, the Region will cover 10,000 NFI kits; FHI will cover 1000 NFI kits, IOM will cover 2000 NFI kits, ERCS will cover 500 NFI kits, and IRC 500 NFI kits. Additionally the Regional Water Bureau and the Regional Agriculture Bureau have committed to re-direct budget to procure 100 kits and 200kits respectively. With the pledges and contributions, the gap stands at 12,000kits. The Afar ICP and NFI cluster to follow up with SCI and ARRA on the unformed pledges.

Food

- Out of the thirteen flood affected woredas, nine woredas are under regular PSNP and /or emergency food assistance. For the remaining four woredas that are covered neither by PSNP nor by relief programme - kelafo (10,000), Mustahil (6000), East Emay (6806), Adadle (1632) and Shinile (654) woredas - ad-hoc allocation has been made.  WFP started food dispatch to these areas on 29 October 2014. A total of 376.38 MT of grain, 37.64 MT of pulses, and 11.29 MT of oil will be distributed for 25,092 flood beneficiaries in these flood affected woredas.

- The sixth round PSNP has been distributed; while, the fifth round relief food dispatch is underway;

- Concerns reflected by the Jijiga ICP: - The PSNP basket constitutes only cereal and pulse and the beneficiaries in PSNP woredas are raising concerns that considering the scale of the flood disaster, full food basket should have been distributed;

WASH

- The WASH sector reported that the Water Purification Chemicals and Body Soap gaps have been fully addressed with contribution. As to jerry-cans distribution, WASH Sector requested the items in the NFI kits to avoid duplication and draw a working figure. IOM noted that the standard NFI kit constitutes three jerry-cans (1 - 20lts and 2 – 10lts); however, it was noted that all kits may not constitutes the standard item. Although the distribution of the full NFI kits is encouraged, the need to distribute items at hand was underscored by the group to ensure timely response.

- Considering the 12,000 NFI HH kits, the group agreed for WASH sector to base 12,000hh for the provision of jerry-cans;

TSF

- TSF provision was undertaken by SCI in flood affected woredas in Mustahili, Ferfer, Gode and Kelafo, using centrally procured TSF resources from OCHA-HRF. The intervention was undertaken to fill the gap until the regular TSF intervention based on a nutrition screening commences.

- Given the severity of flood impacts in flood affected priority 1 woredas, the RHB and UNICEF to expedite the nutrition screening to kick start TSF provision;

- WFP to commence pre-position of TSF resources in the region to avert logistical delays and ensure timely start of the operation once screening is completed;

- Jijiga ICP to identify number of flood displaced in affected Priority 2 and 3 areas to mobilize additional TSF resources from the HRF Central Procurement;

Nutrition

- Three additional Mobile Health and Nutrition Teams (MHNT) are needed to fill response gaps in Dolo Bay, Kelafo and East Emey – UNICEF to implement;

- UNICEF to scale up provision of TFP supplies to meet the increasing requirement;

- Identification of new cases in flood affected areas – screening of under-five population – responsible SCI

- Continued in kind supplies for SCI (TFP and TSF) for its operation in flood affected woredas;

Education

- The need to undertake a post damage joint assessment to determine the level of damage to determine the required intervention was noted by the group. The education cluster to organize a joint post damage assessment and update the matrix accordingly;

Health

- Input was not discussed as sector representatives were not present. DRMFSS bilaterally to discuss with EHNRI and WHO the health sector input.

- Jijiga ICP reported a spike in malaria in Dolo Ado – DRMFSS to discuss with EHNRI and WHO

Livelihood

- Input was not provided by the Agriculture Sector Taskforce. DRMFSS bilaterally to discuss with FAO the regional Livelihood inputs.

SNNPR Flood Response Matrix

- The region requested assistance to 35,698 flood affected people in Dasenech woreda. Based on the request DRMFSS has dispatch an initial relief food assistance to 50 per cent of the affected population;

- The region also requested provision of fodder and hay 16,500 livestock as most grazing lands have been inundated by water: DRMFSS to collaborate with FAO and Agriculture Sector actor to fill the gap;

- The respective sectors to continue to liaise with the regional sector bureaus to identify outstanding sector gaps;