[image: image1.png]



Minutes of ES/NFI Cluster Meetings
	Date
	July 11th , 2013 

	Time
	10:00am

	Venue
	IOM Conference Room

	Attendance
	UNOCHA,IRC,ERCS,GOAL,COOPI,UNICEF,ZOA & IOM


	Agendas
	1. Review last meeting minute
2. Update from partners
3. Flood Contingency plan
4. NFI Strategy 
5. AOB



	1.Review of last meeting minutes 

	Meeting Minutes Reviewed and endorsed.


	2. Update from Partners

	IOM

· 1717 Full NFI kits have been distributed in East Hararge, Kumbi.
· For Conflict affected population in Somalia, 2800 NFI kits have been requested by the regional government and IOM has pre-positioned for 2000.
· For Flood affected population, IOM has dispatched 1500 NFI kits in Mustahil woreda.
· Gambella conflict was in June between Jikawo & Nyinyang where it is identified from an assessment that 1460HH were displaced and IOM has dispatched 1,000.
· 650 NFI kits are also dispatched to Moyale. 
· 910 NFIs were distributed for protracted in Harar.

AP – IOM to share a report on the Gambella conflict caseload 
IRC 

· IRC has respond with 61 standard NFI kits for conflict displaced in Gambella, Wantoa Woreda.
    ERCS
· ERCS is not addressing full kits

· In East Shewa, Welenchity ERCS has dispatched NFIs for 750 HH.
· ERCS has also response to a Fire accident at Bole, Addis Ababa for 18HH with 18 Blankets, 18 Sleeping mat, 36 plates, 36 Cup and 18 Cooking pots. 

GOAL
· Recent Emergency Response Mechanism has been approved by ECHO. 

· Intervention has gotten from ECHO where GOAL and IRC are working on mainly on health & NFI 
Comment - IRC takes the lead & GOAL can access the fund through IRC.

                   -  IOM expects 4000 kits of NFI pre-positioned for IDPs starting August.
AP – To share quality of NFIs granted by ECHO. 

COOPI
· No updates

UNICEF
· UNICEF has done assessment in Benshangul, Hawagalan woreda where there are gaps of 6100 IDPs with no land, access to health, water & education and completely excluded from the community which start displacing 4years back.
AP- UNICEF to provide information about Hawagalan woreda
ZOA
· 850HH kits have been distributed in Akobo.

	3. Flood Contingency Plan

	· Task force is already activated where the flood in the country has been identified. Once approved, it will be shared on the website
AP – mapping out our resources and share what each agency have in the next cluster meeting.  



	4. NFI Strategy

	· It was suggested to come up with clear strategy plan mainly on answering questions like who can provide what and how many in numbers of the items to be distributed.
· Suggested to put details of an assessment in identifying a need in order to respond to the needs.
· Working group to be created between IOM, UNICEF, ERCS & IRC.

AP – IOM, UNICEF, ERCS & IRC– first meeting to be held on Monday  15th of July at 3PM –first draft to be presented & discussed on the next cluster meeting 


	5. AoB

	


The next meeting is to be held on 8th of August, 2013. 
Meeting adjourned.
