# ES & NFI Coordination & Shelter Sector

Meeting Minutes

10 November 2013

Date:	Tuesday 1O November 2013, 1100 – 1230 hrs

Location:	UNHCR Khartoum: Conference Room

# Presente:	ESNFI Project (chair and minutes), UNOCHA, HAC, GFO, Al Ruhamaa, UPO, Concern WW, Jasmar,  Mubadiroon, Labena, Nada Al Azhar.

# Action Items from previous meeting:

| Issue | Responsible | Action Taken | Comments |
| --- | --- | --- | --- |
| GPS coordinates | Sector Partners | Action taken by GFO on last mission |  |
| HWP 2014 | ES NFI /Sector Partners | Project sheets are being shared with Sector lead for comment |  |
| CHF update 2014 | ES NFI /Sector Partners | CHF workshop held on November 6th. Sector participants – GFO/UPO | Details of CHF process to be shared with partners |

# Action Items from This meeting:

| Issue | Discussion / Key Points / Actions |
| --- | --- |
| HPW 2014 | - Partners were reminded to finalise and upload their project sheets onto OPS by 17th November (this was subsequently delayed to 19th November). - Partners need to be well acquainted with mainstreaming of the Gender & Environmental markers in their project sheets. Gender blind projects will be rejected. - Peer review meeting for project prioritisation will be held on the 18th ( subsequently delayed to the 20th) |
| Shelter provision | Discussion on the types of shelters supported by the ES & NFI Sector. For newly displaced, where required, partners can provide sticks/ropes and nails for beneficiaries to build a frame to support the plastic sheet provided by the NFI CP. This type of ‘improved’ emergency shelter should not cost the partner more than 10 US$ per shelter GFO presented a few slides on a new type of transitional shelter that they are piloting in Nyala. Partners were reminded to share ‘lessons learned’ from pilot shelter projects with other Sector partners |
| Flood Updates | Coordination of NFIs assistance to the flood affected population in west kordofan state - ESNFI project/IOM/Concern. |

# NFI-ES Operational update by participants

| ORG | Update | Action/Discussion/Updates |
| --- | --- | --- |
| Concern | C-W procurement of 1000 NFI kits for flood-affected households in west kordofan. | Procurement underway |
| IOM | IOM diversion of 3000 NFI kits for flood response | No progress |
| Islamic Relief | Islamic Relief internationals provided NFIs to flood affected populations in Khartoum state in the areas of: Jabrana, umbada, nifasha localities for 150 households. | Distributed |

The coordination meeting ended at 11.00.

This was followed by the orientation sessions by the Gender Advisor and the Environment advisor with a short lunch break in between.

The meeting ended at 3.30

Meeting participants

| Name | Organization | E-mail | Phone Number |
| --- | --- | --- | --- |
| Nevins Saeed | ESNFI Project | Nevinss@unops.org | 0964201192 |
| Miki Takahashi | ESNFI Project | Mikit@Unops.org | 0964201199 |
| Rami Khalid | ESNFI Project | Ramik@Unopc.org | 0964201196 |
| Khadija AbdelAziz | Al Ruhamaa | Mmarim57@yahoo.com |  |
| Maawia ElTayeb | Mubadiroon | Motabi3ak@gmail.com |  |
| Ibraheem Moodi | UPO | ibrahim@unitedpeac.org |  |
| Nazar Mahmoud | Mubadiron | nazarmahmoud@gmail.com |  |
| Dr.Nada Ali Abdalla | Concern WW |  |  |
| Enas Jafar | Jasmar | Enas_28@yahoo.com |  |
| Usra Abdelhalim | Labena |  |  |
| Nazik Mohammed | Nadal Azhar | Shazan.ahmed2005@hotmail.com |  |
| HAJER Omer | AORD | Hajer-prog@aord.org.sol |  |
| Mohammed Ahmed Omer | HAC |  |  |
| Sulafa Yousuf | Al Ruhamaa |  |  |
| Hafiz Mohammed zein | MC Scotland |  |  |
| Entisar Abdelsadig | Badya Center |  |  |
| John Connely | FAR | SDN-cd@farinternatinional.org |  |
| Fatima Mohammmed ismail | UPO |  |  |
| Tommy Tomiyama | IOM | ttomiyama@iom.int |  |
| Mohamemd Al Tahir | GFO | Gfamily.organization@gmail.org |  |
| Andrew Lokong | CRS | Andrew.lokong@crs.org |  |
| Joyce Munyao | UNHCR | munyao@unhcr.org |  |
| AbdelBasit Mohammed | HAC |  |  |
| Mahmoud Shamselden | HAC |  |  |
| Noon Ahmed | HAC |  |  |
| Mariam Daeifalla | HAC |  |  |
| Asma Adlan Abdulla | HAC |  |  |
| EL Amin Hassan El Amin | HAC |  |  |

Next meeting: 23rd  December --- 1100 Hrs – 12:30 hrs