# ES & NFI Sector Coordination & Shelter Working Groupr

Meeting Minutes

24 October 2013

Date:	Tuesday 24 October 2013, 1100 – 1230 hrs

Location:	UNHCR Khartoum: Conference Room

# Present:	UNHCR ESNFI Project (chair and minutes), IRW, IOM, JVC, Concern, SRCS, Elruhama, AORD, Triangle, UNAMID

# Action Items from previous meeting

| Issue | Responsible | Action Taken | Comments |
| --- | --- | --- | --- |
| Flood Matrix | Sector Partners | Regular Update of flood matrix on the OCHA website | Very little info received |
| Shelter Update. | Sector Partners | Shelter matrix updated | Done |
| Flood response Coordination with HAC | ES NFI /Sector Partners | The coordination is through the Flood task force meetings held at HAC weekly on Wednesdays at 16:00. Last meeting 8th October. | Not many updates as attendance was minimal |
| HWP 2014 | ES NFI /Sector Partners | Needs analysis for HNO has been submitted to OCHA. | Revised 2014 HWP timeline shared with partners |

# Action Items from This meeting

| Item | Discussion / Key Points / Actions |
| --- | --- |
| Flood Response | Partners to update on the flood assistance provided in Khartoum state and other states. |
| 2014 HWP | Partner Project sheets to be finalised and uploaded onto OPS between 7 November to 17 November - Sector coordinators with OCHA have put together a set of Strategic objectives for the 2014 HWP - The Strategic objectives were presented to the HCT for approval. - Once HCT comments incorporated, the Strategic objectives will be shared with the government for discussion/approval. - Once approved, Sector objectives and priorities will be finalised. - Partners advised not to finalize their project sheets before the strategic objectives and priorities are shared by Sector Lead |
| Gender & Environment mainstreaming in 2014 HWP project sheets | A short orientation session by the Gender and Environment advisors will be organised early November for ES & NFI Sector partners. |
| 2014 CHF Update | Sector Lead thanked sector partners for submitting their interim reports timely. CHF workshop planned for November 6th, for Sector Leads and PRG members. The 2014 CHF process will include a new step – the submission of a concept note rather than the full project proposal as an initial submission for review by the PRG. |
| ES & NFI Sector Monthly Update | Sector Lead once again reminded partners to send any updates they have of distributions from their own stock in order for inclusion in the monthly Sector Update for visibility |
| GPS coordinates | Partners requested to record GPS coordinates when doing assessment/ distribution to facilitate mapping. GPS units can be borrowed from ESNFI Project field offices |

# NFI-ES Operational update by participants

| ORG | Update | Action/Discussion/Updates |
| --- | --- | --- |
| TGH | Delivered mosquito nets to 1600 newly displaced households in West Darfur. There is some confusion over a request for specific NFI for vulnerable IDPs in Bindizi and plastic sheets for UM Dukhun, which is being discussed | Under progress |
| IOM | IOM is planning to approach the donor for diversion of 3000 NFI kits lined up for Khartoum, so that needy flood-affected populations in west kordofan and other states can be assisted. | Under progress |
| Concern | C-W plans to procure 1000 NFI kits for flood-affected households in west kordofan. Fund allocated 100,000 usd. Requested ESNFI Project to provide plastic sheets | Under progress |
| ESNFI project | Discussions with IOM/Concern for assisting flood affected households in WKS. ESNFI project will provide plastic sheets to compliment NFIs provided by Concern – | Ongoing -awaiting results of final assessment |
| Islamic Relief | Islamic Relief International reported the distribution of NFIs to 150 flood affected households in Khartoum state in the areas of: Jabrana, umbada, nifasha localities | Distribution completed |

Meeting participants

| Name | Organization | E-mail | Phone Number |
| --- | --- | --- | --- |
| Nevins Saeed | ESNFI Project | nevins@unops.org | 0964201192 |
| Miki Takahashi | ESNFI Project | Mikit@Unops.org | 0964201199 |
| Rami Khalid | ESNFI Project | Ramik@Unopc.org | 0964201196 |
| Shihab Babiker | IRW |  |  |
| Tommy Tomiyama | IOM | Ttomiyama@iom.int | 0922406639 |
| Takaki Imai | JVC | Imai@ngo-jvc.net | 0991606455 |
| Mohammed Toum | Concern | Pea.sudan@concern.net | 0118582155 |
| Ahmed El Jundi | SRCS | Elgundi_nasir08@ymail.com | 0918076476 |
| Sulafa Yusif Mohammed | El Ruhama | Mmarim57@yahoo.com | 0915823023 |
| Khadija Abdelaziz | El Ruhama | Mmarim57@yahoo.com | ----- |
| Hajer Omer | AORD | Hajer-prog@aord.org.sd | 0123441404 |
| Michele Ricca | Triangle TGH | Soudan@trianglegh.org | 0912276245 |
| El Hadi Fadlala Moul | UNAMID | fadlalla@un.org | 09224010601 |

Next meeting: 10th November --- 1100 Hrs – 12:30 hrs