Global Shelter Cluster: Settlement Working Group 
Draft plan of action

13 October 2017

|  | Result 1: AWARENESS & ADVOCACY: Increased awareness of the importance and benefits of area based approaches |  |  |
| --- | --- | --- | --- |
|  | ACTIVITIES | Priority | Timeline |
|  | GLOBAL LEVEL |  |  |
|  | Collaboration: - Work closely, align tasks & leverage with interested humanitarian/development actors (International & National NGOs, UN, donors, etc and complementary working groups/initiatives including: - IASC Meeting Humanitarian Challenges in Urban Areas - InterAction - Global Alliance for Urban Crises - ODI - Grand Bargain localization work stream - Academic Institutions - gFSC urban working group - ALNAP - Global CCCM settlement WG - United Cities & Local Government | High | Ongoing |
|  | Definitions & terminology: - Complete the definitions paper on what is an integrated/area/settlement based approach and what are its key principles and difference between coordination and programs. | High | December 2017 |
|  | GLOBAL, COUNTRY & AGENCY LEVEL |  |  |
|  | Communication and dissemination of lessons learnt - Co-host at least one event/forum/symposium per year on settlement based approaches in partnership with gSC WG agencies and other fora. | Medium | Annual |
|  | - Disseminating lessons learnt: Continue generating and compiling case studies of initiatives using Area Based Approaches & develop a comprehensive set of case studies | High | September 2018 |
|  | - Communications: - Communicate more effectively the settlement based approach through publications, communication products and media, utilizing gSC, country cluster and agency processes & products - Generate and disseminate a clear added value/argument for promoting the area based approach (short document, video etc) | Medium | Ongoing December 2017 |

|  | Result 2: FUNDING: Increased institutional support from donors and operational entities to apply the approach |  |  |
| --- | --- | --- | --- |
|  | GLOBAL, COUNTRY & AGENCY LEVEL |  |  |
|  | Donor advocacy: - Identify potential donor champions and advocate for the importance of the settlement approach | Medium | Ongoing |

|  | Result 3: OPERATIONAL SCALE & QUALITY: Increased knowledge by humanitarian actors (and others) to operationalise and scale up area based approaches |  |  |
| --- | --- | --- | --- |
|  | GLOBAL LEVEL |  |  |
|  | Creation of guidelines: - Create/support the creation of area based programming tool kit/guidance…. Including operational guidance and how it links in with OCHA, Governments, clusters, national coordination mechanisms etc. | Medium | TBC |
|  | Piloting & rollout of area based approaches: - Identify and pilot area based task forces at targeted country levels (e.g. forums to operationalize area/neighborhoods approach at country/city levels. - Promote the approach in targeted cities/urban contexts in: - Response contexts - Preparedness contexts. - Promote the piloting area/settlement based approaches at the country level through consortia & partnerships | High | Ongoing |