## Proframe
Last Updated - | PROFRAME
2026-07-29
By - LM
Objective statements | Performance indicator statements | Data source | Critical assumptions
GOAL: Households affected by Hurricane Matthew restore their lives in dignity
SO1 - Hurricane-affected households live in shelter that meets Sphere Standards | OFDA - # of households in the program area receiving emergency/transitional shelter pursuant to Sphere Project standards and FOG guidelines, disaggregated by shelter category Note: On base sur l'hypothese que chaque maison respecte la superficie minimum de 3.5 m2 par personne ce qui donne une superficie minimum de 21 m2 par menage. | Technical completion checklist | Weather conditions will remain normal over the program duration (i.e no major natural disaster will occur). Security conditions in operating areas will remain stable and will not disrupt the reconstruction process.
| CRS - % of households that report residing in transitional shelter compliant with Sphere Standards by EOP | HH survey
IR 1.1 - Targeted households use critical shelter inputs needed to repair and rebuild their homes | OFDA - # of households in the program area receiving emergency/transitional shelter, disaggregated by shelter category | Technical completion checklist | Weather conditions will remain normal over the program duration (i.e no major natural disaster occurs). Security conditions in operating areas will remain stable and will disrupt the reconstruction process.
| OFDA - % of total affected population in the program area receiving emergency/ transitional shelter assistance, by sex | Beneficiary database / Government data
| OFDA - Total USD amount and percentage of approved budget for emergency/transitional shelter spent on goods and services produced in the affected host country economy | Finance & procurement records
| CRS - % of households using salvaged materials effectively in the rebuild of their shelter | Technical completion checklist
| CRS - % of targeted households that report using complementary shelter inputs purchased with their voucher in the rebuild of their shelter | Post-distribution survey
Output 1.1.1 Targeted households access high-quality, in-kind CGI sheets | CRS - # of households receiving high-quality, in-kind CGI sheets | Redrose database | Targeted households use CGI sheets to rebuild their home.
Output 1.1.2 Targeted households salvage materials effectively in the rebuilding of their home | CRS - # of households receiving salvaging kits | Salvaging kit sign-off sheet | Sufficient materials can be salvaged from existing homes or made from fallen trees to adequately supplement the materials needed for repair and rebuilding. Targeted households adopt salvaging best practices for shelter reconstruction/repair.
| CRS - # of people attending training on best practices for salvaging, disaggregated by sex | Attendance list
Output 1.1.3 Targeted households access complementary shelter material inputs locally | CRS - # of targeted households receiving voucher for shelter reconstruction | Voucher sign-off sheet | Markets will remain functioning, well-stocked, and accessible to beneficiaries without prohibitively high price increases or discrimination.
Output 1.1.4 Labor groups (konbit) mobilized and supported to execute rebuilding activities | CRS - # of konbit members receiving complementary vouchers upon completion of their shelter | Voucher sign-off sheet
SO2 - Targeted community members are better prepared for future disasters | OFDA - # of shelters incorporating DRR/BBB measures, disaggregated by shelter category | Technical completion checklist | Weather conditions will remain normal over the program duration (i.e no major natural disaster will occur). Security conditions in operating areas will remain stable and will not disrupt the reconstruction process.
| CRS - % of CCPC members report feeling better prepared for emergencies | CCPC survey
IR 2.1 Targeted households have adequate advice and technical support to rebuild safely | CRS - % of targeted households applying techniques from build-back-better training in the repair/rebuild of their home, disaggregated by shelter category | Technical completion checklist | Weather conditions will remain normal over the program duration (i.e no major natural disaster will occur). Security conditions in operating areas will remain stable and will not disrupt the reconstruction process.
| OFDA - % of people retaining shelter DRR/BBB knowledge two months after training, by sex and function (i.e head of households or laborer) | BBB training survey
IR 1.2 -Targeted IDP’s in Collective Centers receive adequate assistance and technical support towards accessing appropriate housing solutions | 1.2.1.CRS - % of households receiving rental subsidies renewing a house rental at the end of their rental year. Note: Au cours de l'implementation du projet, on ne dispose pas de donnees pour repondre a cet indicateur. | Cash grant sign-off sheet | Weather conditions will remain normal over the program duration (i.e. no major natural disaster will occur). Security conditions in operating areas will remain stable.
Output 1.2.1 IDP’s receive rental subsidies | 1.2.1.1.CRS - % and # of targeted households receiving rental subsidies for one year, disaggregated by sex | Cash grant sign-off sheet | Weather conditions will remain normal over the program duration (i.e. no major natural disaster will occur). Security conditions in operating areas will remain stable.
| 1.2.1.2.CRS - % of targeted households receiving a relocation stipend, disaggregated by sex | Cash grant sign-off sheet
| 1.2.1.3.CRS - % of targeted households receiving a bonus stipend at the three month's mark, disaggregated by sex | Cash grant sign-off sheet
Output 1.2.2. Technical assistance and household inspection implemented | 1.2.2.1.CRS - # of legal consultation on land tenure successfully concluded by Fondation Haitienne for Affordable Housing. Note: On va se baser sur la methode de temoignage au cas ou la situation fonciere n'est pas claire. | Activity report | Targeted households adopt and incoporate BBB techniques in shelter reconstruction/repair.
| 1.2.2.2.CRS - # of rental unit technical evaluations conducted | Technical evaluation checklist | Community members are interested in accessing and using information about BBB techniques.
Output 2.1.1 Local technicians mobilized and trained | CRS - # of local technicians trained, disaggregated by sex | Attendance list/Training certificate | Sufficient skilled labor will be available in local communities that can be trained and engaged in the life of the program to support stronger, more environmentally conscious building practices.
Output 2.1.2 Targeted households attend Build Back Better (BBB) training | CRS - # of targeted community members participating in build-back-better skill-building sessions, disaggregated by sex and function (i.e. head of household or laborer) | Attendance list | Targeted households adopt and incoporate BBB techniques in shelter reconstruction/repair.
Output 2.1.3 Community members have printed information about BBB techniques | CRS - # of households receiving informational materials | Distribution report | Community members are interested in accessing and using information about BBB techniques.
IR 2.2 Targeted community members have access to DRR technical support to respond to emergencies | OFDA - # of settlements adopting DRR measures | Simulation exercise report | "Weather conditions will remain normal over the program duration (i.e no major natural disaster will occur). Security conditions in operating areas will remain stable and will not disrupt the reconstruction process."
Output 2.2.1 Targeted CCPC members attend two DRR meetings | CRS - # of CCPC members attending DRR meetings, disaggregated by sex | Attendance list | CCPC members will apply DRR measures to better plan for and respond to future emergencies.
Output 2.2.2 Targeted CCPC members participate in one DRR simulation exercise | CRS - # of CCPC members participating in DRR simulation exercise, disaggregated by sex | Attendance list
Note on A13: Nancy Doran:
Note on C13: Nancy Doran: I have changed the data source from CGI distribution sign-off sheet to Redrose database

## MEAL plan
Last Update | MEAL PLAN
2026-07-29
Performance Indicators |  |  |  | Data Collection |  |  | Analysis, use and reporting
Objective statements | Performance indicator statements | Targets | Indicator definition and unit of measurement | Data source(s) | Schedule/ frequency | Person Responsible for collecting the data | Method of analysis | Information use & Reporting Deadline | percentage | Beneficiary #
SO1 - Hurricane-affected households live in shelter that meets Sphere Standards | OFDA - # of households in the program area receiving emergency/transitional shelter pursuant to Sphere Project standards and FOG guidelines, disaggregated by shelter category Note: On base sur l'hypothese que chaque maison respecte la superficie minimum de 3.5 m2 par personne ce qui donne une superficie minimum de 21 m2 par menage. | 2237 | DEFINITIONS Sphere standards - 3.5 sqm per person FOG standards - Field Operation Guide METHOD OF CALCULATION Simple numeric count | Technical completion checklist | Upon completion of shelter reconstruction/ repair | CRS engineers | Comparison against target; observing differences in achievement between shelter categories | Quarterly and Final Narrative Reports; Discuss in monthly project meetings to adjust activities if progress is lower than expected; Include in end-of-project learning event | 70 | 3195 | 2236.5
| CRS - % of households that report residing in transitional shelter compliant with Sphere Standards by EOP | 70% | DEFINITION Sphere standards - same as above METHOD OF CALCULATION Numerator - # of respondents reporting residing in transitional shelter complying with Sphere Standards; denominator - total # of respondents | HH survey | End of Project | MEAL officer/MEAL data collectors | Comparison against target; observing differences in achievement between shelter categories | Final Narrative Report Include in end-of-project learning event | 90 | 3195 | 2875.5
IR 1.1 - Targeted households use critical shelter inputs needed to repair and rebuild their homes | OFDA - # of households in the program area receiving emergency/transitional shelter, disaggregated by shelter category | 3195 | DEFINITION Transitional Shelter - completed reconstructed/ repaired shelter METHOD OF CALCULATION Simple Numeric Count of shelters built, even those that do not comply with Sphere standards | Technical completion checklist | Upon completion of shelter reconstruction/ repair | CRS engineers | Comparison against target | Quarterly and Final Narrative Reports; Discuss in monthly project meetings to adjust activities if progress is lower than expected; Include in end-of-project learning event
| OFDA - % of total affected population in the program area receiving emergency/ transitional shelter assistance, by sex | 90% | DEFINITION Transitional Shelter - completed reconstructed/ repaired shelter Program area - Coteaux METHOD OF CALCULATION Numerator - # of affected population receiving assistance; denominator - total # of affected population | Beneficiary database / Government data | End of Project | MEAL Officer | Comparison against target | Final Narrative Report; Include in end-of-project learning event
| OFDA - Total USD amount and percentage of approved budget for emergency/transitional shelter spent on goods and services produced in the affected host country economy | 50% | METHOD OF CALCULATION (for %) Numerator - total USD amount spent on goods and services produced in the affected host country economy ; denominator - total approved budget for emergency/transitional shelter | Finance & procurement records | End of Project | CRS finance and procurement team | Comparison against target | Final Narrative Report
| CRS - % of households using salvaged materials effectively in the rebuild of their shelter | 70% | DEFINITION Effectively- as per training, in an environmentally conscious way METHOD OF CALCULATION Numerator - # of household using salvaged materials effectively in the rebuild of their shelter ; denominator - total # of beneficiary households | Technical completion checklist | Upon completion of shelter reconstruction/ repair | CRS engineers | Comparison against target | Quarterly and Final Narrative Reports; Discuss in monthly project meetings to adjust activities if progress is lower than expected; Include in end-of-project learning event
| CRS - % of targeted households that report using complementary shelter inputs purchased with their voucher in the rebuild of their shelter | 90% | METHOD OF CALCULATION Numerator - # of respondents reporting using the voucher they received for complementary shelter material inputs; denominator - total # of respondents | Post-distribution survey | 3 weeks after the distribution takes place | MEAL officer/MEAL data collectors | Comparison against target | Quarterly and Final Narrative Reports; Discuss in monthly project meetings to adjust activities if beneficiiaries are not using cash or voucher or are using cash or voucher for other purposes
Output 1.1.1 Targeted households access high-quality, in-kind CGI sheets | CRS - # of households receiving high-quality, in-kind CGI sheets | 3195 | DEFINITION High-quality - 28 gauge CGI sheets METHOD OF CALCULATION Simple numeric count | Redrose database | At each distribution | CRS Project Team | Comparison against target | Quarterly and Final Narrative Reports; Discuss in monthly project meetings to adjust activities if progress is lower than expected
Output 1.1.2 Targeted households salvage materials effectively in the rebuilding of their home | CRS - # of households receiving salvaging kits | 3195 | DEFINITION Salvaging kits - handsaws, smoothing planes, chisels, mallets, hammers, measuring tape and square METHOD OF CALCULATION Simple numeric count | Salvaging kit sign-off sheet | At each distribution | CRS Project Team | Comparison against target | Quarterly and Final Narrative Reports; Discuss in monthly project meetings to adjust activities if progress is lower than expected
| CRS - # of people attending training on best practices for salvaging, disaggregated by sex | 3550 | METHOD OF CALCULATION Simple numeric count | Attendance list | At each training | Trainers | Comparison against target; difference between comparison group (men and women) | Quarterly and Final Narrative Reports; Discuss in monthly project meetings to adjust activities if progress is lower than expected
Output 1.1.3 Targeted households access complementary shelter material inputs locally | CRS - # of targeted households receiving voucher for shelter reconstruction | 3195 | METHOD OF CALCULATION Simple numeric count | Voucher sign-off sheet | At each distribution | CRS Project Team | Comparison against target | Quarterly and Final Narrative Reports; Discuss in monthly project meetings to adjust activities if progress is lower than expected
Output 1.1.4 Labor groups (konbit) mobilized and supported to execute rebuilding activities | CRS - # of konbit members receiving complementary vouchers upon completion of their shelter | 3195 | METHOD OF CALCULATION Simple numeric count | Voucher sign-off sheet | Upon completion of shelter reconstruction/ repair | CRS Project Team | Comparison against target | Quarterly and Final Narrative Reports; Discuss in monthly project meetings to adjust activities if progress is lower than expected
SO2 - Targeted community members are better prepared for future disasters | OFDA - # of shelters incorporating DRR/BBB measures, disaggregated by shelter category | 2237 | DEFINITIONS DRR measures - as per BBB guidelines; at least 50% of recommended techniques are incorporated FOG standards - Field Operation Guide METHOD OF CALCULATION Simple numeric count | Technical completion checklist | Upon completion of shelter reconstruction/ repair | CRS engineers | Comparison against target; observing differences in achievement between shelter categories | Quarterly and Final Narrative Reports; Discuss in monthly project meetings to adjust activities if progress is lower than expected; Include in end-of-project learning event
| CRS - % of CCPC members report feeling better prepared for emergencies | 90% | DEFINITIONS Better prepared - compared to pre-Matthew situation Emergencies - natural disasters METHOD OF CALCULATION Numerator - # of CCPC members who report feeling better prepared for emergencies; Denominator - total # of CCPC members interviewed | CCPC survey | End of Project | MEAL Officer/MEAL data collectors | Comparison against target | Final Narrative Report Include in end-of-project learning event
IR 2.1 Targeted households have adequate advice and technical support to rebuild safely | CRS - % of targeted households applying techniques from build-back-better training in the repair/rebuild of their home, disaggregated by shelter category | 80% | DEFINITION Applying techniques - as per BBB guidelines; at least 50% of recommended techniques are applied METHOD OF CALCULATION Numerator - # of households applying techniques from BBB training in the repair/rebuild of their home; denominator - total # of beneficiary households | Technical completion checklist | Upon completion of shelter reconstruction/ repair | CRS engineers | Comparison against target; observing differences in achievement between shelter categories | Quarterly and Final Narrative Reports; Discuss in monthly project meetings to adjust activities if progress is lower than expected; Include in end-of-project learning event
| OFDA - % of people retaining shelter DRR/BBB knowledge two months after training, by sex and function (i.e head of households or laborer) | 80% | DEFINITION DRR knowledge- as per training curriculum METHOD OF CALCULATION Numerator - # of household retaining shelter DRR knowledge; denominator - total # of beneficiaries interviewed | BBB training survey | Two months after training | MEAL Officer/MEAL data collectors | Comparison against target; observing differences in achievement between comparison groups | Quarterly and Final Narrative Reports; Discuss in monthly project meetings to adjust activities if progress is lower than expected; Include in end-of-project learning event
IR 1.2 -Targeted IDP’s in Collective Centers receive adequate assistance and technical support towards accessing appropriate housing solutions | 1.2.1.CRS - % of households receiving rental subsidies renewing a house rental at the end of their rental year. Note: Au cours de l'implementation du projet, on ne dispose pas de donnees pour repondre a cet indicateur. |  | DEFINITION Applying techniques - as per BBB guidelines; at least 4 BBB techniques are applied METHOD OF CALCULATION Numerator - # of households receiving rental subsidies renewing a house rental; Denominator - total # of beneficiary households | Cash grant sign-off sheet | End of Project | MEAL officer | Comparison against target; observing differences in achievement between comparison groups | #REF!
Output 1.2.1 IDP’s receive rental subsidies | 1.2.1.1.CRS - % and # of targeted households receiving rental subsidies for one year, disaggregated by sex | 100% | METHOD OF CALCULATION Simple numeric count ; Numerator-# of households receiving rental subsidies for one year; Denominator- total # of beneficiary households | Cash grant sign-off sheet | After evaluation of rental unit | MEAL officer | Comparison against target; difference between comparison group (men and women) | Quarterly and Final Narrative Reports; Discuss in monthly project meetings to adjust activities if progress is lower than expected
| 1.2.1.2.CRS - % of targeted households receiving a relocation stipend, disaggregated by sex | 90% | METHOD OF CALCULATION Numerator - # of households receiving a relocation stipend; Denominator - total # of beneficiary households | Cash grant sign-off sheet | After evaluation of rental unit | MEAL officer | Comparison against target; difference between comparison group (men and women) | Quarterly and Final Narrative Reports; Discuss in monthly project meetings to adjust activities if progress is lower than expected
| 1.2.1.3.CRS - % of targeted households receiving a bonus stipend at the three month's mark, disaggregated by sex | 90% | METHOD OF CALCULATION Numerator - # of households receiving a bonus stipend at he three month's mark; Denominator - total # of beneficiary households | Cash grant sign-off sheet | After evaluation of rental unit | MEAL officer | Comparison against target; difference between comparison group (men and women) | Quarterly and Final Narrative Reports; Discuss in monthly project meetings to adjust activities if progress is lower than expected
Output 1.2.2. Technical assistance and household inspection implemented | 1.2.2.1.CRS - # of legal consultation on land tenure successfully concluded by Fondation Haitienne for Affordable Housing. Note: On va se baser sur la methode de temoignage au cas ou la situation fonciere n'est pas claire. |  | METHOD OF CALCULATION Simple numeric count | Activity report | Every 3 months | MEAL officer | Comparison against target | Quarterly and Final Narrative Reports; Discuss in quarterly project meetings to adjust activities if progress is lower than expected
| 1.2.2.2.CRS - # of rental unit technical evaluations conducted | 300 | METHOD OF CALCULATION Simple numeric count | Technical evaluation checklist | CRS engineer site visit for each rental unit | CRS engineers | Comparison against target; difference between comparison group (men and women) | Quarterly and Final Narrative Reports; Discuss in monthly project meetings to adjust activities if progress is lower than expected
Output 2.1.1 Local technicians mobilized and trained | CRS - # of local technicians trained, disaggregated by sex | 10 | METHOD OF CALCULATION Simple numeric count | Attendance list/Training certificate | At each training | Trainers | Comparison against target; difference between comparison group (men and women) | Quarterly and Final Narrative Reports; Discuss in monthly project meetings to adjust activities if progress is lower than expected
Output 2.1.2 Targeted households attend Build Back Better (BBB) training | CRS - # of targeted community members participating in build-back-better skill-building sessions, disaggregated by sex and function (i.e. head of household or laborer) | 3550 | METHOD OF CALCULATION Simple numeric count | Attendance list | At each training | Trainers | Comparison against target; difference between comparison group (men and women) | Quarterly and Final Narrative Reports; Discuss in monthly project meetings to adjust activities if progress is lower than expected
Output 2.1.3 Community members have printed information about BBB techniques | CRS - # of households receiving informational materials | 3550 | METHOD OF CALCULATION Simple numeric count | Distribution report | After distribution takes place | CRS Project Team | Comparison against target | Quarterly and Final Narrative Reports; Discuss in monthly project meetings to adjust activities if progress is lower than expected
IR 2.2 Targeted community members have access to DRR technical support to respond to emergencies | OFDA - # of settlements adopting DRR measures | 1 | DEFINITION Settlements - Les Coteaux Adopting - successful completion of simulation exercise by CCPC members METHOD OF CALCULATION Simple numeric count | Simulation exercise report | After simulation exercise takes place | CRS Project Team | Comparison against target | Final Narrative Report Include in end-of-project learning event
Output 2.2.1 Targeted CCPC members attend two DRR meetings | CRS - # of CCPC members attending DRR meetings, disaggregated by sex | 30 | METHOD OF CALCULATION Simple numeric count | Attendance list | At each meeting | CRS Project Team | Comparison against target; difference between comparison group (men and women) | Quarterly and Final Narrative Reports; Discuss in quarterly project meetings to adjust activities if progress is lower than expected
Output 2.2.2 Targeted CCPC members participate in one DRR simulation exercise | CRS - # of CCPC members participating in DRR simulation exercise, disaggregated by sex | 30 | METHOD OF CALCULATION Simple numeric count | Attendance list | At the simulation exercise | CRS Project Team | Comparison against target; difference between comparison group (men and women) | Quarterly and Final Narrative Reports; Discuss in quarterly project meetings to adjust activities if progress is lower than expected
Note on B22: Nancy Doran: this line is not possible to verify. The project is only 1 month long.
Note on E21: Nancy Doran: This cannot be the same tool as the one used for B22
Note on E23: Nancy Doran: This tool cannot be the same. There should be a sign off sheet.

## IPTT
Last Updated - April 24, 2017 |  | Indicator Performance Tracking Table (IPTT)
By - ND
Last Updated | Indicator Performance Tracking Table (IPTT)
2026-07-29
By - LM
INDICATORS | Tool | TOTAL Planned in First (Proposal) | TOTAL planned (revised) | December 2016 |  | January 2017 |  | February 2017 |  | March 2017 |  | April 2017 |  | May 2017 |  | June 2017 |  | July 2017 |  | August 2017 |  | September 2017 |  | October 2017 |  | November 2017 |  | December 2017 |  | January 2018 |  | February 2018 |  | March 2018 |  | April 2018 |  | May 2018 |  | TOTAL # Accomplished | TOTAL % Accomplished |  | Comments
|  |  |  | Planned | Accomplished | Planned | Accomplished | Planned | Accomplished | Planned | Accomplished | Planned | Accomplished | Planned | Accomplished | Planned | Accomplished | Planned | Accomplished | Planned | Accomplished | Planned | Accomplished | Planned | Accomplished | Planned | Accomplished | Planned | Accomplished | Planned | Accomplished | Planned | Accomplished | Planned | Accomplished | Planned | Accomplished | Planned | Accomplished |  |  | Comments (5/30/18)
SO1 - Hurricane-affected households live in shelter that meets Sphere Standards
OFDA - # of households in the program area receiving emergency/transitional shelter pursuant to Sphere Project standards and FOG guidelines, disaggregated by shelter category Note: On base sur l'hypothese que chaque maison respecte la superficie minimum de 3.5 m2 par personne ce qui donne une superficie minimum de 21 m2 par menage. | Technical completion checklist | 2237 | 1400 | 0 | 0 | 5 | 3 | 20 | 0 | 25 | 24 | 350 | 34 | 400 | 326 | 400 | 107 | 400 | 311 | 400 | 331 | 25 | 310 | 0 | 275 | 0 | 72 | 0 | 11 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 | 66 | 1870 | 133.6% |  | Completed
CRS - % of households that report residing in transitional shelter compliant with Sphere Standards by EOP | HH survey | 70% | 70% | [35 empty] | 70% | 70% | NA |  | Completed. Need Percentages
IR 1.1 - Targeted households use critical shelter inputs needed to repair and rebuild their homes
OFDA - # of households in the program area receiving emergency/transitional shelter, disaggregated by shelter category | Technical completion checklist | 3195 | 2000 | 0 | 0 | 5 | 3 | 20 | 0 | 25 | 24 | 350 | 34 | 400 | 326 | 400 | 107 | 400 | 323 | 400 | 337 | 25 | 311 | 0 | 277 | 0 | 72 | 0 | 12 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 83 | 1909 | 95.45% | 83 TCL ont ete remplis au cours du mois de mai 2018 pour la phase I du projet | Why are we only at 1818?
OFDA - % of total affected population in the program area receiving emergency/ transitional shelter assistance, by sex | Beneficiary database / Government data | 90% | 57% | [22 empty] | 57% | [13 empty] | 44.81% | NA |  | Completed: Total Number of individauls in the targeted Area: 21,302 (4,621 HH). Total number of beneficiaries to receive Transitional Shelter Assistance: 10,000 (2000 HH) | Total Number of Individuals Affected in the Targeted Area: 21,302 (4,621 households)
OFDA - Total USD amount and percentage of approved budget for emergency/transitional shelter spent on goods and services produced in the affected host country economy | Finance & procurement records | 50% | 50% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | [10 empty] | 0% | NA |  | To be completed at the end of the project.This should include our technicians, doors and windows. | Total Number of Direct Beneficiaries Targeted: 16,500 (3,300 households)
CRS - % of households using salvaged materials effectively in the rebuild of their shelter | Technical completion checklist | 70% | 70% | 0% | 0% | 0.3571% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 20% | 7.3% | 10% | 12.15% | 10% | 15.25% | 10% | 22.75% | 10% | 13.85% | 10% | 13.7% | 0% | 3.6% |  | 0.15% |  | 0% |  | 0% |  | 0% |  | 0% |  | 3.3% | 92.05% | NA |  | Completed: We started a pilote zone on February with 5 beneficiaries to get experiences and understand the challenges. | Total Number of Indirect Beneficiaries Targeted: N/A - 100% directly targeted
CRS - % of targeted households that report using complementary shelter inputs purchased with their voucher in the rebuild of their shelter | Post-distribution survey | 90% | 90% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 90% | 0% | 90% | 100% | 90% | 98% | 90% | 87% | 90% | 0% | 90% | 79.01% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0% |  | 0% |  | 91% | NA |  | Completed: The voucher distribution started on March. PDS is an ongoing activity | Total Number of IDP Beneficiaries Targeted: 1500 (300 households)
CRS - # of households receiving high-quality, in-kind CGI sheets | Redrose database | 3195 | 2000 | 0 | 0 | 5 | 5 | 20 | 0 | 25 | 131 | 400 | 266 | 400 | 264 | 400 | 140 | 400 | 279 | 400 | 441 | 25 | 222 | 125 | 120 | 0 | 5 | na | na | na | na | na | na | na | na | na | na | na | na | 1873 | 93.65% |  | Completed: This number should be closer to 2000.
CRS - # of households receiving salvaging kits | Salvaging kit sign-off sheet | 3195 | 2000 | 0 | 0 | 0 | 0 | 20 | 25 | 25 | 352 | 400 | 477 | 400 | 133 | 400 | 360 | 400 | 14 | 400 | 523 | 25 | 118 | na | na | na | na | na | na | na | na | na | na | na | na | na | na | na | na | 2002 | 100.1% |  | Completed: tools in the tool kits were reduced to provide construction tools only to reach more families with needed inputs to purchase quality building materials.
CRS - # of people attending training on best practices for salvaging, disaggregated by sex | Attendance list | 3550 | 2000 | 0 | 0 |  | 0 | 20 | 25 | 25 | 352 | 400 | 477 | 400 | 133 | 400 | 360 | 400 | 14 | 400 | 523 | 25 | 118 | na | na | na | na | na | na | na | na | na | na | na | na | na | na | na | na | 2002 | 100.1% |  | Completed
CRS - # of targeted households receiving voucher for shelter reconstruction | Voucher sign-off sheet | 3195 | 2000 | 0 | 0 | 0 | 0 | 20 | 25 | 240 | 352 | 480 | 477 | 480 | 133 | 480 | 360 | 320 | 14 | 0 | 523 | 0 | 118 | na | na | na | na | na | na | na | na | na | na | na | na | na | na | na | na | 2002 | 100.1% |  | Completed: The voucher distribution started on March because the voucher system was set up at the end of February.
CRS - # of konbit members receiving complementary vouchers upon completion of their shelter | Voucher sign-off sheet | 3195 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | na | na |  | Complete: Through the initial program design, a need to increase the construcion materials amounts for the beneficiaries was identified. CRS made the decision to remove the bonus and add this amount to the construction material voucher. To encourage quality construction, CRS increase the amount of BoQ's required to acquire all the material allowing for closer monitoring and evaluation. As well, local technicians could only be paid upon successful completion of services. |  | The beneficiaries received one voucher with the full package according to his/her specific category.
#REF! | Cash for Rent
Output 1.2.2. Technical assistance and household inspection implemented
1.2.2.1.CRS - # of legal consultation on land tenure successfully concluded by Fondation Haitienne for Affordable Housing. Note: On va se baser sur la methode de temoignage au cas ou la situation fonciere n'est pas claire. | Activity report | na | na | na | na | na | na | na | na | na | na | na | na | na | na | na | na | na | na | na | na | na | na | na | na | na | na | na | na | na | na | na | na | na | na | na | na | na | na | na | NA | CRS will be using a form of temoinage to determine the property ownership if ownership is in question. | Phase 2
1.2.2.2.CRS - # of rental unit technical evaluations conducted | Technical evaluation checklist | na | 300 | na | na | na | na | na | na | na | na | na | na | na | na | na | na | na | na | na | na | na | na | na | na | 25 |  | 100 |  | 100 |  | 75 |  | 0 |  | 0 |  | 0 |  | 300 | 100% |  | Phase 2
SO2 - Targeted community members are better prepared for future disasters
OFDA - # of shelters incorporating DRR/BBB measures, disaggregated by shelter category | Technical completion checklist | 2237 | 1400 | 0 | 0 | 5 | 3 | 20 | 0 | 25 | 24 | 350 | 34 | 400 | 326 | 400 | 107 | 400 | 315 | 400 | 331 | 25 | 271 | 0 | 275 | 0 | 72 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1761 | 125.8% |  | Completed
CRS - % of CCPC members report feeling better prepared for emergencies | CCPC survey | 90% | 90% | [22 empty] | 90% | [6 empty] | 90% | [6 empty] | 90% | NA |  | Activities have been completed the survey is to be performed and this indicator to be closed out. (20180202)
IR 2.1 Targeted households have adequate advice and technical support to rebuild safely
CRS - % of targeted households applying techniques from build-back-better training in the repair/rebuild of their home, disaggregated by shelter category | Technical completion checklist | 80% | 80% | 0% | 0% | 0.3125% | 0.1875% | 0% | 0% | 0% | 0% | 0% | 0% | 22% | 9.312% | 25% | 15.38% | 25% | 19.12% | 25% | 28.5% | 1.562% | 16.94% | 0% | 17.19% | 0% | 4.5% | 0% | 0.1875% | 0% | 0% | 0% |  | 0% |  | 0% |  | 0% |  | 111.3% | NA |  | Completed
OFDA - % of people retaining shelter DRR/BBB knowledge two months after training, by sex and function (i.e head of households or laborer) | BBB training survey | 80% | 80% | 0% | 0% | 0.3125% | 0.1875% | 0% | 0 | 0% | 0% | 15% | 20.83% | 15% | 20.83% | 15% | 20.83% | 15% | 20.83% | 15% | 20.83% | 5% | 20.62% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0% |  | 0% |  | 0% |  | 125% | NA |  | Completed: The BBS survey is completed. We performed a sample survey of 600 families
CRS - # of local technicians trained, disaggregated by sex | BBS/ attendees list | 10 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42 | 22 | 0 | 0 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 79 | 197.5% |  | Completed: CRS has identified a deficit of BBS technicians in certain inaccessible zones. Thus, we plan to train an additional BBS training course for 22 additional local technicians geared to inhabitants in these zones. The training started on April 25, 2017. 58 Techniciens ont suivi des séances de formation pendant 10 jours allant de la période du 27 septembre au 07 décembre 2017.
CRS - # of targeted community members participating in build-back-better skill-building sessions, disaggregated by sex and function (i.e. head of household or laborer) | Attendance list | 3550 | 2000 | 0 | 0 | 5 | 0 | 20 | 25 | 240 | 352 | 480 | 477 | 480 | 133 | 480 | 360 | 320 | 14 | 0 | 523 | 0 | 118 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 2002 | 100.1% | Sur le systeme Redrose, le projet a deja oriente 2000 menages sur les thematiques de BBS. Mais, il y a un ecart de 308 menages sur l'IPTT, donc on ajoute cette quantite au mois de septembre. | Completed
CRS - # of households receiving informational materials | Distribution report | 3550 | 2000 | 0 | 0 | 0 | 0 | 20 | 25 | 240 | 352 | 480 | 477 | 480 | 133 | 480 | 360 | 320 | 14 | 0 | 523 | 0 | 118 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 2002 | 100.1% | Sur le systeme Redrose, le projet a deja distribue 2000 flyers aux 2000 menages. Mais, il y a un ecart de 308 menages sur l'IPTT, donc on ajoute cette quantite au mois de septembre. | Completed: The informational flyers have been produced at the end of February 2017
IR 2.2 Targeted community members have access to DRR technical support to respond to emergencies
OFDA - # of settlements adopting DRR measures | Simulation exercise report | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 1 | 100% |  | Completed
CRS - # of CCPC members attending DRR meetings, disaggregated by sex | Attendance list | 30 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 25 | 0 | 25 | 30 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67 | 223.3% |  | NOT COMPLETED: There were two different sessions. There was a work shop with the CPC of Coteaux on the contengency plan on May 26-27, 2017. 67 is duplicating the numbers.
CRS - # of CCPC members participating in DRR simulation exercise, disaggregated by sex | Attendance list | 30 | 30 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 17 | 56.67% |  | Completed
PHASE 2
IR 1.1 - Targeted households use critical shelter inputs needed to repair and rebuild their homes
CRS - % of targeted households that report using complementary shelter inputs purchased with their voucher in the rebuild of their shelter | Post-distribution survey | na | 70% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 10% |  | 30% | 0 | 30% |  | 30% | 100% | 0 |  | 100% |  |  | Phase 2
# of households in the program area who received equipment (inputs) to build the partition of their home | Technical completion checklist | na | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 0 | 300 | 0 | 300 | 17 | 300 | 108 | 0 | 407 | 0 | 451 | 983 | NA |  | Phase 2
CRS - # of targeted households receiving voucher for shelter reconstruction | Voucher sign-off sheet | na | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 72 | 300 | 312 | 300 | 289 | 300 | 237 | 0 | 90 | 0 | 0 | 1000 | NA |  | Phase 2
IR 1.2 -Targeted IDP’s in Collective Centers receive adequate assistance and technical support towards accessing appropriate housing solutions
1.2.1.CRS - % of households receiving rental subsidies renewing a house rental at the end of their rental year. Note: Au cours de l'implementation du projet, on ne dispose pas de donnees pour repondre a cet indicateur. | Cash grant sign-off sheet | na | na | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | na | na |  | Not Complete: This indicator is not possible to measure. The CRS Cash for Rent Program is only 6 months long.
Output 1.2.1 IDP’s receive rental subsidies
1.2.1.CRS - % of households receiving rental subsidies renewing a house rental at the end of their rental year. Note: Au cours de l'implementation du projet, on ne dispose pas de donnees pour repondre a cet indicateur. | Cash grant sign-off sheet | na | na | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | na | na |  | Not Complete: This indicator is not possible to measure. The CRS Cash for Rent Program is only 6 months long.
1.2.1.1.CRS - % and # of targeted households receiving rental subsidies for one year, disaggregated by sex | Cash grant sign-off sheet | na | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | na | na |  | Phase 2: This indicator is not possible as the Cash for Rent project only extends 6 months
1.2.1.2.CRS - % of targeted households receiving a relocation stipend, disaggregated by sex | Cash grant sign-off sheet | na | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 0 | 100 | 101 | 100 | 0 |  | 97 |  | 65 |  | 25 |  | 0 | 288
1.2.1.3.CRS - % of targeted households receiving a bonus stipend at the three month's mark, disaggregated by sex | Cash grant sign-off sheet | na | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 100 | 0 | 100 | 0 | 75 | 101 | 75 | 94 | 0 | 68 | 0 | 25 | 288
IR 2.1 Targeted households have adequate advice and technical support to rebuild safely
CRS - # of local technicians trained, disaggregated by sex | Attendance list/Training certificate | na | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 52 | 0 | 0 | 0 | 57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 109
Note on A12: Nancy Doran: Est ce que c'est necessaire a noter les different category?
Note on A30: Nancy Doran: Do we need to discern the categories?
Note on A33: Nancy Doran: To be determined by the CLO attendance lists. Katrice is to do the follow up with Finance
Note on A36: Nancy Doran: Laneau to complete this report.
Note on A37: Nancy Doran: Laneau a faire le suivi
Note on A38: Nancy Doran: Laneau a faire le suivi
Note on A45: Nancy Doran: A VERIFIER AVEC KEMAS ET RHODE.
Note on A47: Nancy Doran: A VERIFIER AVEC KEMAS ET RHODE.
Note on B18: Nancy Doran: To be verified with Rosulme. All sign off sheets to be collected and filed.
Note on B24: Nancy Doran: WE ARE NOT PROVIDING THIS SERVICE.
Note on AN10: Nancy Doran: verifiez ce numero
Note on AO9: Nancy Doran: verifiez ce numero
Note on AO37: Nancy Doran: Numbers have been duplicated.
Note on AP6: Nancy Doran: Do we need this column? It is not in the one created by Lea.
Note on AP10: Nancy Doran: Il faut faire une

## DIP-Cash for Rent
CATHOLIC RELIEF SERVICES
CASH FOR RENT
Detailed Implementation Plan 2017
| FY 2017-2018 |  |  |  | FY 2017-2018
| Sept | oct. | nov. | dec. | Q1 | Q2 | Q3 | Q4
BUT : Aider 300 familles déplacées dans des centres collectifs à se rélocaliser dans des logements décents et sécuritaires.
Objectifs strategiques 1: Targeted IDPs have access to adequate shelter
Resultats intermediaires: Targeted IDP’s in Collective Centers receive adequate assistance and technical support towards accessing appropriate housing solutions
Outputs
Output 1: IDP’s receive rental subsidies and relocation assistance funds
Identify geographical Target Areas
Rental Market Studies
IDP Registration
Project introduction to Mayors
MOU with the Mayor with a rental rate agreed upon
Mayor validation of IOM beneficiary list
Beneficiary Orientation
Beneficiaires locate house to rent
Output 2: Rental unit inspection is performed by project engineers
Rental Unit visit verification and contract signing
Payments
Follow-up visits
Beneficiary Assessment Survey
Property Owner Assessment Survey
Collective Center Assessment Survey
Beneficiary Bonus Payment
IDP's sites Close out letter (Signed by the Mayor)
Close-out surveys
Household
Collective Center and Camps
Landlords

## MEAL Calendar
Last Updated - 9/14/17 | MEAL CALENDAR
By - ND
Activities/Reports | Person Responsible For Timely Completion | Dec 2016 |  | Jan 2017 |  | Feb 2017 |  | Mar 2017 |  | Apr 2017 |  | May 2017 |  | June 2017 |  | Jul 2017 |  | Aug 2017 |  | Sept 2017 |  | Oct 2017 |  | Nov 2017 |  | Dec 2017 |  | Janv 2018 |  | Feb 2018 |  | Mar 2018 |  | Apr 2018 |  | May 2018
|  | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2
Major Data Collection Activities
Registration & Assessment
Tool Development | MEAL TA
Data Collection | MEAL Officer
Development of technical completion checklist
Tool Development | Shelter PM/Engineers
Data Collection | Shelter Engineers
PDM survey
Tool Development | MEAL TA & MEAL Officer
Data Collection | MEAL Officer & volunteers
BBB training survey
Tool Development | Shelter PM/MEAL Officer
Data Collection | MEAL Officer & volunteers
HH survey
Tool Development | MEAL Officer
Data Collection | MEAL Officer & volunteers
CCPC survey
Tool Development | Shelter PM/MEAL Officer
Data Collection | MEAL Officer & volunteers
P2: Selection Beneficiare survey
Tool Development | Shelter PM/MEAL Officer
Data Collection | MEAL Officer & volunteers
P2: TCL
Tool Development | Shelter PM/MEAL Officer
Data Collection | MEAL Officer & volunteers
P2: PDM
Tool Development | Shelter PM/MEAL Officer
Data Collection | MEAL Officer & volunteers
P2: HH Survey
Tool Development | Shelter PM/MEAL Officer
Data Collection | MEAL Officer & volunteers
P2/CFR: HH Survey
Tool Development | Shelter PM/MEAL Officer
Data Collection | MEAL Officer & volunteers
P2/CFR: Landlord Survey
Tool Development | Shelter PM/MEAL Officer
Data Collection | MEAL Officer & volunteers
P2/CFR: Collective Center Survey
Tool Development | Shelter PM/MEAL Officer
Data Collection | MEAL Officer & volunteers
Reporting
IDP’s receive rental subsidies and relocation assistance funds
Identify geographical Target Areas
Rental Market Studies | MEAL Officer
IDP Registration | IOM
Project introduction to Mayors | Cash for Rent Officer
MOU with the Mayor with a rental rate agreed upon | Cash for Rent Officer
Mayor validation of IOM beneficiary list | Cash for Rent Officer
Beneficiary Orientation | Cash for Rent Officer
Beneficiaires locate house to rent | Beneficiary
Rental unit inspection is performed by project engineers
Rental Unit visit verification and contract signing (all in the same day) | Engineers /Cash for Rent Officer
Payments | PM,finance
Follow-up visits | MEAL Officer
Beneficiary Assessment Survey | MEAL Officer
Property Owner Assessment Survey | MEAL Officer
Collective Center Assessment Survey | MEAL Officer
Beneficiary Bonus Payment | MEAL Officer
IDP's sites Close out letter (Signed by the Mayor) | CRS TEAM / Mayor

## stepbystep_Rentals
| STEPS | 1 | 2 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 7
RENTALS
WHAT? | DESCRIPTION OF THE PROCESS | REGISTRATION OF IDP'S | BENEFICIARY SELECTION AND VALIDATION | RENTAL BENEFICIARY ORIENTATION & PROTECTION TRAINING | SELECT RENTAL PROPERTIES | AGREEMENT BETWEEN LANDLORD AND BENEFICIARY | LANDLORD PAYMENT TRANCHE 1 | CASH GRANT FOR RELOCATION | 4-8 week Follow up Visit | BONUS CASH GRANT FOR BENEFICIARY 2 MONTH RENTAL | 13 Month Beneficiary Survey
WHO? | RESPONSIBLE | IOM (DTM) AND MEAL | CLO & MAYOR | MEAL,CLO,PROTECTION OFFICER | Beneficiary with CRS Validation | PM,Mayor,Landlord,Beneficiary | PM | PM | Engineer, MEAL |  | MEAL
HOW? | MEANS OF VERIFICATION | CRS IDP survey/IOM registration/DPC card/Photo | Beneficiary list approved and signed by the Mayor | Attendance List (iForm) | 1. Inspection Checklist 2. Land tenure docs 3. Certification from Mayor | MOU between landlord and beneficiary | Finance | Finance | Beneficiary Survey, | Finance | Beneficiary Survey,
WHEN? | HOW MUCH TIME DOES IT TAKE TO COMPLETE THIS STEP | 1 week | 1 day | 1 day | 1 wk | 1 | 3 wks | 3 wks |  | 3 wks | 1 wk
Note on E5: Hrybyk, Anna: iForm needs to be developed for this
Note on G5: Hrybyk, Anna: iForm needs to be developed for this
Note on I5: Hrybyk, Anna: 1. iForm should be developed for this 2 & 3 should be in beneficiary file