Shelter/NFI Cluster Coordination Meeting, Dahuk

Location: 		BRHA Conference Room, Dahuk

Date and time: 		5th November 2019

Attendance:	ACTED, BCF, BRHA, Care International, Caritas Czech Republic, CCCM Cluster, Harikar, ICRS, OCHA, PWJ, Protection Cluster, REACH Initiative, SNFI Cluster, OCHA, Ster NGO, UNHCR, War Child UK, WFP.

| Agenda Item | Key Points | Actions |
| --- | --- | --- |
| General SNFI Update | - SNFI Cluster has access to sandbags for insulating MoMD tents from leaking. We would like to make these available to BRHA to support camps’ preparation for the rain and winter season. It will be perfect if sandbag placing is paired with MoMD tent replacement, for maximum effect. | - BRHA to communicate to SNFI Cluster how many tents in which camps will need sandbags. |
| Winterization | - SNFI Cluster has issued Winter Report #1 outlining the winter plan and the capacity of partners to cover seasonal needs. Partners in Dohuk are coordinating to avoid duplication. - CRS has funding available to provide winter support (240,000 IQD per family) to 3,000 families living out of camp in Dohuk. - UNHCR will cover with cash for winter (240,000 IQD) all IDPs in camps after enrolling them in ASSIST (UNHCR vulnerability tool). As for out of camps, 4,883 IDP HHs have already started cashing out. - Kerosene: MOMD distribution (40 liters) started 18 October. Dawodiya , Berseve 1 & 2, Darkar, Chammishku, Rwanga, Khanke, Bajidkandala, Kabarto 1 and Shekhan are covered. The remaining camps (Essian, Mamrashan, Shariya, Kabarto 2, Mamilian and Garmawa) to be covered next week. MOMD to start the second cycle of distribution of 100 litres in the coming weeks. The plan is to provide 200 litres per HH, distributed in three cycles. | - Other partners to inform BRHA and SNFI Cluster of any planned winter activities. - SNFI Cluster will continue collecting monthly information on kerosene distribution in camps, with support from CMs and BRHA. Kobo collection tool to be found here: - https://enketo.unhcr.org/x/#uBtpQ8kD |
| CAMPS | - MoMD tent replacement: BRHA has conducted a meeting with GIZ and discussed the plan for the tent replacement in all MOMD camps. GIZ has agreed to support the tent transportation and replacement through Cash for Work. The old tents will be disposed by Municipality of each district. So far tents received in Essian (1862), Chamishku (2000), Kabarto 1 (3000), Kabarto 2 (500), and Mamilian (229). - AFAD tent replacement: tents from the supplier should start arriving after 11 Nov, replacement to start first with Shariya, then Bersive 1. - UNHCR tent replacement: UNHCR has replaced 1,366 tents in UNHCR camps. | - BRHA to send to UNHCR a list of HHs who were not present in camps during replacement. |
| AOB | Contact: Petya Boevska is the SNFI Sub-National Cluster Coordinator for KRI. She can be reached at coord3.iraq@sheltercluster.org OR 0771 994 5692 |  |

Next meeting:		3rd December 2019