Shelter/NFI Cluster Coordination Meeting, Erbil

Location: 		EJCC Meeting Room, Erbil

Date and time: 		10am, 28th Oct 2019

Attendance:		UNHCR, EJCC, BCF, PWJ and SNFI Cluster Coordinator KR-I

| Agenda Item | Key Points | Actions |
| --- | --- | --- |
| Winterization | - UNHCR is covering all ASSIST-registered people in camps and 4,000 IDPs out of camps with cash for winter (240,000 IQD or USD 200). Transfers to start by Qandil in November through Asiacell or Zain. - Kerosene distribution is the responsibility of the Government of Iraq (GoI). Humanitarian partners will not be distributing kerosene at household level. - Winter items and clothing to be distributed by MoMD – no clear plans have been shared. | - IDPs can contact the Iraqi Information Center (IIC) in case of complaints at: Toll Free Ph: 80069999 - SNFI Cluster to continue national level advocacy with MoO and MoMD on distribution. |
| Camps | - Khazer M1: BCF has replaced 500 MoMD tents, the rest will be replaced as soon as budget available and WASH facilities are relocated. Tents are lower quality than previously installed. - Tent replacement – UNHCR will replace tents as damaged in UNHCR camps. - UNHCR-tented camps (U2, U3) need extra plastic sheeting to prevent leakage. - Caravanned and semi-constructed camps (Harshm and Baharka) need caravan maintenance and plastic sheeting for the leaking roofs. | - SNFI Cluster to see if stock of plastic sheeting is available for Partners. - PWJ to look into an assessment of caravan maintenance and open water channel needs. |
| SNFI Cluster Update | - Activity Info is the official platform for ALL humanitarian partners to report completed and planned activities, assessments and contingency plans. BCF and Qandil to report all UNHCR-funded activities as HRP. - Partners to report completed activities by 5th of every month for achievements in the previous month. Entries cannot be changed after the platform closes. | - For Activity Info support, contact Mohammed Faisal (Information Management Officer) at: im.iraq@sheltercluster.org |
| AOB | - Next meeting to be scheduled in December 2019 to get updates on winter plans - Petya Boevska (UNHCR) is the SNFI Sub-national Cluster Coordinator for KR-I) and could be reached @ 0771 994 5692 or coord3.iraq@sheltercluster.org. | Formal email informing partners about the meeting with date and time to be sent to partners. |