## Slide 1
http://sheltercluster.org/response/iraq
Ninewa Shelter & NFI Cluster Coordination Meeting
Agenda
Review of Pending Action Points from 09.25.19 Meeting
Update on Year-to-Date Achievements & Gaps
Key Issues – Updates from Partners by District
  Hamdaniya , Mosul, Sinjar, Tel Afar, Tilkaif
Winterization
IIC Complaints Focal Points
HNO/HRP Process Updates
AOB Sunday, 27 October 2019

## Slide 2: Review of 25 September Meeting
Review of Pending Action Points from 09.25 Meeting
  Partners to continue to update Activity Info databases, liaise with Shelter Cluster for any issues in reporting
  Shelter Cluster to circulate an email request for partners to share their focal points for any complaints

## Slide 3: Update on Achievements
SNFI Achievements Reported in Activity Info Jan-Sept 30
District | Shelter Target | NFI Target | Shelter Achievement | NFI Achievement
Hamdaniya | 13,326 people | 40,459 people | 17,829 (134%) | 33,805 (84%)
Mosul* | 156,605 people | 165,199 people | 16,776 (11%) | 48,654 (29%)
Sinjar | 6,710 people | 4,986 people | 1,865 (28%) | 12,852 (258%)
Tel Afar | 17,237 people | 16,476 people | 1,770 (10%) | 5,116 (31%)
Til Kaif | 4,209 people | 7,173 people | 3,977 (94%) | 1,312 (18%)

## Slide 4: Ninewa Updates by District
Hamdaniya
Partners | Sub-District | What | Targets | November Plans
Malteser International (through local church) | Qaraqosh town | Rehabilitation of Cat 2 & 3 Houses | ~100 HHs | Still in planning stages, exact number of houses TBD.
Malteser International (through local church) | Bahzani town | Rehabilitation of Cat 2 & 3 Houses | 30 HHs | Ongoing
Partners reporting in Activity Info: BCF, CNSF, Caritas Czech, Caritas Iraq, CRS, IOM, IRW, Malteser International, Mission East, MoMD, Samaritan’s Purse

## Slide 5: Ninewa Updates by District
Mosul
Partners | Sub-District | What | Targets | October Activities
Medair | West Mosul (Zinjili, 17 Tamouz, and Mushirfa) | War Damage Rehabs | 17 HHs | Rapid Security Assessment finalized for Mushirfa, Zinjili, and 17 Tamouz Conduct the WDS scoping Conduct SEVAT (TBC) Develop BoQs for WDS Cat-2
Partners reporting in Activity Info: BCF, CRS, HA, IOM, IRW, Malteser Int’l, NRC, RIRP, Samaritan’s Purse, UN-Habitat
UNDP (does not report in Activity Info, does report in the WDS Portal)

## Slide 6: Ninewa Updates by District
Sinjar
Partners | Sub-District | What | Targets | October Plans
Medair | Sinuni, Golat Village | NFI Distribution | 342 HHs | Completed September 16th: -UNHCR kits distributed to the remaining families -218 blankets, 42 cooking stoves, 51 Jerrycans, 345 Hygiene kits, 19 Female sanitary kits
IOM | Sinjar, Al Shamal, Markaz Sinjar | War Damage Rehabs Cat 2 & 3 | 300 HHs | 
Partners reporting in Activity Info: IOM, Mission East

## Slide 7: Ninewa Updates by District
Tal Afar
Partners | Sub-District or Town | What | Targets | November Plans
ACTED | Tal Afar | War Damage Rehabs, Cat 2 & 3 | 350 HHs | 
CRS | Telafar: Saad, Khadraa, Rabee, Taleea 1,2,3, Nidaa, Kifah Al-Jinubi, and Qadesiya neighborhoods | War Damage Rehabs, Cat 2 & 3 | 57 houses of 681 individuals | Continue monitoring the houses under repairs and support households who got first tranches
DRC | Ayadiyah town | War Damage Rehabs Cat 2 & 3 | 310 shelters | Assessments, particularly Tel Afar, Sinjar districts (additional 53 targeted this month)
DRC | Wanna, Ayadiyah villages, Zummar | SOK Distributions | (120 planned this month) | Assessments, particularly for new returnees
NRC | Rabeaa and Zumar Sub districts ( Villages and City Center) | War Damage-Rehabilitation of Category 2 through Cash for shelter modality | 260 HHs | Ongoing pre-assessments to finalize the areas of intervention and starting FGD and assessments in selected areas
Peace Winds Japan | Gir Kafir village, Zummer sub-district, | War Damage Rehabs, Cat 2 & 3 | 149 HHs | Construction to start in November
Partners reporting in Activity Info: ACTED, CRS, IOM, TDH-Lausanne

## Slide 8: Ninewa Updates by District
Til kaif
Partners | Sub-District | What | Targets | October Plans
Partners reporting in Activity Info: Caritas Iraq, Medair, Mission East

## Slide 9: Winterization
Currently 6 partners have shared their plans regarding winterization: CRS, IOM, IRW, Mission East, UNHCR, and UNICEF.
Any other partners planning winterization activities are requested to contact me immediately to coordinate their plans.
All partners are reminded that we do not and should not provide kerosene, as this is an MoMD activity.

## Slide 10: IIC Call Center Focal Points
The Iraq Information Center (formerly the IDP Call Center) has been forwarding complaints and requests for services to the Shelter Cluster
  We will refer these complaints to your organization, however, we want to clearly identify focal points for each organization to receive complaints. Focal points should ideally be someone in a supervisory capacity of programming, backed by an M&E staff or PSEA focal point
  For organizations that have hotlines, we would still like a clear focal point for complaints as hotlines are not always active and may cost complainants money
  SNFI Cluster will send an email request to partners to share focal points
  Partners are requested to share their complaint focal point by 31 October with Teri (coord2.Iraq@sheltercluster.org)

## Slide 11: HNO/HRP Process Update
We expect to target approximately 540,000 people, for approximately $53 million in our HRP appeal.
Focus will be primarily on Shelter compared to NFI.

## Slide 12: Any Other Business?
  Any points partners need assistance with or would like to raise for future meetings?

## Slide 13
THANK YOU