## Slide 1
http://sheltercluster.org/response/iraq
Ninewa Shelter & NFI Cluster Coordination Meeting
Agenda
Introduction of Avedis Baberian, incoming Ninewa Sub-National Shelter Cluster Coordinator
Key Issues – Partners to provide an update on their planned, ongoing, and completed interventions by district
SNFI Cluster to Share an Update on Gaps in Ninewa and planning for the end of the year
Update on Winterization
HRP 2020 Updates
AOB
Thursday, 28 November 2019

## Slide 2: Update on Achievements
SNFI Achievements Reported in Activity Info Jan-Oct 30
District | Shelter Target | NFI Target | Shelter Achievement | NFI Achievement
Hamdaniya | 13,326 | 40,459 | 19,295 (144%) +10% | 34,770 (86%) +2 %
Mosul* | 156,605 | 165,199 | 25,659 (16%) +6 % | 48,654 (29%) +0%
Sinjar | 6,710 | 4,986 | 1,865 (28%) +0% | 12,852 (258%) +0%
Tel Afar | 17,237 | 16,476 | 3,432(20%) +10% | 5,116 (31%) +0%
Til Kaif | 4,209 | 7,173 | 3,977 (94%) +0% | 1,312 (18%) +0%

## Slide 3: Ninewa Updates by Partner
CRS
Type of Intervention | Area of Intervention | Number of Beneficiaries (HH) | December Plans
Cash for repairs to War-Damaged Rehabilitation of CAT 1&2 – first and second Tranches | Telafar: Saad, Khadraa, Rabee, Taleea 1,2,3, Nidaa, Kifah Al-Jinubi, and Qadesiya neighborhoods | First tranches: 49 houses of 107 HH/ 522 individuals. Second tranches: 16 houses of 42 HH/248 individuals | Continue monitoring the houses under repairs and support households who got first tranches. Continue registration of the returnees with damaged houses in the previously targeted neighborhoods Start new registration in Mualemeen, Naser, Zahra, Wahda, and Kifah Al-Shemali neighborhoods

## Slide 4: Ninewa Updates by Partner
DRC
Type of Intervention | Area of Intervention | Number of Beneficiaries (HH) | December Plans
MSNA Assessment (HH survey, FGDs, KII) | Hatra Town (Al-Hadar), Hatra District | n/a | Shelter Response Planning
MSNA Assessment (HH survey, FGDs, KII) | Ba’aj Town, Ba’aj Town and surrounding villages | n/a | Shelter Response Planning
SEVAT & Technical assessments | Ayadiyah sub district, areas of high new returns | n/a | Writing BoQ for 140 DSU and 100 SOK
Market Assessments – cash for shelter | Ayadiyah sub district | n/a | Continued assessments, technical assessments

## Slide 5: Ninewa Updates by Partner
Malteser
Type of Intervention | Area of Intervention | Number of Beneficiaries (HH) | December Plans
War-Damage house rehabilitation of Category 2 to 3 | Qaraqosh Town | 108 HHs | Expected to start the rehabilitation work within December, 2019
War-Damage house rehabilitation of Category 2 to 3 | Bahzani Town | 30 HHs | Expected to start the rehabilitation work within December, 2019
War-Damage house rehabilitation of Category 2 to 3 | Qaraqosh Town | 108 HHs | Expected to start the rehabilitation work within December, 2019

## Slide 6: Ninewa Updates by Partner
NRC
Type of Intervention | Area of Intervention | Number of Beneficiaries (HH) | December Plans
War-Damage Rehabilitation of Category 2 /CASH | Mosul/Old city( Al-Ahmadia, Hamam Manqoosha, Nabi Jarjis and Al-Mshahada NBHs) | 18 Shelter/31 HHs assessed in Nabi Jarjis | Continue door to door assessment process.
War-Damage Rehabilitation of Category 2 /CASH | Sinjar (Barbarosh, Perzekre, Al-Qadisya, Al-Salam and Al-Taakhe NBHs) | n/a | Starting door to door assessment process.
War-Damage Rehabilitation of Category 2 /CASH | Baaj (Al-Risala, Al-Yarmook, Al-Qadsyia, Al-Thawra and Al-Askari NBHs) | n/a | Starting door to door assessment process.

## Slide 7: Ninewa Updates by Partner
UN Habitat
Type of intervention | Area of intervention | Number of beneficiaries (HHs) | Stage
Construction of low-cost housing units | Bab Sinjar, Mosul, Nineweh governorate | 840 | Continuation of ongoing construction of low-cost housing units
Rehabilitation of critical shelters Provision of rental subsidies | Fayda and Markaz Sumel sub-districts, Sumel District; and Markaz Zakho and Rizgari Sub-districts, Zakho District, Dohuk Governorate | 100 20 | SEVAT exercise planned through CCR
Facilitation of SEVAT exercise Distribution of NFI kits Distribution and installation of SOKs | Al-Garma, Al Saqlawiyah, and Markaz Fallujah Sub-districts, Fallujah District, Anbar Governorate | 1,000 1,000 1,000 | CFP advertised, in process Appointment of NGO IP and distribution of NFIs

## Slide 8: Ninewa Updates by Partner
UN Habitat
Type of intervention | Area of intervention | Number of beneficiaries (HHs) | Stage
Rehabilitation of damaged housing units | Mosul: Al Shiffaa and Sinjar: Al Shuhadaa, Rozh halat, Kirtik Weran Shar & Al Nasir | 147 in Mosul and 200 in Sinjar | Starting the 1st round of rehabilitation (81 units in Mosul and 125 in Sinjar).
Rehabilitation of: Damaged - housing units Public facilities Public open spaces | Mosul, Nineveh Governorate: Sikak, Matahin, Maghrib Heet, Anbar governorate: Hay Al-Baker Yathrib, Salahaddin governorate: Yathrib center and Al-Bohashima area | Housing: 150-200 hh per gov. Open spaces: Minimum 2,000 HH per gov. Public facilities: 1 per site | Rehabilitation of emergency health center in Yathrib Rehabilitation of Al-Nojoom school in Heet Rehabilitation of approx. 20 houses per area Rehabilitation Al-Yarmouk park boundary wall

## Slide 9: Winterization
Currently 8 partners have shared their plans regarding winterization: CRS, IOM, IRW, Mission East, UNHCR, and UNICEF, German Red Cross, DRC
Any other partners planning winterization activities are requested to contact me immediately to coordinate their plans.
All partners are reminded that we do not and should not provide kerosene, as this is an MoMD activity.

## Slide 10: Winterization
Situation In Camps
  Jad’ah1, 2, 4 & 5(Mosul), AAF and HTC (Falluja)
    No support reported currently, low needs reported.
  Other camps covered by UHNCR (Cash for Winter)
Situation Out of Camps
  Camp consolidation and closure of camps in Ninewa => population in critical shelter to be larger than identified when the latest MCNA VII (August 2019) and ILAIV(June 2019)
  Adapt planning to the ground conditions
  Vulnerability targeting when assessing populations for winter assistance.

## Slide 11: Winterization
  State Support
      The GoI has not shared any plans with humanitarian partners to indicate on appropriate heating and cooking fuel provision
      MoMD has not communicated plans for distribution of winter items and clothing for IDPs in and out of camp.

## Slide 12: HNO/HRP2020 Process Update
  Still under discussion
  Focus will be primarily on Shelter compared to NFI.
  HC requested to decrease the overall amount

## Slide 13: Any Other Business?
  Any points partners need assistance with or would like to raise for future meetings?

## Slide 14
  THANK YOU !!