Location:   IOM Office, Sulaymaniyah

Time:         10:00 – 11:00

Present:  IOM, JCCC, UNHCR, OCHA, Qandil and YAO.

Location:   IOM Meeting Room / Titanic

Time:         17 Oct 2019, @10:00 – 11:00

Agenda included:

- Winter Response Plans of Partners

- Remaining Needs and Gaps – MNCA VI and ILA IV

- Activity Info Reporting

- Update from SNFI Cluster – national level

- Emergency Planning for refugee preparedness – UNHCR

- Agency Updates

- AOB

Summary of Action Points:

| No. | Action points for the next meeting | Who: | Completed by When: |
| --- | --- | --- | --- |
| 1. | SNFI Cluster to share with JCC and CCCM technical specs for MoMD tents | SNFI Cluster Coordinator | 20 Oct, 2019 |
| 2. | Partners to request SNFI Cluster for any training needed at Sulaymaniyah level | ALL | 30 Oct, 2019 |
| 3. | Partners to coordinate refugee response preparedness actions with UNHCR | ALL partners | ongoing |

Minutes:

| Agenda Item | Key Points | Action points |
| --- | --- | --- |
| Follow-Up on Action Points | Pending action points are above for the next meeting |  |
| Discussion on winter plans in 2019 for SNFI | - So far only UNHCR has informed SNFI that they will be providing cash for winter to 3,192 IDP families in Sulaymaniyah governorate. The recommended amount from SNFI is 240,000 IQD (USD 200) per family. - Refugees: blanket winterization cash assistance for 2,130 families | Partners to inform of winter plans, if any. |
| Remaining Needs and Gaps | - In-camp targets have been covered more than 200%. - 0% coverage for out of camp populations, while MCNA VI shows that OoC IDPs in Sulaymaniyah governorate need cooking stove (17%), Kitchen Set (27%), Blankets (27%), Clothing (17%), Bedding (32%) and Mattresses/Mats (36%) - Additionally, there are 76 families living in critical shelter (Unfinished and Abandoned Buildings, Schools, Religious Buildings and Informal settings) – ILA IV - Activity Info – YAO and BCF (UNHCR-funded) are reporting. | Partners to focus efforts at out of Camp IDPs until the end of the year. SNFi Cluster to reach out to Iraqi Red Crescent to bring them to report activities in AI. |
| General Cluster Updates | - HNO: The people in need (PIN) for Sulaymaniyah governorate is estimated at 40,944 individuals in need of some shelter and/or NFI support. The targets for 2020 HRP will be set in November/December 2019. - SNFI Cluster has MoMD-type tents in tock in Erbil – proposal to replace all remaining MoMD tents in Ashti IDP. | JCC, SNFI and CCCM Clusters to coordinate on tent replacement ensure tents are in place before the winter season. |
| Emergency Planning for Refugees - UNHCR | - UNHCR is leading the preparedness planning for possible refugee influx from NES. They have capacity to assist 2,000 families in the initial stages. Proposed action is to support for people to settle mostly out of camps, or to re-open Barzinha or Surdesh. - Cash for rent will be the preferred assistance. UNHCR has no warehouse in Sulaymaniyah but Core Relief Items could be requested from Erbil, if needed. |  |
| Partner Updates | - UNHCR-YAO – NFI distributions in the camps are continuing, except for Surdesh, where humanitarian activities have finished on 31 July 2019. - IOM distributed basic NFI to 190 families that have been displaced since January 2019. No additional planned activities. - CCCM: discussions for the consolidation of Qoratu camp are ongoing. Intention surveys to be carried out by Protection to inform where people will go after the closure. Meeting with authorities: IDPs from Qurato to move to out of camp locations, area of origin or Tazade camp. | Partners to update their activities for the remaining of 2019 in Activity Info (4W template for planned activities) and Contingency template for emergency stock) |
| AOB | - Cristiana Cipollini is Focal Point for SNFI Cluster in Sulaymaniyah: cipolini@unhcr.org or 0772 6174005. - Rawaz Jalal Hama Ali (REACH) is co-chairing SNFI Cluster Sulaymaniyah: rawazj@reach-iraq.org or 0770 1201983. - Petya Boevska is the Sub-national SNFI Cluster Coordinator, based in Erbil and attending sub-national meetings: coord3.iraq@sheltercluster.org or by phone 0771 9945692. - Activity Info Reports are due from Partners on the 5th of every month. |  |