## Slide 1: Cash Programmes Lessons in Darfur Sudan
Implemented by Cluster partners
DRC and TGH

## Slide 2: Why Cash/Vouchers
The context:
  Markets are functional – support local economy
  People use cash – and accept it
  Injecting cash at local level contributes to boost local economy and local suppliers
  Saves cost of transporting in-kind food items – and time spent on procurement
  Restores some dignity to beneficiaries and allows flexibility
  Has been shown to ease the acceptance of newly arrived people among the communities

## Slide 3: DRC project in Nertiti, Jebel Mara, Darfur
Value vouchers most appropriate for Nertiti context
Beneficiary identification – involved local Sheikhs, Umdas, and DRC staff
Used cash programming for food support – to fill hunger gap in the 3 months before harvest for IDP HHs and vulnerable host community HHs
Value-based vouchers – beneficiaries free to choose the items from the available list
Value of voucher was SDG310 per HH per month – based on the MEB in Darfur (per WFP 2016)
Covered 4000HHs in Nertiti in 3 rounds of distribution
Vendors: Accepted bank transfers from Khartoum for payment – which reduced risk for DRC

## Slide 4: Successes

## Slide 5
All 4000HHs were able to receive and cash their vouchers - allowed flexibility in products so apart from food items they were also able to get soap and some household items
All of the HHs used their vouchers
Voucher Design: included a list of some basic commodities and their prices to ensure information and prevent under supplier by vendors– this, in the very first round of distribution, influenced beneficiaries to only go for the listed commodities.
PDM showed the food items they received helped them get through the lean period to the harvest period
Engagement of local traders boosted local economy

## Slide 6: Challenges
Establishing HH size: Not easy going by definition of people eating from the same pot
  Makes it difficult to tailor the voucher to HH size – all HHs receive the same amount initially
Vendors: First year: Initial discussions and agreement signed with 6 vendors – only 2 came through
  They did not trust the new system
  Beneficiaries required to cash the voucher within a maximum of 3 days – affected stock availability – variety of commodities available to beneficiaries. Vendors need to restock in-between distribution rounds
Usual practice: In one village the Sheikhs collected vouchers from beneficiaries to collect the goods, pool them together, and redistribute equally to all – said this is how they have always handled humanitarian aid in the village.
  DRC received this information instantly, halted distribution, recovered the vouchers, talked to the Umda, and once situation clarified distribution continued – subsequent distribution rounds went as per plan. Importance of robust monitoring.
Inflation: The devaluation of the SDG late 2016 saw beneficiaries getting less food for the voucher value than was anticipated

## Slide 7: Going forward
Vendors: After seeing the success of the first year, the vendors are now all enthusiastic to take part in the next programme cycle and other vendors have shown considerable interest to come on board – will allow for more choice and variety for beneficiaries.
Encashment period of vouchers: Can be increased with more vendors on board, ensuring more items are available: vendors won’t run out of stock or need to restock in the middle of a distribution round
Improving and revising forms/templates to be used by vendors to track and collate the vouchers
  Voucher design has been changed to exclude these items and instead display a list of available commodity prices at each vendor’s store and their prices outside the store
Household size: looking at ways to adapt to household size

## Slide 8: Market fairs in Darfur
In 2017 TGH organized two fairs in AjerObeid and Muradaf in Central Darfur (Um Dukhun Locality) using Cash Vouchers
Benefits:
Allows beneficiaries to obtain goods of their choices directly from the local markets
To address their immediate basic needs
Not to receive items they already have or don’t use
Cash Vouchers have a global specific value (715 SDG)
Vouchers were exchanged with pre-selected suppliers brought in the villages with their items in the organized fair

## Slide 12: Preparation before the Fair
Selection of location based on feasibility of traders willing to bring their good to that location
Seeking community leadership and ensure “Do no Harm” TGH created a Fair committee composed of Sheiks. Their roles:
  Contributing to the whole process by preparing and supervising the event.
  Scheduling for each Sheikh when to come to the fair
  with their beneficiaries
Assessments and Verifications to identify vulnerable HH that would benefit
Estimation of the quantity of items needed
Selection of suppliers: 3 criteria: Quality of items, Prices, Availability
Distribution of plastic vouchers of different values
Information about items prices
Coordination with HAC and National Security

## Slide 13: Process
Off loading the truck and counting of items for each suppliers and signature of supplier
Preparation of the area with (delimitation, banner displaying maximum item prices)
Setting up a complaints desk
Arrival of beneficiaries led by their sheikhs as per pre-defined schedule communicated before the fair.
Vouchers checked by TGH staff
At the end of the fair, the material purchased and all remaining items counted by TGH and suppliers
Recount of the vouchers by TGH teams and comparison with the sales records of each supplier
Supplier immediately paid in Khartoum by bank transfer for security reasons

## Slide 15: Success – TGH Market fairs
Good for local economy
Suppliers very satisfied – willing to participate again
Beneficiaries satisfied with the opportunity to select their own items
No security problem due to effective preparedness

## Slide 16: Challenges
As prices are higher than in Khartoum, HH have access to a smaller quantity of items than through direct distribution
Logistic procedure and organization are heavy
Fair success is directly linked with trader availability
Suppliers do not always respect contracts
Temporary degradation of security context in Um Dukhun
Missing items, mostly because of non-respect of contract regarding items to be brought by some suppliers
Sending back the truck to Um Dukhun on time and the loading of the truck every evening/morning for the following day
Missing households because of conflicts/ rainy season

## Slide 17: Going forward
It would be better to mix direct distribution and voucher based market fairs as trucking of some items to the location of the fair was difficult
Training and sensitizing suppliers on IDP/returnee needs and take women’s specific needs into consideration