GSC Strategic Advisory Group (SAG) Meeting Notes

Date: 29th August 2019

Participants: ACTED/IMPACT Initiatives, Australian Red Cross, CARE International, Danish Refugee Council, Habitat for Humanity, IFRC, InterAction, IOM, Norwegian Refugee Council, Save the Children, UNHCR

Excused: Catholic Relief Services

Key Action Points of the Meeting

| Action Point | Who | Deadline |
| --- | --- | --- |
| Review/add theme titles and vote by adding initials next to the preferred theme titles. The most voted theme title will be chosen. | SAG members | COB 29 August |
| Review/add possible speakers and vote by adding initials next to the preferred speakers. | SAG members | COB 29 August |
| The process to select the SAG will be the same as last year. The SAG co-chairs to take forward the process. | SAG co-chairs | As per attached schedule |
| 1.1.G.1. Prepare a “pipeline-break” analysis of what the surge and remote support team has achieved and what would be the consequences of not continuing this support in terms of what we did last year, what we could be doing and what we won’t be able to do because of running out of funding. | All agencies hosting GSC surge capacity and remote support. | For GSC meeting |
| 1.1.G.4. Devote a session on defining the nature of regional shelter forums, regional shelter cluster meetings, and regional consultations by GSC WGs | SAG members | December SAG retreat |
| 1.1.G.4. Ask coordinators through an online survey to be presented at the October Shelter Coordination Workshop what their regional coordination needs are if any. Ask them what is going on in terms of energy in their countries (working groups, and others). Ask also about their relation with Health. | Shelter Coordination Workshop organizers | End of August |
| 1.3.G.6. Develop case studies on transition to shelter and settlements recovery coordination: Nepal, Fiji, Iraq and Ukraine. | CRS, IFRC/ Australian Red Cross, UNHCR | October |
| 1.4.G.4. Prepare a discussion paper on the quality of shelter coordination support services and response in merged CCCM and Shelter Clusters compared to non-merged clusters. | NRC and DRC | November |

- Welcome, revision of the minutes, and revision of agenda

No changes to the meeting agenda were suggested. The Chair went through the Action Points from the previous SAG Meeting providing an update on progress made to date.

- October Shelter week

A link with possible theme titles and speakers for the GSC Meeting was shared with SAG members for suggestions. A few suggested themes and speakers have been included in the shared document. The SAG went through the suggested theme titles and speakers to date and additional suggestions made. The Special Rapporteur on the Right to Adequate Housing will not be able to participate as she has a competing appointment.

| Action Point | Who | Deadline |
| --- | --- | --- |
| Review/add theme titles and vote by adding initials next to the preferred theme titles. The most voted theme title will be chosen. | SAG members | COB 29 August |
| Review/add possible speakers and vote by adding initials next to the preferred speakers. | SAG members | COB 29 August |

- SAG election

We propose to take the same approach as last year and elect the new SAG using an online tool prior to the meeting. The new SAG will be presented during the meeting in a short event. We have not been able to address the issue of membership that we flagged in last year´s elections but perhaps it is something to address in the December retreat. Below is the methodology used last year with the revised dates. The call for EoI to be a SAG member has already been launched.

| Action Point/Decisions | Who | Deadline |
| --- | --- | --- |
| The process to select the SAG will be the same as last year. The SAG co-chairs to take forward the process. | SAG co-chairs | As per attached schedule |

- Progress in Strategy implementation

The SAG went through the progress made in implementation of pillar 1 through the online tool here. There is still confusion about the nature, participation and ownership of the regional shelter cluster meetings/workshops and the regional shelter forums.

| Action Point/Decisions | Who | Deadline |
| --- | --- | --- |
| 1.1.G.1. Prepare a “pipeline-break” analysis of what the surge and remote support team has achieved and what would be the consequences of not continuing this support in terms of what we did last year, what we could be doing and what we won’t be able to do because of running out of funding. | All agencies hosting GSC surge capacity and remote support. | For GSC meeting |
| 1.1.G.4. Devote a session on defining the nature of regional shelter forums, regional shelter cluster meetings, and regional consultations by GSC WGs | SAG members | December SAG retreat |
| 1.1.G.4. Ask coordinators through an online survey to be presented at the October Shelter Coordination Workshop what their regional coordination needs are if any. Ask them what is going on in terms of energy in their countries (working groups, and others). Ask also about their relation with Health. | Shelter Coordination Workshop organizers | End of August |
| 1.3.G.6. Develop case studies on transition to shelter and settlements recovery coordination: Nepal, Fiji, Iraq and Ukraine. | CRS, IFRC/ Australian Red Cross, UNHCR | October |
| 1.4.G.4. Prepare a discussion paper on the quality of shelter coordination support services and response in merged CCCM and Shelter Clusters compared to non-merged clusters. | NRC and DRC | November |

- Updates from the GCCG

Debriefing of the EDG mission to Nigeria: key findings included the need for a more integrated approach; a lack of strategic vision of the shelter/CCCM sector (the Global CCCM Cluster coordinator from IOM is currently on mission in Nigeria to assess what can be done about it); problem of space and overcrowding. The EDG recommended the following as way forward: clusters need to strengthen their capacity and GCCs are considering to have a call with the ICCG or Deputy HC to explore what action can be taken such as carrying out a support mission.

Presentation on energy: Mark Gibson from GPA presented and mentioned a UK NGO is interested in supporting the shelter cluster. There might have been a misunderstanding and maybe he meant the Environment CoP. There will be a follow up meeting with him by the GSC CCs.

An EDG mission to Burkina Faso is planned.

The agenda for the next GCCG meeting to take place on the 19th of September includes Afghanistan and cash.

- AOB

Save the Children: Andy will be replaced as SAG member by another colleague, name to be confirmed. Liz will continue as currently.

IOM: suggested to carry out two trainings on the second day of the Shelter Coordination Workshop: distribution ToT and HLP in Shelter ToT. For the GSC Meeting, they will be happy to have some time for the Shelter Projects WG and the Diaspora WG.

Shelter Centre Meeting: there will be a Shelter Meeting on Friday organized by the Shelter Centre.

December SAG retreat: a reminder that the agreed dates are 3-4 December.

The next SAG meeting will be on 26th September

at mid-day Geneva time, 6am Washington, 8pm Melbourne.