## 21.3.'13
5000 | [10 empty] | Shelter/NFI/CCCM Cluster
Shelter Cluster Action List, Rakhine - Actions per Site
Site Number (correlates to maps) | Location (Township) | Name of site | Number in need of shelter |  | Temporary 8-unit Shelters required | Approximate cost of shelters to meet needs | Current Land Situation/Status/Action | Consultation with beneficiaries & host community as to suitability of proposed location, including security & freedom of movement | Identification of shelter provider (signify if shelter actor has been identified) | Field visit: 1. Land survey 2. Site Plan 3. Tendering | Approximate construction time | Monitoring: Inspection of materials/structural framework/completion | Final handover inspection
|  |  | Pop. | HH |  | Denotes Funds Required
1 | Sittwe | Basara | 1902 | 421 | 53 | 296800 | Rakhine State Govt will NOT construct shelters here - likely relocation beyond Hmanzi junction. Govt needs to identify suitable land. Required land: 3.8 acres + compensation for land owners | Action required by Govt & shelter actor once land & shelter provider identified | No shelter actor available from Shelter Cluster. Shelter provider must be identified/Govt? | Done in parallel, 1 week to 10 days required | 4-6 weeks Govt to ensure security for contractors & materials | Shelter Provider | X
2 | Sittwe | Baw Du Pha | 8791 | 1350 | 168 | 940800 | Rakhine State Govt are considering constructing shelters where tents are currently located. Govt needs to confirm plans/identify suitable land. Required land: 17.6 acres + compensation for land owners | Action required by Govt | Govt to confirm if shelter provider | Done in parallel, 1 week to 10 days required | 4-6 weeks Govt to ensure security for contractors & materials | Shelter Provider | X
3 | Sittwe | Dar Pai | 10470 | 1721 | 215 | 1204000 | Rakhine State Govt does not recognise as an official IDP camp and will NOT approve shelters. Govt to clarify position & identify suitable land. Required land: 20.1 acres + compensation for land owners | Action required by Govt & shelter actor once land & shelter provider identified | No shelter actor available from Shelter Cluster. Shelter provider must be identified/Govt? | Done in parallel, 1 week to 10 days required | 4-6 weeks Govt to ensure security for contractors & materials | Shelter Provider | X
4 | Sittwe | Khaung Doke Khar | 2108 | 361 | 46 | 257600 | Proposed construction was rejected in Nov 2012, not regarded by Govt as officially recognised camp. Govt to clarify position & identify suitable land. Required land: 4.2 acres + compensation for land owners | Action required by Govt & shelter actor once land & shelter provider identified | No shelter actor available from Shelter Cluster. Shelter provider must be identified/Govt? | Done in parallel, 1 week to 10 days required | 4-6 weeks Govt to ensure security for contractors & materials | Shelter Provider | X
5 | Sittwe | Thae Chaung | 15554 | 2445 | 308 | 1724800 | Rakhine State Govt does not recognise as an official site and will NOT consider shelters here. Govt to clarify position & identify suitable land. Required land: 31.2 acres + compensation for land owners | Action required by Govt & shelter actor once land & shelter provider identified | No shelter actor available from Shelter Cluster. Shelter provider must be identified/Govt? | Done in parallel, 1 week to 10 days required | 4-6 weeks Govt to ensure security for contractors & materials | Shelter Provider | X
6 | Sittwe | Thae Chaung (Kyaukphyu) | 2203 | 547 | 69 | 386400 | Rakhine State Government adamant that these IDPs (many from Pauktaw T/ship) will NOT be provided temp shelter in Sittwe TP & this rainy season will be provided tents but then relocated back to place of origin Required land: 4.4 acres + compensation for land owners | Based on current situation, likely best case scenario is Govt to identify more suitable land to locate IDPs in tents
7 | Sittwe | Hmanzi Junction | 1092 | 203 | 26 | 145600 | Rakhine State Govt are considering constructing 30 shelters where tents are currently located. Govt needs to confirm plans/identify suitable land. Required land: 2.2 acres + compensation for land owners | Action required by Govt & shelter actor once land & shelter provider identified | Govt must confirm if shelter provider | Done in parallel, 1 week to 10 days required | 4-6 weeks Govt to ensure security for contractors & materials | Shelter Provider | X
8 | Sittwe | Bu May Ohn Taw (PT) | 2858 | 443 | 40 | 224000 | Rakhine State Government adamant that these IDPs (primarily from Pauktaw T/ship-urban areas) will NOT be provided temp shelter in Sittwe TP & this rainy season will be provided tents but then relocated back to Pauktaw/place of origin Required land: 5.7 acres + compensation for land owners | Based on current situation, likely best case scenario is Govt to identify more suitable land to locate IDPs in tents
9 | Sittwe | Bu May Ohn Taw Shore (PT) | 252 | 59 | 17 | 95200 | Rakhine State Government adamant that these IDPs (primarily from Pauktaw T/ship-urban areas) will NOT be provided temp shelter in Sittwe TP & this rainy season will be provided tents but then relocated back to Pauktaw/place of origin Required land: 0.5 acres + compensation for land owners | Based on current situation, likely best case scenario is Govt to identify more suitable land to locate IDPs in tents
5275200
1 | Myebon | Kan Thar Htwat Wa | 269 | 44 | 6 | 33600 | Playing field in front of Monastery | Ongoing | UNHCR | Land survey/site plan complete/tender in process | 4-6 weeks Govt to ensure security for contractors & materials | UNHCR | X
2 | Myebon | Taung Paw (Option A) | 3900 | 705 | 89 | 498400 | Preferable option would be to construct shelters in place of origin. However, concern would be temporary shelter would not get replaced (in due course) by permanent shelters. | To pursue option A, would require significant consultation with IDPs and assurances from Govt regarding IDP security & temporary nature of shelters. | UNHCR | Done in parallel, 1 week to 10 days required | 4-6 weeks Govt to ensure security for contractors & materials | UNHCR | X
|  | Taung Paw (Option A) |  |  |  |  | Shelters to be constructed adjacent to place of displacement. Elevated structures to be constructed above rice field. | Ongoing | UNHCR | Land survey/site plan complete/tender in process | Govt to ensure security for contractors & materials | UNHCR | X
532000
3 | Pauktaw | Ah Nauk Ywe (Option A) | 3773 | 773 | 97 | 543200 | Preferable option would be to construct shelters in place of origin. However, concern would be temporary shelter would not get replaced (in due course) by permanent shelters. | To pursue option A, would require significant consultation with IDPs and assurances from Govt regarding IDP security & temporary nature of shelters. | UNHCR funded /DRC implemented | Done in parallel, 1 week to 10 days required | 4-6 weeks Govt to ensure security for contractors & materials | DRC/UNHCR | X
|  | Ah Nauk Ywe (Option B) |  |  |  |  | Shelters to be constructed adjacent to place of displacement. Elevated structures to be built above rice field. | Ongoing | UNHCR funded /DRC implemented | Land survey/site plan complete/tender in process | 4-6 weeks Govt to ensure security for contractors & materials | DRC/UNHCR | X
4 | Pauktaw | Nget Chaung (Option A) | 7902 | 1345 | 164 | 918400 | Preferable option would be to construct shelters in place of origin. However, concern would be temporary shelter would not get replaced (in due course) by permanent shelters. | To pursue option A, would require significant consultation with IDPs and assurances from Govt regarding IDP security & temporary nature of shelters. | UNHCR | Done in parallel, 1 week to 10 days required | 4-6 weeks Govt to ensure security for contractors & materials | UNHCR | X
|  | Nget Chaung (Option B) |  |  |  |  | Shelters to be constructed adjacent to place of displacement. Elevated structures to be built above rice field. | Ongoing | UNHCR | Land survey/site plan complete/tender in process | 4-6 weeks Govt to ensure security for contractors & materials | UNHCR | X
5 | Pauktaw | Kyein Ni Pyin | 4401 | 778 | 110 | 616000 | Pasture land | Ongoing | UNHCR | Land survey/site plan complete/tender in process | 4-6 weeks Govt to ensure security for contractors & materials | UNHCR | X
6 | Pauktaw | Sin Tet Maw (Option A) | 3803 | 845 | 106 | 593600 | Preferable option would be to construct shelters in place of origin. However, concern would be temporary shelter would not get replaced (in due course) by permanent shelters. | To pursue option A, would require significant consultation with IDPs and assurances from Govt regarding IDP security & temporary nature of shelters. | UNHCR funded / DRC implemented | Done in parallel, 1 week to 10 days required | 4-6 weeks Govt to ensure security for contractors & materials | DRC/UNHCR | X
|  | Sin Tet Maw (Option B) |  |  |  |  | Shelters to be constructed adjacent to place of displacement. Elevated structures to be built above rice field. | Ongoing | UNHCR funded / DRC implemented | Land survey/site plan complete/tender in process | 4-6 weeks Govt to ensure security for contractors & materials | DRC/UNHCR | X
2671200
[6 empty] | Note: for the combined cost to meet the temporary shelter needs of Meybon & Pauktaw T/ships is approx. US$3.5 million (includ. elevated shelter). Currently UNHCR has US$1.1 million confirmed, additional US$800,000 awaiting confirmation for 27th March. Remaining gap of US$1.5 million UNHCR still in negotaion with donor, no clear date if/when will be confirmed. |  |  |  |  | Construction time is based on calculation of 500 pax. to build 50 shelters per month. Currently 35 contractors available in Rakhine, 6 would be utilised for UNHCR/DRC shelters
Note, costings for shelters per site is based on cost of US$700 per single family unit, with each structure containing 8 individual family units. Costs do not include additional camp infrastructure such as communal kitchens and camp management office.
Required land is based on simple calculation of 1 acre for 500 individuals