## 15.4.'13
5000 | [12 empty] | Shelter/NFI/CCCM Cluster
Shelter Cluster Action List, Rakhine - Actions per Site, 15.4.'13
The below table was first submitted to the Government of Myanmar April 6th in Nay Pyi Taw as part of the Inter-Agency Preparedness/Contingency Plan - Rakhine State, Myanmar, March 2013. In addition to that meeting and the following meeting April 7th in Yangon at the Myanmar Peace Centre with the Government of Myanmar and key international donors, the UN and the UNHCR led Shelter Cluster was encouraged by the progress made in these discussions in reaching an understanding of five key matters of joint interest: 1. The Government of Myanmar has committed itself to lead reconciliation efforts at all levels between the divided communities in Rakhine State; 2. An agreement that the Government of Myanmar will facilitate the voluntary return of internally displaced persons (IDPs), who are able and willing, to their places of origin, as soon as feasible; 3. It is acknowledged that temporary shelter is required for IDPs currently precluded from returning to their places of origin. In this respect, the Government of Myanmar is committed to delivering international standards in shelter and other vital services, with particular attention to the most vulnerable; 4. The Government of Myanmar will provide sufficient and where feasible non flood prone land for the construction of temporary shelters plus seek to ensure a transparent and fair allocation of temporary shelters for the displaced; 5. A commitment by the authorities in Nay Pyi Taw to open a dedicated communication channel for humanitarian actors in Rakhine State to ensure an immediate response when needed.
Site Number (correlates to maps) | Location (Township) | Name of site | Number in need of shelter |  | Temporary 8-unit Shelters required | Approximate cost of shelters to meet needs | Current Land Situation/Status/Action | Discussion with Shelter Cluster, Govt (Minister for Immigration, Deputy Minister for Border Affairs & Chief Minister for Rakhine) & US, Australia, British Ambassadors & ECHO during April 8th visit to Rakhine State | Identification of shelter provider. Signify if shelter actor has been identified during April 8th visito Rakine State | Consultation with beneficiaries & host community as to suitability of proposed location, including security & freedom of movement | Field visit: 1. Land survey 2. Site Plan 3. Tender | Shelter design | Approximate construction time | Monitoring: Inspection of materials/structural framework/completion | Final handover inspection
|  |  | Pop. | HH |  | Denotes Funds Required
1 | Sittwe | Basara | 1902 | 421 | 53 | 296800 | Rakhine State Govt will NOT construct shelters here - likely relocation beyond Hmanzi junction. Govt needs to identify suitable land. Required land: 3.8 acres + compensation for land owners | Govt stated that 6 potential sites in rural areas of Sittwe Township have been identified for temporary shelter. Shared with Shelter Cluster evening 6th April. More precise details needed from Govt. Shelter Cluster concern over sufficiency of land. | Shelter Cluster confirmed NO shelter member, including UNHCR, has programmatic capacity to complete shelters before rains. Govt provisionally confirmed as shelter provider. | Action required by Govt as the shelter actor | Done in parallel, 1 week to 10 days required. Shelter Cluster to provide technical support in site planning & shelter design re. adherence to international standards. | Temporary shelter (TS) design as agreed between Shelter Cluster and Govt office: Development Affairs Minister, Rakhine State Government. See attached TS drawings (45'x30'x9') | Govt provisionally stated 3 months to build shelters. Govt to ensure security for contractors & materials. | Govt as the shelter actor supported by Shelter Cluster | X
2 | Sittwe | Baw Du Pha | 8791 | 1350 | 168 | 940800 | Rakhine State Govt are considering constructing shelters where tents are currently located. Govt needs to confirm plans/identify suitable land. Required land: 17.6 acres + compensation for land owners | Govt stated that 6 potential sites in rural areas of Sittwe Township have been identified for temporary shelter. Shared with Shelter Cluster evening 6th April. More precise details needed from Govt. Shelter Cluster concern over sufficiency of land. | Shelter Cluster confirmed NO shelter member, including UNHCR, has programmatic capacity to complete shelters before rains. Govt provisionally confirmed as shelter provider. | Action required by Govt as the shelter actor | Done in parallel, 1 week to 10 days required. Shelter Cluster to provide technical support in site planning & shelter design re. adherence to international standards. | Temporary shelter (TS) design as agreed between Shelter Cluster and Govt office: Development Affairs Minister, Rakhine State Government. See attached TS drawings (45'x30'x9') | Govt provisionally stated 3 months to build shelters. Govt to ensure security for contractors & materials. | Govt as the shelter actor supported by Shelter Cluster | X
3 | Sittwe | Dar Pai | 10470 | 1721 | 215 | 1204000 | Rakhine State Govt does not recognise as an official IDP camp and will NOT approve shelters. Govt to clarify position & identify suitable land. Required land: 20.1 acres + compensation for land owners | Govt stated that 6 potential sites in rural areas of Sittwe Township have been identified for temporary shelter. Shared with Shelter Cluster evening 6th April. More precise details needed from Govt. Shelter Cluster concern over sufficiency of land. | Shelter Cluster confirmed NO shelter member, including UNHCR, has programmatic capacity to complete shelters before rains. Govt provisionally confirmed as shelter provider. | Action required by Govt as the shelter actor | Done in parallel, 1 week to 10 days required. Shelter Cluster to provide technical support in site planning & shelter design re. adherence to international standards. | Temporary shelter (TS) design as agreed between Shelter Cluster and Govt office: Development Affairs Minister, Rakhine State Government. See attached TS drawings (45'x30'x9') | Govt provisionally stated 3 months to build shelters. Govt to ensure security for contractors & materials. | Govt as the shelter actor supported by Shelter Cluster | X
4 | Sittwe | Khaung Doke Khar | 2108 | 361 | 46 | 257600 | Proposed construction was rejected in Nov 2012, not regarded by Govt as officially recognised camp. Govt to clarify position & identify suitable land. Required land: 4.2 acres + compensation for land owners | Govt stated that 6 potential sites in rural areas of Sittwe Township have been identified for temporary shelter. Shared with Shelter Cluster evening 6th April. More precise details needed from Govt. Shelter Cluster concern over sufficiency of land. | Shelter Cluster confirmed NO shelter member, including UNHCR, has programmatic capacity to complete shelters before rains. Govt provisionally confirmed as shelter provider. | Action required by Govt as the shelter actor | Done in parallel, 1 week to 10 days required. Shelter Cluster to provide technical support in site planning & shelter design re. adherence to international standards. | Temporary shelter (TS) design as agreed between Shelter Cluster and Govt office: Development Affairs Minister, Rakhine State Government. See attached TS drawings (45'x30'x9') | Govt provisionally stated 3 months to build shelters. Govt to ensure security for contractors & materials. | Govt as the shelter actor supported by Shelter Cluster | X
5 | Sittwe | Thae Chaung | 15554 | 2445 | 308 | 1724800 | Rakhine State Govt does not recognise as an official site and will NOT consider shelters here. Govt to clarify position & identify suitable land. Required land: 31.2 acres + compensation for land owners | Govt stated that 6 potential sites in rural areas of Sittwe Township have been identified for temporary shelter. Shared with Shelter Cluster evening 6th April. More precise details needed from Govt. Shelter Cluster concern over sufficiency of land. | Shelter Cluster confirmed NO shelter member, including UNHCR, has programmatic capacity to complete shelters before rains. Govt provisionally confirmed as shelter provider. | Action required by Govt as the shelter actor | Done in parallel, 1 week to 10 days required. Shelter Cluster to provide technical support in site planning & shelter design re. adherence to international standards. | Temporary shelter (TS) design as agreed between Shelter Cluster and Govt office: Development Affairs Minister, Rakhine State Government. See attached TS drawings (45'x30'x9') | Govt provisionally stated 3 months to build shelters. Govt to ensure security for contractors & materials. | Govt as the shelter actor supported by Shelter Cluster | X
6 | Sittwe | Thae Chaung (Kyaukphyu) | 2203 | 547 | 69 | 386400 | Rakhine State Government adamant that these IDPs (many from Pauktaw T/ship) will NOT be provided temp shelter in Sittwe TP & this rainy season will be provided tents but then relocated back to place of origin Required land: 4.4 acres + compensation for land owners | Based on current situation, likely best case scenario is Govt to identify more suitable land to locate IDPs in tents. Govt must confirm precise land where IDPs will be located. | NA | Govt supported by UNHCR led Shelter Cluster | Shelter Cluster to provide technical support to Govt in site planning & provision of tents/emergency shelter |  |  |  | NA
7 | Sittwe | Hmanzi Junction | 1092 | 203 | 26 | 145600 | Rakhine State Govt are considering constructing 30 shelters where tents are currently located. Govt needs to confirm plans/identify suitable land. Required land: 2.2 acres + compensation for land owners | Govt stated that 6 potential sites in rural areas of Sittwe Township have been identified for temporary shelter. Shared with Shelter Cluster evening 6th April. More precise details needed from Govt. Shelter Cluster concern over sufficiency of land. | Shelter Cluster confirmed NO shelter member, including UNHCR, has programmatic capacity to complete shelters before rains. Govt provisionally confirmed as shelter provider. | Action required by Govt as the shelter actor | Done in parallel, 1 week to 10 days required. Shelter Cluster to provide technical support in site planning & shelter design re. adherence to international standards. | Temporary shelter (TS) design as agreed between Shelter Cluster and Govt office: Development Affairs Minister, Rakhine State Government. See attached TS drawings (45'x30'x9') | Govt provisionally stated 3 months to build shelters. Govt to ensure security for contractors & materials. | Govt as the shelter actor supported by Shelter Cluster | X
8 | Sittwe | Bu May Ohn Taw (PT) & Bu May Ohn Taw Shore (PT) - note IDPs in Bu May Ohn Taw Shore (PT) to reloacte to Bu May Ohn Taw (PT) | 2858 | 443 | 40 | 224000 | Rakhine State Government adamant that these IDPs (primarily from Pauktaw T/ship-urban areas) will NOT be provided temp shelter in Sittwe TP & this rainy season will be provided tents but then relocated back to Pauktaw/place of origin Required land: 5.7 acres + compensation for land owners | Based on current situation, likely best case scenario is Govt to identify more suitable land to locate IDPs in tents. Govt must confirm precise land where IDPs will be located. | NA | Govt supported by UNHCR led Shelter Cluster | Shelter Cluster to provide technical support to Govt in site planning & provision of tents/emergency shelter |  |  |  | NA
9 | Sittwe |  | 252 | 59 | 17 | 95200 | Rakhine State Government adamant that these IDPs (primarily from Pauktaw T/ship-urban areas) will NOT be provided temp shelter in Sittwe TP & this rainy season will be provided tents but then relocated back to Pauktaw/place of origin Required land: 0.5 acres + compensation for land owners
[6 empty] | 5275200 | During April 8th visito Rakine State Govt requested funding for shelters in Sittwe Township, Shelter Cluster confirmed they would advocate with donors for funding. | Above mentioned plans (in total) allows for 400 temporary shelters, approximately 20,000 persons. Still leaves gap of 25,000 without temporary shelter for rainy season. Shelter Cluster requires further clarity from Govt on precise temporary shelter site plans and construction of temporary shelters for Sittwe Township.
1 | Myebon | Kan Thar Htwat Wa | 269 | 44 | 6 | 33600 | Playing field in front of Monastery | Temporary shelters will be built on the current IDP site. There is insufficient land to build the required number of temporary shelters in the IDPs place of origin. | UNHCR | UNHCR/Govt - ongoing | Land survey, site plan & tender complete | Design as agreed with Shelter Cluster - see attached TS drawings (45'x30'x9') | 6-8 weeks Govt to ensure security for contractors & materials | UNHCR | X
2 | Myebon | Taung Paw (Option A) | 3900 | 705 | 89 | 498400 | Preferable option would be to construct shelters in place of origin. However, concern would be temporary shelter would not get replaced (in due course) by permanent shelters. | Due to remaining high levels of tension between Rakhine and IDPs, and despite the preferable option of building temporary shelters for Muslim IDPs in their place of origin, at this juncture and particularly for the IDPs’ security, Government of Myanmar explicitly requested that the shelters not be built in IDP place of origin. | NA | NA | NA | NA | NA | NA | NA
|  | Taung Paw (Option A) |  |  |  |  | Shelters to be constructed adjacent to place of displacement. Elevated structures to be constructed above rice field. | Govt must ensure the land is sufficiently compacted plus provide an additional 2.5 acres. | UNHCR | UNHCR/Govt - ongoing | Land survey, site plan & tender complete | Design as agreed with Shelter Cluster - see attached TS drawings (45'x30'x9') | 6-8 weeks Govt to ensure security for contractors & materials | UNHCR | X
532000
3 | Pauktaw | Ah Nauk Ywe (Option A) | 3773 | 773 | 97 | 543200 | Preferable option would be to construct shelters in place of origin. However, concern would be temporary shelter would not get replaced (in due course) by permanent shelters. | Return to place of origin for these IDPs is not viable since it would require the IDPs to return to Pauktaw Town where their security cannot be assured. | NA | NA | NA | NA | NA | NA | NA
|  | Ah Nauk Ywe (Option B) |  |  |  |  | Shelters to be constructed adjacent to place of displacement. Elevated structures to be built above rice field. | Due to no other suitable land available, the shelters will have to be elevated at the identified site. | DRC/UNHCR | DRC/UNHCR/Govt - ongoing | Land survey, site plan & tender complete | Design as agreed with Shelter Cluster - see attached TS drawings (45'x30'x9') | 6-8 weeks Govt to ensure security for contractors & materials | DRC/UNHCR | X
4 | Pauktaw | Nget Chaung (Option A) | 7902 | 1345 | 164 | 918400 | Preferable option would be to construct shelters in place of origin. However, concern would be temporary shelter would not get replaced (in due course) by permanent shelters. | Construction of temporary shelters on IDP place of origin viable but must be confirmed that the IDPs would be willing to live in this location. UNHCR following-up with the IDPs the week of April 8th and determine if they would be willing to live in their place of origin. | UNHCR | To pursue option A, would require significant consultation with IDPs and assurances from Govt regarding IDP security & temporary nature of shelters. | Done in parallel, 1 week to 10 days required | X | 6-8 weeks Govt to ensure security for contractors & materials | UNHCR | X
|  | Nget Chaung (Option B) |  |  |  |  | Shelters to be constructed adjacent to place of displacement. Elevated structures to be built above rice field. | Action dependent upon results of UNHCR/IDP consultation week April 6th | UNHCR | UNHCR/Govt - ongoing | Land survey, site plan & tender complete | Design as agreed with Shelter Cluster - see attached TS drawings (45'x30'x9') | 6-8 weeks Govt to ensure security for contractors & materials | UNHCR | X
5 | Pauktaw | Kyein Ni Pyin | 4401 | 778 | 110 | 616000 | Pasture land | Suitable pasture land confirmed for the construction of temporary shelters. Govt confirmed that efforts by neighboring communities to block access and building of shelters will be addressed, as needed. | UNHCR | UNHCR/Govt - ongoing | Land survey, site plan & tender complete | Design as agreed with Shelter Cluster - see attached TS drawings (45'x30'x9') | 6-8 weeks Govt to ensure security for contractors & materials | UNHCR | X
6 | Pauktaw | Sin Tet Maw (Option A) | 3803 | 845 | 106 | 593600 | Preferable option would be to construct shelters in place of origin. However, concern would be temporary shelter would not get replaced (in due course) by permanent shelters. | Return to place of origin for these IDPs is not viable since it would require the IDPs to return to Pauktaw Town where their security cannot be assured. | NA | NA | NA | NA | NA | NA | NA
|  | Sin Tet Maw (Option B) |  |  |  |  | Shelters to be constructed adjacent to place of displacement. Elevated structures to be built above rice field. | Due to no other suitable land available, the shelters will have to be elevated at the identified site. | DRC/UNHCR | DRC/UNHCR/Govt - ongoing | Land survey, site plan & tender complete | Design as agreed with Shelter Cluster - see attached TS drawings (45'x30'x9') | 6-8 weeks Govt to ensure security for contractors & materials | DRC/UNHCR | X
2671200
The UN, and UNHCR as Shelter Cluster Lead, also stresses the equally critical point that while the central focus of Monday’s visit to Rakhine was on shelter, the provision of sufficient health and water and sanitation (WASH) support as well as physical safety is equally if not more critical in terms of life saving activities. Similarly close cooperation between the Government of Myanmar and the UNICEF led WASH Cluster and the WHO–Merlin led Health Cluster is vital. It is a sobering thought that between in the first three months of 2013 it is reported that approximately 30 people have died in the Taung Paw IDP camp, including 14 women, 10 babies, four at birth.
Note, costings for shelters per site is based on cost of US$700 per single family unit, with each structure containing 8 individual family units. Costs do not include additional camp infrastructure such as communal kitchens and camp management office.
Required land is based on simple calculation of 1 acre for 500 individuals