## Sheet1
|  | Activity matrix (Humanitarian Response Plan 2016) |  |  | FINAL Version: 05 NOV 2015
# | Activity | Definition | Cost | Area of intervention | Duration / implementation |  |  | HH/ind.
1 | Winterization or multipurpose cash grant | Injection of a one off, unconditional cash grant for preparing for winter (utilities + NFI + clothes) through bank transfer or vouchers. | 100 USD / individual | All oblast except NGCA | One-off for winter period / throughout year |  | 375 | 80000 | 30000000 | 0
2 | Cash for rent or other shelter-linked monetized solutions | Securing adequate and to-standard shelter. As a response for potential eviction. Possibility to decommission Collective Centers. Cash activities matching rent and utilities indicators. | Rural up to 600 USD/year per HH | All oblasts except NGCA | 6 month minimum, 12 preferable. |  | 1026 | 5000 | 5130000
City up to 660 USD/year per HH
Metropole up to 2040 USD/year per HH
3 | Collective Center winterization | Basic repair and NFI provision for Collective Center. | 300 to 400 USD per indiv. | Accent on 5 oblast of the east. | Seasonal activity (late summer, fall 2016) usually 10 to 45 days of works |  | 400 | 5000 | 2000000
|  | Specialized C.C. accomodating IDPs popualtion with special needs (e.g. institutions, retirement home; orphanage; accommodation for PWD; etc.). | Up to 600 USD per Indiv. if specialized |  |  |  | 750 | 1000 | 750000
|  | Basic repairs might include: Water & Sanitation; Electricity; Windows; basic refresh and roof repair; heating system. |  |  |  |  | 200 | 7000 | 1400000
4 | Light and medium repairs | Roofing materials and glazing for house repair in order to avoid deterioration and to stabilize living conditions of IDPs/Returnees/ Affected population. | 300 to 400 light repair | Donetsk ; Luhansk GCA (very limited); NGCA huge demand | 3 to 5 days/house |  | 400 | 5000 | 2000000
|  |  | up to 800 USD medium repair |  |  |  | 1250 | 10000 | 12500000
[5 empty] | 7 to 15 days/house |  |  |  | 0
5 | Structural repairs ["heavy repairs"] | Partial reconstruction of one or several walls. Full Concrete ring beam and appropriated retrofitting for the structure. Partial Flooring (warm room). Partial Opening (warm room). Full Roofing. Partial Insulation. Basic sanitation & heating system. | up to 4000 USD per HH (2 p.) an extra + 500 USD per extra person. | Damaged villages along former contact lines | 30 to 45 days/house
6 | Reconstruction/permanent housing | Reconstruction on existing foundations of a NEW full structurally sound small house. Average 10 to 12 m2 per person (gross surface). Insulated. Basic furniture (bed). Heating system. Sanitation. Possibility of future extension highly appreciated. | 8000 USD/HH (2 p.house) + 1000 USD per extra person. | Damaged villages along former contact lines | 45 to 90 days / house |  | 80 | 20000 | 1600000
7 | Winterization (insulation) | Materials for basic house insulation for the winter | 80 to 100 USD | Donetsk & Luhansk principally | 7 to 10 days / house
8 | Essencial utilities networks repairs and connection | Conditionality: other works are implemented in the community and repairs are complementing general activities as a last resort | 100-250 USD per HH | Donetsk & Luhansk principally
9 | Solid fuel & heater | Provision of appropriate solid fuel for winterisation; heater if necessary ( 20% of the case) | 110 USD/ HH without heater 200 USD/HH fuel + heater | Donetsk & Luhansk principally, Damaged village along the contact line | Seasonal activity, extension of winter 2015, winterization 2016
10 | NFI (clothing set) | In-kind provision of warm clothes, jackets, thermal underwear, shoes | 80 to 100 USD /pers | Accent on 5 oblast of the east. | Seasonal activity, extension of winter 2015, winterization 2016
11 | NFI (bedding set) | In-kind provision of bed linen, pillow case, blankets | 16 USD linen | Accent on 5 oblast of the east. | Seasonal activity, extension of winter 2015(25%), winterization 2016 (75%)
|  |  | 8 USD blanket |  |  |  | 162 | 30000 | 4860000
12 | NFI (general) | Essential household item provision, e.g. kitchen kit, hygiene kit (if not covered by WASH sector); bed and matresses if needed | 200 USD / HH | Accent on 5 oblast of the east. | Seasonal activity, extension of winter 2015, winterization 2016
[7 empty] | 88 | 10000 | 880000
[7 empty] | 26.4 | 20000 | 528000
[7 empty] | 88 | 20000 | 1760000
[7 empty] | 110 | 20000 | 2200000
[7 empty] | 2 | 10000 | 20000
65628000
950000
0.1
[5 empty] | 95000 | 31666.6667 | 5145833.3333
[7 empty] | 5200 | 162.5
600
400000
|  |  |  | 666.6667 | 41.6667 | 52.0833