Shelter Cluster Meeting Minutes/Actions – attendance sheet to follow

Lauperville Day 3

| A. Task | B. Update / Gap | C. Action | D. Responsible Person/ Agency | E. Status / Deadline |
| --- | --- | --- | --- | --- |
| A1 | We have no secondary data review, we are not sure what data is already available and there are a lot of small assessments coming in every day. Can we do a SDR as a URGENCY | IMO carryout a secondary data review and consolidate the data and assessments | IMO | Day 4 |
| C2 | We need to see what to do with all of the data and information that is now available. Do we need to still collect data? There is support on data and plans from the assessment specialist due imminently in-country | IMO to audit existing data and create an analysis plan based on the agreed template | IMO Meeting will be called by OCHA | Day 4 |
| C1 | All Clusters are coming up with population/people in need (PiN) figures and they are all different! Can we work together and come up with better method? | IMO, there is new PiN guidance from Geneva IMWG, can you read it and let us know what our options are regarding getting to a figure for our strategy and helping us with targets. We are still going to be missing data until the assessments are complete but if we have a methodology ready to go that would help. Please draft a 2 pager on PiN options and data that we are still missing, also outline options for creating targets for the cluster | IMO | Day 4 (will be discussed at the IMWG) |
| C3 | We had some displacement data just sent from UNDAC for storm Ralf, this needs to be analysed. | IMO to analyse current data on displacement from Storm Ralf (in collaboration with CCCM), especially in terms of where people are in evacuation centres/schools etc., where are areas most in need of shelter relief, tarp distribution etc.). | IMO/CC IMO will need to present this at the IMWG | Day 4 |
| NA | Shelter Cluster Strategy text needs to be finalised. | The text needs to be re-written after we received more information and in light of the new storm | Partners send comments to CC ASAP | ASAP |
| D1/D2 | Shelter Response Monitoring Plan for Shelter Cluster Strategy to be developed. There are a number of indicators that have been proposed but they need to be discussed, are they appropriate? | IMO to draft log frame for Shelter Cluster strategy and define how, how often and where to get data for the indicators. Aggregation of indicators also needs to be taken into account, as well as relevance and measurability of indicators. | IMO develop draft log frame/monitoring plan for cluster | Day 4 |
| B1 | What agencies are working in Shelter? We are in desperate need of a contact list with some many new agencies coming in. This needs to be uploaded to the web portals asap so partners can access it Use a template if available | IMO to decide on tool (Excel / MailChimp, HiD), design contact list (think about fields that are needed, subscribe options for topics etc.) and populate it based on the Govts mapping of agencies document which has sector agencies/names and #s Upload to the web portal (Shelter and OCHA) if appropriate. | IMO | Day 4 |
| B2 | We have no presence online yet on the OCHA or shelter websites. We need to be on both? Please confirm (IMO). IMO urgent task | IMO to get permissions and passwords for both HR.info and ShelterCluster.org portals from OCHA and the Global Support Team and upload relevant documents to the website (contact list, meeting minutes, cluster strategy, weather forecast, log frame/monitoring plan, 4W, secondary data review etc.) | IMO | Day 4 |
| B4 | IMO strategy/systems framework needs to be developed and maintained over the course of the emergency, used as a handover etc. Is there a template available that we can just amend? Other Clusters using the UNHCR template that also can link to indicators and monitoring framework, this is very handy, all planning info in one place. | IMO to start outlining the IM systems for the cluster using Shelter Cluster template, discuss with CCCM IMO to ensure interoperability of systems. | IMO | Day 4-5 |
| C5/C6 | There is a new Assessment Group being led by OCHA and they need a few things off us including a list of assessments we have collected, our draft SDR and our needs for future assessments. We specifically need to indicate the gaps and where we might need more assessments done. Assessment meeting will be called over next days. | IMO please 1. fill in the assessment registry (will be shared by assessment specialist) 2. have the SDR ready to share and 3. define the potential methodology for any proposed assessment in terms of questions / indicators and data collection methods to ensure relevant baseline data for shelter and NFI interventions. This is based on the secondary data review and analysis plan. Note any proposed shelter assessment might become part of a joint assessment, via OCHA, with WASH etc. | IMO | Day 5 (have it ready before lunch) |
| D3 | Data collection tool needs to be developed to assess the response. Does the IMO just want to use something like a traditional Excel 4W or maybe something like ActivityInfo or survey gizmo. The internet is good so the partners are happy to log their response online or via Excel. Ensure other Clusters not monitoring same interventions | IMO to develop a 4W template for monitoring the response in line with the log frame/ monitoring plan (either online or offline). What clusters track what activities, who tracks hygiene kits (WASH?) to avoid overlap. IMO have draft to show 4W monitoring tool at the next Shelter Cluster meeting to partners for endorsement | IMOs Worth discussing with other IMOs to see what they are producing? | Day 5 |
| D4 | Training partners on using the 4W | IMO to prepare an operational guide (1-2 pages) for training partners in the use/usefulness of the 4W | IMO | Day 5 |
| G5 | CCCM Cluster has told us they were requested by MDP to facilitate camp and spontaneous site (SS) decommissioning, return and reintegration processes to the central mountains from surrounding counties. They need to prioritise SS to decommission. We have limited NFI supplies and are only now getting information on what is in the pipeline by shelter partners. | IMO to look at the housing damage data and the supplies/pipeline data to determine how many HHs can be assisted with currently available resources. IMO also to look at the gap in response, e.g. how many shelter repair kits are still needed? Meet with CCCM IMO to discuss the shortfall in supplies and to see what the best SSs to decommission are. Do we need more information, e.g. a rapid assessment here? | Shelter IMOs ID areas, assess response gaps and pass information to CCCM IMO | Day 5 |
| NA | WASH - OXFAM will distribute hygiene kits tomorrow with Bowtown an intended location – they will provide feedback to Shelter Cluster tomorrow on actual distribution. | OXFAM provide feedback to both the Shelter and WASH Cluster re urgent needs | OXFAM | Day 5 |
| NA | WASH - OXFAM offered to build latrines in flood/storm damaged zone. They can provide labourers, slabs and material for 1000 HH. They need to know where Shelter is currently providing material and can work together | Shelter partners to provide feedback on where they are working, link into WASH partners. Once agreed, the 4W will be sent to all partners, please fill in the 4W when requested so that the IMO can share this information back to WASH | Shelter partners | TBC |
| E1 | The Shelter Cluster factsheet needs to be drafted and shared. | IMO to use the factsheet template and guidance to complete the factsheet in collaboration with the CC. | IMO | Day 5 |
| E2 | Cluster would like an overview of the flooding (Storm Ralf) with some affected population and displacement figures. Can we create a visualisation/map and share ASAP on the portal or via email (which would be appropriate?) | IMO to get the necessary data and make an appropriate visualisation with a map. | IMO | Day 5 |
| G8 | There are still lots of displaced from storm Ralf last month in the mountains and there is a storm due next week forecast in the same areas. | We need more accurate forecasts of where the storm will be and what the likely outcomes will be. | IMO to get up-to-date forecast on new storm Upload to the portals | Day 5 |
| B10 | For all staff departing, please ensure end of mission report is complete and available to all cluster colleagues to assess | IMO departing soon, please complete an end of mission report for handover | IMO | Day 5 |