## CGI Bundles_0824
Sinduhpalchok Coverage of CGI Bundles 24th Aug. 2015 | [8 empty] | Data Source: Shelter Cluster Agency Tracking, 24thAug 2015, IOM Pipeline Database, DDRC MOU data matrix
VDC | HH Updte 2015 | Item | Implementing agency | MOU in VDC | Completed (HH) | Ongoing / In Country Stock (HH) | Planned (funded) (HH) | Grand Total(HH) | Remarks | Data Source | Coverage (Total vs HH updated 2015)
Attarpur | 711 | CGI | RELIEF International | Yes | 368 |  |  | 368 | For ward 6,7,8 | SC Agency Tracker | 103.1%
|  | CGI | Christian Aid | No |  |  | 365 | 365 |  | IOM Pipeline
Bandegaun | 1450 | CGI | Plan International | Yes |  | 350 |  | 350 |  | IOM Pipeline | 24.14%
Bansbari | 1425 | CGI | Save the Children |  |  |  |  | 0 |  | SC Agency Tracker | 0%
Banskharka | 875 | CGI | Care Nepal | Yes | 514 | 50 |  | 564 |  | SC Agency Tracker | 64.46%
Baramchae | 850 | CGI | Nepal Youth Foundation | Yes |  |  |  | 0 | Partial HH | MOU | 101.9%
|  | CGI | Lutheran World Federation | No |  | 866 |  | 866 |  | SC Agency Tracker
Barhabise | 1848 | CGI | IOM | Yes | 1457 |  |  | 1457 |  | IOM Pipeline | 80.47%
|  | CGI | Kingdom Investement Nepal | Yes |  |  | 30 | 30 | Small Cottage to 30 Priority HH | MOU
Baruwa | 826 | CGI | Global Communities | Yes | 660 |  |  | 660 |  | Confirmed w/Global Communities | 79.9%
Batase | 1520 | CGI | Plan International | Yes |  | 346 |  | 346 |  | IOM Pipeline | 22.76%
Bhimtar | 1250 | CGI | Maryknoll Fathers and Brothers Projects (MFBPN) | Yes | All |  |  | All | TBC | VDC Secretary | 100%
Bhotang | 825 | CGI | People in Need | Yes | 695 |  |  | 695 |  | SC Agency Tracker | 84.24%
Bhotechaur | 1750 | CGI | Mission East |  |  |  |  | 0 |  | VDC Secretary | 0%
BhoteNamlang | 1133 | CGI | Plan International | Yes |  | 225 |  | 225 |  | IOM Pipeline | 104.4%
|  | CGI | People in Need | No | 958 |  |  | 958 |  | SC Agency Tracker
Bhotsipa | 1280 | CGI | UN-HABITAT | Yes |  |  | 34 | 34 |  | SC Agency Tracker | 35.08%
|  | CGI | Women Development Advocacy Center | No | 121 |  |  | 121 |  | SC Agency Tracker
|  | CGI | Plan International | Yes |  | 294 |  | 294 |  | IOM Pipeline
Chautara | 1609 | CGI | Germany GIZ | No | 40 |  |  | 40 |  | SC Agency Tracker | 2.486%
Chokati | 840 | CGI | Oxfam | Yes | 300 |  |  | 300 |  | SC Agency Tracker | 35.71%
Dhuskun (Ghuskun) | 1036 | CGI | [5 empty] | 0 |  |  | 0%
Dubachaur | 1950 | CGI | Caritas Switzerland | Yes | 683 |  |  | 683 | Ward 1,2,3,4 | MOU | 96.82%
|  | CGI | Care Nepal | Yes | 1205 |  |  | 1205 | Ward 5,6,7,8,9 | SC Agency Tracker
Fulpingdanda | 1420 | CGI | Phase Nepal | Yes | 1389 |  |  | 1389 |  | SC Agency Tracker | 97.82%
Gati | 1199 | CGI | [5 empty] | 0 |  |  | 0%
Ghorthali | 645 | CGI | SOLIDARITY International | Yes | 534 |  |  | 534 |  | SC Agency Tracker | 82.79%
|  | CGI | Gulmi Sewa sangh, Gramin Hate maloo | No |  |  |  | 0 |  | VDC Secretary
Ghumthang (Dhumthang) | 750 | CGI | [5 empty] | 0 | Islamic foundation? Not yet started | VDC Secretary | 0%
Ghunsakot | 642 | CGI | People in Need | Yes | 585 |  |  | 585 |  | SC Agency Tracker | 103.6%
|  | CGI | Bishow Hindu Maha Sangh | No |  |  | 80 | 80 |  | VDC Secretary
Ghuyang (Thanpalchap) | 1140 | CGI | K.I. Nepal | No | 276 |  |  | 276 | TBC | VDC Secretary | 24.21%
Golche | 915 | CGI | Save the Children | Yes |  | 642 |  | 642 |  | SC Agency Tracker | 96.39%
|  | CGI | SOLIDARITY International | Yes |  | 240 |  | 240 |  | SC Agency Tracker
Gumba | 842 | CGI | Save the Children | Yes | 31 | 457 |  | 488 |  | SC Agency Tracker | 99.88%
|  | CGI | SOLIDARITY International | Yes | 294 | 59 |  | 353 |  | SC Agency Tracker
Hagam | 1160 | CGI | Phase Nepal | Yes | 1086 |  |  | 1086 |  | SC Agency Tracker | 93.62%
Haibung | 630 | CGI | Share and Care Nepal | Yes | 136 |  |  | 136 | 9 ward only | SC Agency Tracker | 21.59%
Helambu | 967 | CGI | Helari Trust | No | 600 |  |  | 600 |  | VDC Secretary | 98.24%
|  | CGI | Action Aid Nepal | No |  | 350 |  | 350 |  | SC Agency Tracker
Ichok | 1621 | CGI | Maiti Nepal | Yes |  |  |  | 0 | ward no 8 only | MOU | 21.59%
|  | CGI | Action Aid Nepal | No |  | 350 |  | 350 |  | SC Agency Tracker
Irkhu | 955 | CGI | UN-HABITAT | Yes |  | 32 |  | 32 |  | SC Agency Tracker | 3.351%
Jalbire | 728 | CGI | Phase Nepal | Yes | 702 |  |  | 702 |  | SC Agency Tracker | 96.43%
Jethal | 860 | CGI | HANDICAP International | No |  |  | 30 | 30 |  | VDC Secretary | 8.372%
|  | CGI | Habitat for Humanity Nepal |  | 42 |  |  | 42 | TSK- handed over to the VDC | SC Agency Tracker
Jyamire | 1835 | CGI | Plan International | Yes |  | 363 |  | 363 |  | IOM Pipeline | 19.78%
Kadambas | 1132 | CGI | Phase Nepal | Yes | 1003 |  |  | 1003 |  | SC Agency Tracker | 88.6%
Kalika | 670 | CGI | Impact Nepal | Yes |  |  | 625 | 625 | Tunnel Houses | VDC Secretary | 93.28%
Karthali | 1244 | CGI | SOLIDARITY International | Yes | 314 |  | 694 | 1008 |  | SC Agency Tracker | 81.03%
kiul | 1000 | CGI | Action Aid | Yes | 898 |  |  | 898 |  | VDC Secretary | 89.8%
Kubhinde | 1001 | CGI | UN-HABITAT | Yes |  | 37 |  | 37 |  | UN-HABITAT | 92.21%
|  | CGI | World Vision | Yes | 886 |  |  | 886 |  | SC Agency Tracker
Kunchok | 1335 | CGI | Micah Network Nepal | Yes | 1335 |  |  | 1335 |  | VDC Secretary | 100%
Lagarche | 884 | CGI | Care Nepal | No | 762 | 71 |  | 833 |  | SC Agency Tracker | 94.23%
Lisangkhu | 1252 | CGI | RELIEF International | Yes | 132 |  |  | 132 | For ward 8, 9 | SC Agency Tracker | 10.54%
Listokot | 1269 | CGI | [5 empty] | 0 |  |  | 0%
Mahangkal | 1375 | CGI | Action Aid | Yes | 702 |  |  | 702 |  | VDC Secretary | 51.05%
Maneswar | 1200 | CGI | [5 empty] | 0 |  |  | 0%
Mangkha | 2300 | CGI | Save the Children |  |  |  |  | 0 |  | SC Agency Tracker | 0%
|  | CGI | Namloo Nepal | No |  |  |  | 0 | For ward 2,3,4,5,9 | VDC Secretary
Marming | 1100 | CGI | [5 empty] | 0 |  |  | 0%
Melamchi | 1395 | CGI | Caritas Switzerland | Yes |  | 315 |  | 315 |  | MOU | 26.16%
|  | CGI | Madabari Sewa Samaj | No | 50 |  |  | 50 |  | VDC Secretary
Nawalpur | 940 | CGI | [5 empty] | 0 | No agency present | VDC Secretary | 0%
Palchok | 715 | CGI | Caritas Switzerland | Yes | 696 |  |  | 696 |  | SC Agency Tracker | 97.34%
Pangretar | 927 | CGI | Oxfam | Yes | 296 |  |  | 296 |  | SC Agency Tracker | 100%
|  | CGI | Terre des homes France | No |  |  | 100 | 100 |  | Info by Christian Aid
|  | CGI | Christian Aid | No |  |  | 531 | 531 |  | IOM Pipeline
Pangtang | 738 | CGI | Lutheran World Federation | No |  | 659 | 250 | 909 |  | IOM Pipeline | 142.1%
|  | CGI | Personal contribution |  | 140 |  |  | 140 |  | VDC Secretary
Pedku | 503 | CGI | Habitat for Humanity Nepal | Yes | 502 |  |  | 502 | TSK-included CGI Sheets (10PCs), Steel Reinforcing rod(re-bar)-4 PCs,Steel Tube/pipe (8 PCs), GI wire (1.5 KG) per HH | SC Agency Tracker | 99.8%
Phataksila | 1225 | CGI | Save the Children |  |  |  |  | 0 |  | SC Agency Tracker | 0%
Phulpingkatti | 1100 | CGI | [5 empty] | 0 |  |  | 0%
Phulpingkot | 1153 | CGI | Phase Nepal | Yes |  |  |  | 0 |  | SC Agency Tracker | 152.8%
|  | CGI | World Vision International | No | 1762 |  |  | 1762 | Data to be verified | VDC Secretary
Pipaldanda | 818 | CGI | [5 empty] | 0 | No agency present | VDC Secretary | 0%
Piskar | 675 | CGI | Gramin Hate maloo Sang | No |  |  |  | 0 | TBC | VDC Secretary | 0%
Ramche | 1009 | CGI | Oxfam | Yes |  | 501 |  | 501 |  | SC Agency Tracker | 49.65%
Sangachok | 3000 | CGI | [5 empty] | 0 | No agency present | VDC Secretary | 0%
Sanusirubari | 1182 | CGI | Peace Winds Japan | Yes | 1030 |  |  | 1030 |  | SC Agency Tracker | 116.8%
Sanusirubari |  | CGI | World Vision International | No | 350 |  |  | 350 |  | SC Agency Tracker
Selang | 667 | CGI | Lutheran World Federation | No |  | 777 | 250 | 1027 |  | SC Agency Tracker | 154%
Shikharpur | 850 | CGI | Plan International | Yes |  | 110 |  | 110 |  | IOM Pipeline | 12.94%
Sindhukot | 1120 | CGI | Caritas Switzerland | No | 1108 |  |  | 1108 |  |  | 98.93%
Sinpal Kavre | 837 | CGI | Plan International | Yes |  | 160 |  | 160 |  | IOM Pipeline | 19.12%
Sipapokharae | 1160 | CGI | UN-HABITAT | Yes |  |  | 49 | 49 |  | SC Agency Tracker | 6.379%
|  | CGI | Sindhu Utahan |  | 25 |  |  | 25 |  | VDC Secretary
Sunkhani | 949 | CGI | Oxfam | Yes | 161 | 200 |  | 361 |  | SC Agency Tracker | 104.4%
|  | CGI | Habitat for Humanity | No |  | 395 |  | 395 |  | SC Agency Tracker
|  | CGI | Isra Aid | No | 235 |  |  | 235 | Ward 7,9 | SC Agency Tracker
Syaule | 1164 | CGI | Plan International | Yes |  | 240 |  | 240 |  | IOM Pipeline | 20.62%
Talamarang | 1001 | CGI | Action Aid | No |  | 300 |  | 300 |  | SC Agency Tracker | 29.97%
Tatopani | 1500 | CGI | Oxfam | Yes |  | 329 |  | 329 |  | SC Agency Tracker | 21.93%
Tauthali | 1029 | CGI | [5 empty] | 0 | No agency present | VDC Secretary | 0%
Tekanpur | 595 | CGI | Christian Aid | No |  | 560 |  | 560 | No agency present | VDC Secretary | 94.12%
Thakani | 1070 | CGI | Care Nepal | In Process |  | 1070 |  | 1070 |  | Care Nepal | 100%
Thangpalkot | 860 | CGI | [5 empty] | 0 |  |  | 0%
Thokarpa | 1250 | CGI | Caritas Nepal | Yes | 1181 |  |  | 1181 |  | Caritas Nepal | 94.48%
Thulo Dhading | 770 | CGI | Habitat for Humanity Nepal | Yes | 1234 |  |  | 1234 |  | SC Agency Tracker | 160.3%
Thulo Pakhar | 1200 | CGI | Christian Aid | Yes | 956 |  |  | 956 | with Clean Energy Nepal | SC Agency Tracker | 79.67%
Thulo Sirubari | 2056 | CGI | Help-hilfe the Selbsthilfe EV | Yes |  | 1700 |  | 1700 |  | SC Agency Tracker | 82.68%
Thumpakhar | 1299 | CGI | Lutheran World Federation | No |  |  |  | 0 |  | IOM Pipeline | 0%
Yamuna Danda | 552 | CGI | Caritas Nepal | Yes | 237 | 245 |  | 482 |  | Caritas Nepal | 87.32%

## Blanket_0824
Sinduhpalchok Coverage of Blanket 24th Aug. 2015 | [5 empty] | Data Source: Shelter Cluster Agency Tracking, 24thAug 2015
VDC | HH_(2011 Census) | HH Updte 2015 | Implementing agency | Completed (HH) | Ongoing / In Country Stock (HH) | Planned (funded) (HH) | Grand Total(HH) | Coverage (Total vs HH updated 2015)
Attarpur | 464 | 711 | [5 empty] | 0%
Bandegaun | 1160 | 1450 | [5 empty] | 0%
Bansbari | 1102 | 1425 | We World Onlus | 100 | 100 |  | 200 | 88.49%
|  |  | Save the Children | 1061 |  |  | 1061
Banskharka | 588 | 875 | CARE | 1208 |  |  | 1208 | 138.1%
Baramchae | 705 | 850 | OXFAM | 813 |  |  | 813 | 95.65%
Barhabise | 1683 | 1848 | Germany-GIZ | 50 |  |  | 50 | 89.94%
|  |  | OXFAM | 1612 |  |  | 1612
Baruwa | 487 | 826 | CARE | 570 |  |  | 570 | 122.2%
|  |  | Save the Children | 439 |  |  | 439
Batase | 1152 | 1520 | [5 empty] | 0%
Bhimtar | 892 | 1250 | Save the Children | 27 |  |  | 27 | 2.16%
Bhotang | 624 | 825 | Save the Children | 300 |  |  | 300 | 133.7%
|  |  | CARE | 803 |  |  | 803
Bhotechaur | 792 | 1750 | MedAir-MissionEast | 276 |  | 1253 | 1529 | 93.09%
|  |  | We World Onlus | 100 |  |  | 100
BhoteNamlang | 1074 | 1133 | [5 empty] | 0%
Bhotsipa | 994 | 1280 | DDRC | 900 |  |  | 900 | 70.31%
Chautara | 1618 | 1609 | Germany-GIZ | 42 |  |  | 42 | 8.825%
|  |  | Save the Children | 100 |  |  | 100
Chokati | 627 | 840 | Himalayan Disaster Relief Volunteer Group | 50 |  |  | 50 | 87.14%
|  |  | OXFAM | 682 |  |  | 682
Dhuskun (Ghuskun) | 759 | 1036 | [5 empty] | 0%
Dubachaur | 1375 | 1950 | HELVETAS Swiss Intercooperation Nepal | 1650 |  |  | 1650 | 84.62%
Phataksila | 894 | 1225 | Save the Children | 803 |  |  | 803 | 65.55%
Fulpingdanda | 1054 | 1420 | [5 empty] | 0%
Phulpingkatti | 783 | 1100 | Caritas Nepal | 775 |  |  | 775 | 165.5%
|  |  | MedAir-MissionEast |  |  | 1045 | 1045
Phulpingkot | 904 | 1153 | World Vision International | 600 |  |  | 600 | 52.04%
Gati | 874 | 1199 | MedAir-MissionEast | 1237 |  |  | 1237 | 103.2%
Ghorthali | 465 | 645 | Mercy corps | 574 |  |  | 574 | 88.99%
Ghumthang (Dhumthang) | 851 | 750 | Himalayan Disaster Relief Volunteer Group | 20 |  |  | 20 | 149.3%
|  |  | Mercy corps | 1100 |  |  | 1100
Golche | 731 | 915 | People in Need |  | 915 |  | 915 | 100%
Gumba | 674 | 842 | [5 empty] | 0%
Ghunsakot | 449 | 642 | Welthungerhilfe | 580 |  |  | 580 | 90.34%
Hagam | 818 | 1160 | Himalayan Disaster Relief Volunteer Group | 61 |  |  | 61 | 178.9%
|  |  | Mercy corps |  |  | 900 | 900
|  |  | OXFAM | 1114 |  |  | 1114
Haibung | 576 | 630 | MedAir-MissionEast | 722 |  |  | 722 | 228.1%
|  |  | Save the Children | 715 |  |  | 715
Helambu | 656 | 967 | OXFAM | 738 |  |  | 738 | 171.5%
|  |  | HELVETAS Swiss Intercooperation Nepal | 920 |  |  | 920
Ichok | 1270 | 1621 | We World Onlus |  | 100 |  | 100 | 6.169%
Irkhu | 751 | 955 | [5 empty] | 0%
Jalbire | 611 | 728 | OXFAM | 477 |  |  | 477 | 65.52%
Jethal | 620 | 860 | Save the Children | 1240 |  |  | 1240 | 241.5%
|  |  | AWO International e. V | 837 |  |  | 837
Jyamire | 1199 | 1835 | Save the Children | 79 |  |  | 79 | 4.305%
Kadambas | 834 | 1132 | OXFAM | 955 |  |  | 955 | 84.36%
Kalika | 545 | 670 | OXFAM | 250 |  |  | 250 | 37.31%
Karthali | 836 | 1244 | Mercy corps |  |  | 1000 | 1000 | 80.39%
Kiul | 764 | 1000 | HELVETAS Swiss Intercooperation Nepal | 1048 |  |  | 1048 | 178.3%
|  |  | OXFAM | 635 |  |  | 635
|  |  | We World Onlus |  | 100 |  | 100
Kubhinde | 693 | 1001 | World Vision International | 886 |  |  | 886 | 88.51%
Kunchok | 927 | 1335 | OXFAM | 1051 |  |  | 1051 | 78.73%
Lagarche | 592 | 884 | Care | 731 |  |  | 731 | 82.69%
Lisangkhu | 938 | 1252 | Himalayan Disaster Relief Volunteer Group | 150 |  |  | 150 | 95.29%
|  |  | Caritas Nepal | 1043 |  |  | 1043
Listokot | 949 | 1269 | MedAir-MissionEast | 1240 |  |  | 1240 | 97.71%
Mahangkal | 1024 | 1375 | People in Need |  | 2599 |  | 2599 | 196.3%
|  |  | We World Onlus |  | 100 |  | 100
Maneswar | 789 | 1280 | Mercy corps | 924 |  |  | 924 | 72.19%
Mangkha | 1860 | 2300 | ACTED | 495 |  |  | 495 | 43.26%
|  |  | Save the Children | 500 |  |  | 500
Marming | 718 | 1100 | Arbeiter-Samariter- Bund Germany (ASB) |  | 1000 |  | 1000 | 90.91%
Melamchi | 1179 | 1395 | Save the Children | 1189 |  |  | 1189 | 198.9%
|  |  | We World Onlus |  | 100 |  | 100
|  |  | HELVETAS Swiss Intercooperation Nepal | 1485 |  |  | 1485
Nawalpur | 797 | 940 | [5 empty] | 0%
Palchok | 489 | 715 | HELVETAS Swiss Intercooperation Nepal | 675 |  |  | 675 | 94.41%
Pangretar | 762 | 927 | [5 empty] | 0%
Pangtang | 487 | 738 | OXFAM | 676 |  |  | 676 | 91.6%
Pedku | 391 | 503 | [5 empty] | 0%
Pipaldanda | 787 | 818 | [5 empty] | 0%
Piskar | 538 | 675 | MedAir-MissionEast | 610 |  |  | 610 | 90.37%
Ramche | 999 | 1009 | OXFAM | 966 |  |  | 966 | 202.5%
|  |  | Mercy corps | 1077 |  |  | 1077
Sangachok | 2128 | 3000 | Himalayan Disaster Relief Volunteer Group | 70 |  |  | 70 | 5.333%
|  |  | Save the Children | 90 |  |  | 90
Sanusirubari | 779 | 1182 | [5 empty] | 0%
Selang | 526 | 667 | [5 empty] | 0%
Shikharpur | 583 | 850 | [5 empty] | 0%
Sinpal Kavre | 833 | 837 | [5 empty] | 0%
Sindhukot | 681 | 1120 | MedAir-MissionEast | 1013 |  |  | 1013 | 99.38%
|  |  | We World Onlus | 100 |  |  | 100
Sipapokharae | 608 | 1160 | [5 empty] | 0%
Sunkhani | 626 | 949 | Caritas Nepal | 750 |  |  | 750 | 79.03%
| 626 | 949 | OXFAM | 698 |  |  | 698 | 73.55%
Syaule | 833 | 1164 | Save the Children | 1000 |  |  | 1000 | 85.91%
Talamarang | 716 | 1001 | Save the Children | 208 |  |  | 208 | 138.6%
|  |  | We World Onlus | 300 |  |  | 300
|  |  | Concern Worldwide | 879 |  |  | 879
Tatopani | 1733 | 1500 | OXFAM | 599 |  |  | 599 | 39.93%
Tauthali | 776 | 1029 | [5 empty] | 0%
Tekanpur | 422 | 595 | [5 empty] | 0%
Thakani | 718 | 1070 | Himalayan Disaster Relief Volunteer Group | 15 |  |  | 15 | 182%
|  |  | MedAir-MissionEast | 998 |  |  | 998
|  |  | Save the Children | 934 |  |  | 934
Ghuyang (Thanpalchap) | 822 | 1140 | Welthungerhilfe | 1042 |  |  | 1042 | 91.4%
Thangpalkot | 653 | 860 | [5 empty] | 0%
Thokarpa | 1036 | 1250 | Caritas Nepal | 1153 |  |  | 1153 | 92.24%
Thulo Dhading | 509 | 770 | Himalayan Disaster Relief Volunteer Group | 270 |  |  | 270 | 80.52%
|  |  | Samaritan's Purse | 350 |  |  | 350
Thulo Pakhar | 758 | 1200 | Himalayan Disaster Relief Volunteer Group | 50 |  |  | 50 | 126.4%
|  |  | AWO International e. V | 967 |  |  | 967
|  |  | Save the Children | 500 |  |  | 500
Thulo Sirubari | 1331 | 2056 | Samaritan's Purse | 210 |  |  | 210 | 10.21%
Thumpakhar | 997 | 1299 | AWO International e. V | 1203 |  |  | 1203 | 92.61%
Yamuna Danda | 393 | 552 | [5 empty] | 0%