# Urban and Settlement Approach WG

## Strategic Directions – reflections from cluster retreats

## October 2018

## Immediate priorities (2018)

- Settlement Approach Infographics

  - Develop key messages/content for Graphic Designer

- Country applied studies

  - Draft ToR

  - Propose to develop a very clear 2 pager: what is area/settlement based approach, its various forms/modalities in: assessment, planning/coordination; programming). Use as a ‘fact-sheet’ for the Iraq/Guatemala and 2019 country studies

  - Iraq case study

  - Guatemala study

- Relationship between Urban Settlement WG and the Global Alliance for Urban Crises

  - Keeping it informal to start.

- Case study analysis

  - Develop ToR.

- Identifying regional champions

  - Identify 1 - 2 per region

  - Develop generic ToR, including some benefits to them (e.g. funded participation in the regional consultations, informing country applied studies)

## Late 2018/2019 onwards

### ‘Settlements Approach’

- Settlements guidance note 2018 – 2020

  - Create an informal ‘advisory group’

  - Recruit consultant shortly for consistency in the approach & consultations, but in a phased/chunked style of work over 2019 & 2020)

  - Consultation in Geneva (or NY) to kick off (1st quarter 2019)

  - Plan 2 more regional consultations (2019/2020)

  - Plan 3 country applied studies (2019/2020): Engaging with HCs/RC, HCT/UNCT, clusters etc

  - Finalise settlements guidance note (2020)

- Proactive reach-out to other clusters/platforms

  - Presenting at other cluster SAGS (WASH; Protection)

  - Consider to merge/direct the gFSC Urban Livelihood WG into the Settlements WG.

  - HDNTT – engage (end October event)

  - IASC Strategic Directions – Urban Coordination Guidance note: Promote/roll out in Targeted countries (link this to the OFDA funded country applied studies)

- Ongoing ‘settlement/area based approach’ advocacy

  - Building on the above, identifying any opportunities to promote the approach. (IASC; other clusters; Global Alliance for Urban Crises; etc)

- Continued ‘piloting’ / support to rolling out the approach

  - Discuss with co-conveners and targeted WG members – ‘How can we/let us apply the approach within our own programs’. For example, identify a location for:

    - REACH to undertake area / settlements based assessment (within the frame of the shelter cluster… or not)

    - Shelter cluster rep, OCHA, CCCM rep, or a ‘responsibilised agency/NGO’ to commit to support the planning & IM for this specific location – ideally with municipal counterpart

    - CRS/ACTED/other WG partners to commit / aim to program based off the area/settlement based planning

  - Suggest the Iraq (2018) scoping trip and 2019 country applied studies work towards this.

- Targeted operational support in applying the settlements approach (coordination; IM; planning)

  - Reach out to UNHabitat’s UrbanHub

  - Could link this to OFDA’s country applied studies

  - Use to go hand-in-hand with the development of the settlement’s approach

### ‘Urban’

- Define the parameters for ‘urban’ within the WG

- Reach out to WG members and country cluster coordinators: What specific assistance are you needing in ‘urban’ crises.

- Identify links with HLP, rental etc. See what synergies/work streams we can collaborate on.

- Shelter cluster coordination training– ‘urban module’ development

  - Discuss with GSC co-lead agencies on interest for the WG to lead and develop an ‘urban’ module for the cluster coordination training. (And potentially a ‘settlement/area’ coordination model after the development of the guidance)