## Sheet1
Non-Food Items Working Group 2017 Plan
Task/Activity | Responsible | Status | Jan | Feb | Mar | April | May | June | July | Aug | Sept | Oct | Nov | Dec
Nairobi Workshop Outcomes | Gregg/Corinne
Compile and collate guidelines and forms relating to NFI distributions; review and post to the NFI Working Group website |  | In Progress
Share NFI distribution training material and simulation exercises |  | Not Started
Post NFI workshop report to GSC website |  | Complete
Post all presentations to GSC website |  | Complete
Organise NFI workshop in Asia |  | In Progress
Knowledge Management and Community of Practice | Corinne
Create a formal Community of Practice for the NFI working group under the GSC |  | Not Started
Harness IT solutions such as Linked-In, Slack.com and (open-sourced) knowledge management software to enhance the Community of Practice through: |  | Not Started
a) References, resources and documentation management |  | Not Started
b) Linking practitioners (by maintaining a database of expertise by technical competence and geographical experience) |  | Not Started
Collect, review and publish resources/documents and disseminate or share via the NFI website: |  | Not Started
o Distribution & Assessment documents |  | In Progress
o Post Distribution Monitoring tools and guidelines |  | In Progress
o Common Pipeline resources |  | In Progress
o IEC materials |  | In Progress
o NFI distribution training resources |  | Not Started
Vulnerability Scorecard | Gregg
Carry out detailed evaluation of suitability of the scorecards and potentially develop a 'build your own' kit | Elizabeth Mayer (WVI) | In Progress
Pilot study in 2 countries (Somalia+1) to look at ranking of NFIs for different disaster context and climate. |  | Not Started
Engage Oxford Brookes University to assist with statistical analysis |  | Not Started
Not Started
Non-Food Item Fairs | Gregg
Complete NFI fair manual/guidelines |  | In Progress
Assist UNICEF translate NFI fair manual / guidelines into English and disseminate |  | Not Started
Not Started
Quality Control | Corinne
GSC to explore the possibility of prepositioning quality control equipment and through cluster partners (ICRC?), offer training on key tests on common items such as CGI |  | Not Started
Provide details of minimum QC tools, estimated pricing and potential suppliers |  | Not Started
Develop Common Pipeline tool kit with recommended SOPs and examples of forms used |  | Not Started
Share resources and lessons learned already available – S. Sudan / Pakistan / Haiti etc |  | Not Started
Not Started
Othe Outcomes not Prioritised for 2017 | Gregg/Corinne
Harnessing (new) technology for registration and assessments - Compile information about software such as LMMS, Scope and Red Rose and develop guidance for dissemination |  | Not Started
14. NFI Classification, typology and responsibility for tracking items - Continue work commenced in NFI WG workshop to refine the list of NFIs by typology and use the list to advocate, at GSC level, for engagement with other global clusters to agree on a common understanding of roles and responsibilities vis a vis NFIs across the different sectors |  | Not Started
"Selecting NFI for Shelter" Guidelines - Review publication and consider whether to produce a new edition or promote existing edition |  | Not Started
Fire Safety Check List - Develop generic check list or consideration matrix to facilitate the development of fire safety programming and messaging. Share resources and lessons learned from Lebanon, Jordan Iraq, etc |  | Not Started
Post Distribution Monitoring of use of plastic sheeting (PS): A lot of the group discussion centred on the various uses of plastic sheeting and what constitutes a shelter response. The resulting recommendation is to develop and roll out across 4 - 5 countries a PDM that specifically looks at the use of PS provided as part of NFI kit and analyses how PS is actually used and reported |  | Not Started

## Sheet2
Not Started
In Progress
Complete
Overdue